## Arizona 2016 End of Year
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes ( What is the reach and impact of these activities? How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics)
1. One Health Social Media Messaging | Blog shared by ADHS Director on One Health Event on 11/5/206 (see attached) | Addressed objective 1. Blog shared through facebook and on ADHS website. Reach was estimated to be 250+ unique individuals.
| 10 social media posts shared on One Health, zoonotic disease prevention, food safety, and importance of handwashing when interacting with animals | Addressed objectives 1, 2, 3, and 4
| Finalizing content for One Health website, to launch in early 2017 | In progress
2. Protect you and the Zoo from Flu | Conference call October 24, 2016 with project partners to plan and discuss grant activities. | Logistics and planning meeting for Protect you and the Zoo from Flu event with collaborating agencies. Addresses objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth
| Hosted Protect you and the Zoo from Flu (11/5/2016). See word document for detailed activity description. | Addressed multiple objectives, flyer attached. Addressed objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth. 114 influenza vaccinations were administered and over 500 families were educated. Share information from event with stakeholders.
| Continued distribution of One Health educational materials, including the fact sheet. | Addresses objective 1, 2, 3, and 4. One-page fact sheet on One Health was widely distributed at public education events. Fact sheet will increase awareness and knowledge of One Health (including careers in human and animal health), motivate participants to adopt behavior that can help prevent zoonotic disease transmission, and facilitate understanding among youth about roles of Arizona professionals in One Health.
3. Other | Disseminated revised toolkit for animal vendors at agricultural fairs (state/county) and youth events. | Impact is to enhance awareness of zoonotic disease transmission mechanisms and understand preventive measures that can be taken at various public settings.
| Educational booth and outreach at Arizona State Fair Public Safety Days, Oct. 29-30, 2016 | Impact is to enhance awareness of zoonotic disease transmission mechanisms and understand preventive measures that can be taken at various public settings.
| 5-year data analysis review and report compiled for Salmonellosis infections with animal exposures | Addresses objectives 1, 2, 3, 4, and 5. Review shared with stakeholders.
| One Health Day Activities on November 3, 2016 | Fostered relationships with stakeholders on One Health and continued capacity building and idea sharing for future activities. See word document for detailed activities.
| Future planning activities, including conference call with AZ 4-H Assistant Director to discuss 2017 outreach | Addresses objective 5
4. One Health Career Exploration Day | Completed evaluations | Summary: 31 students attended and participated in interactive activities/presentations focused on public health, one health careers, rabies, food safety, biosecurity, farm health, disease transmission routes, outbreak investigations, and wildlife health. The post-evaluation survey (attached) was comprised of 14 questions. 64% accurately defined One Health, 81% defined outbreak and food safety practices, 94% defined PPE measures to prevent disease spread, 52% defined zoonoses. Post evaluation showed a 65% increase in knowledge post event.