Influenza Education among Youth in Agriculture
Final Progress Report, Arizona


Please return completed Progress Report to CSTE at mschroeder@cste.org.  

1. Identify your top three achievements over the last quarter. 
a. Protect you and the Zoo from Flu
b. One Health Day—November 3, 2016
c. Future One Health Planning Activities
· Pets in the classroom/animals on school-grounds survey to teachers
· Provide prevention toolkits and presentations. 
· 4-H Biosecurity toolkits
· One Health curriculum and interactive activities.

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health) 

· Arizona Department of Health Services: main leader for project activities, coordinating and developing structure and objectives for One Health Career Exploration Day and One Health outreach in Arizona. Identification and bringing together of key partners for One Health and zoonoses prevention and response are conducted by ADHS. Lead coordinator in One Health Day activities and Protect you and the Zoo from Flu.

· Maricopa County Department of Public Health: secondary lead for project activities and plays large role in developing and implementing outreach objectives for One Health message. Assisted with Protect you and the Zoo from Flu event by providing and administering influenza vaccinations. 

· Arizona Department of Agriculture and Arizona Game and Fish Department: participatory role in project activity development and outreach, as well as One Health Day. 

· Midwestern University College of Veterinary Medicine and University of Arizona: hosted One Health Day events for students. 

3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
· Our key challenge was completing the online modules and website launch for 2016. However, we have had successful conversations with the Arizona 4-H Assistant Director and have drafted some future activities to engage 4-H and target Arizona youth. 

4. Please include an updated project timeline (see below, only included relevant components). 

October
· Developed and disseminated flyer for Protect you and the Zoo from Flu
· Gathered materials for Protect you and the Zoo from Flu
· Attended Arizona State Fair and distributed One Health materials at educational booth during at Public Safety Days, Oct. 29-30
· Prepared for One Health Day events at agency
· Conference call with participating staff to discuss and confirm logistics for Protect you and the Zoo from Flu 
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November
· November 3: One Health Day hosted. Arizona Department of Health Services collaborated with various partners to host activities for the agency to enhance awareness and understanding of the One Health concept. Activities included:
· Staffing an educational table with give-ways to promote One Health and disease prevention. 
· Streaming CDC Video One Health: from Concept to Action.
· Shared messaging via social media, agency emails, and blogs (e.g. will include link to CDC podcast “People Can Catch Diseases from Their Pets”).
· Photograph of agency staff wearing One Health Champion t-shirts to use with messaging.
· Hosted an interactive One Health Lunch and Learn with presentations and prizes from Department of Health Services (food safety and enteric disease team), Department of Agriculture, and Game and Fish Department. 
· Participated in panel discussions with Midwestern University College and Veterinary Medicine and University of Arizona during a screening of the PBS documentary “Spillover: Zika, Ebola, and Beyond”.
· November 5: Protect you and the Zoo from Flu hosted. Exceeded our target of 100 influenza vaccines administered. (114 were given). This was a very successful event hosted with the Phoenix Zoo and is likely something we would do again next year.
· Continued outreach through social media

December 
· Collected influenza vaccination data from event and compile report for stakeholders
· Built plans for sustainability of One Health partnerships and initiatives amongst Arizona public health and animal health partners.
· Veterinary student intern developed One Health curriculum materials for teachers and youth (all in draft form, implementation planned for next year)


5. If you have materials you are already distributing, please include a sample PDF or link of those materials.  

Attached and uploaded to Basecamp!

6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.

Arizona does not require additional assistance at this time. We enjoyed being a part of the 2016 project and are excited about the Basecamp website for sharing of materials. There are many projects that other states have engaged in this year that Arizona would like to adapt for the future. 

7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables. 

Attached, the only deliverable that is still in progress is our website. We were unsuccessful in launching the contests originally proposed in the grant, however were very pleased with the events that we hosted and our outreach efforts.

