	July 20, 2021
	Rob to do walkthrough of design options (flat file) with some YIA content for reaction during CSTE/CDC call

	TBD August 2021
	Rob to do walkthrough of two final design options (flat file) with YIA content for reaction during virtual grantees workshop (site feedback)
*invite eval to meeting to help document and gather feedback

Amy Panzer to present some graphic designs/logos for reaction from sites during virtual workshop

	September 21, 2021
	Update/walkthrough of most recent website iteration on CSTE/CDC call (actual website with working links)

	October 19, 2021
	Update/walkthrough of most recent website iteration on CSTE/CDC call (as needed)

	TBD November 2021
	Walkthrough of updated website with funded sites for final feedback/comments

	December 31, 2021
	Final website look completed and ready for dissemination

	January 2022
	Communicate and share new website broadly
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