
Please return completed Interim Progress Report to CSTE at mhuynh@cste.org by July 31, 2021.
Note: Please submit one response per site.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: 
· Develop Spanish versions of the "Bring Home the Blue, Not the Flu!" content and courses
Accomplishments/Progress to-date:
· Elementary course content has been translated to Spanish and reviewed/edited for accuracy, consistency, and clarity of the translated content.
· Middle/high school course content has been translated to Spanish and reviewed/edited for accuracy, consistency, and clarity of the translated content.
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)
· N/A (translation is complete but creation of the Spanish version of the website and uploading of the course to this site is a separate deliverable for Phase 2; will include in final progress report)

· Deliverable 2: 
· Modify “Bring Home the Blue, Not the Flu!” resources to incorporate into Google Classroom and Seesaw
Accomplishments/Progress to-date:
· Created Google Classroom and Seesaw activities, notes, and supplemental resources for multiple grade levels
· Created guides for teachers utilizing Seesaw and Google Classroom
· Establish procedures for the future use of Seesaw and Google Classroom
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)
· N/A (Adding Seesaw and Google Classroom lessons to BlueNotFlu.org for access by teachers is a separate deliverable for Phase 2; will include in final progress report)

· Deliverable 3:
· Conduct outreach to youth and adults in Iowa using all materials created
Accomplishments/Progress to-date:
· Present an interactive, in-person workshop at the Iowa FFA Association Leadership Conference to youth
· Present an interactive, in-person workshop at the 4-H State Conference to youth
· Present an interactive, virtual workshop at the World Food Prize Iowa Youth Institute to youth
· Host a train-the-trainer workshop for adults and youth in 4-H leadership positions at the Worth County Fair (youth Community Action Plan [CAP] project); participate in interactive, in-person workshop at the Worth County Fair
· Host an interactive, in-person workshop for youth in Franklin County
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 4: 
· Alignment of the “Bring Home the Blue, Not the Flu!” curriculum with various national curriculum standards
Accomplishments/Progress to-date:
· Curriculum approved for incorporation into the National Agriculture in the Classroom matrix 
· Curriculum approved for incorporation into the Iowa Agriculture Literacy Foundation lesson plans
Did this deliverable include an educational intervention: Yes / No
		(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 5:
· Maintain the courses and supplemental material completed in past funding cycles
Accomplishments/Progress to-date:
· Track visits to the course webpage and courses
· Answer requests for help/information
Did this deliverable include an educational intervention: Yes / No
		(If Yes, please complete the Impact Chart appended to this report.)

2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H/FFA, State PH, State Animal Health).
· State Public Health: Overall project leadership, deliverable review
· CFSPH: Project management, completion of deliverables, completes, leads, or coordinates outreach activities
· State Animal Health: Deliverable review, connection to facilitate participation in events related to fairs and exhibitions
· Iowa 4-H: connection to facilitate participation in multiple 4-H events; multiple trained trainers throughout Iowa who can/have completed outreach within their 4-H clubs, at fairs, etc.
· Iowa FFA: connection to facilitate participation in multiple FFA events; multiple trained trainers throughout Iowa who can/have completed outreach within their classrooms, etc.
· Nevada 4-H: deliverable review, participates in train-the-trainer events and facilitates outreach activities within Nevada 4-H

3) As relevant, describe areas of concern or challenges in meeting the objectives or providing deliverables especially as it relates to COVID-19.
· Some personnel changes/hiring delays which have created delays in anticipated completion of deliverables within Phase 1; no concerns with being able to complete Phase 1 and Phase 2 deliverables fully by completion of project period
· Some adjustments/delays in event scheduling due to reassessment of events after COVID-19; mitigation by substitution of similar activities  

4) Please outline your evaluation goals and timeline for the remainder of the project period (August 1 – December 31, 2021). 
· Deliverable: Develop Spanish versions of the "Bring Home the Blue, Not the Flu!" content and courses
· Translate supplemental resources (August), educator materials (September), Hands-on activity guides (October), Pre- and post- evaluation surveys (November), and website explanatory content (December) to Spanish; review/edit for accuracy, clarity, and consistency of translated content
· Develop new versions of the online courses to portray diversity and create a welcoming culture/environment (November)
· Deliverable: Create a Spanish version of the BlueNotFlu.org website
· Set up servers for appropriate URL, create theme and incorporate photos into the website, develop systems to track and report site activity, and develop privacy and site use policies (December)
· Deliverable: Promote the Spanish website to Iowa and US users (December)
· Deliverable: Promote SeeSaw and Google Classroom lessons to educators in Iowa and the US
· Add Seesaw and Google Classroom materials to BlueNotFlu.org (December)
· Update repositories for Blue not Flu curriculum (December)
· Add content to Teachers Pay Teachers website (December)
· Circulate information about lessons to state and national partners (December)
· Deliverable: Conduct outreach to youth and adults in Iowa using all materials created
· Present an interactive, virtual workshop at the Association of Iowa Fairs Annual Conference to fair board members and other attendees (December 2021 or January 2022)
· Present an interactive, virtual workshop at the Iowa FFA Association Immersion activity (by December)
· Present an interactive, virtual workshop at the Iowa FFA Precision Ag Day s (by December)
· Deliverable: Conduct outreach to adults in Nevada using materials created and train-the-trainer sessions
· Allow access to all content to the University of Nevada, Reno Extension (UNR) (August)
· Organize web based train-the-trainer sessions for how to use the resources for UNR (by December)
· Host and facilitate train-the-trainer sessions for UNR (by December)
· Deliverable: Conduct outreach to youth in Nevada
· UNR Extension and other Nevada youth educators will utilize “Bring Home the Blue, Not the Flu!” course at workshops (by December)
· Provide materials to UNR Extension agents and planning intentions (by December)

5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424). For Basecamp access, please email mhuynh@cste.org. 

OPTIONAL (responses to these prompts are not required but your input is greatly appreciated and welcome):

· If you have a story or anecdotal example of:

· how an individual, group, or community was positively impacted as a result of your YIA project’s interventions; 
· how an outbreak response that was better facilitated as a result of strengthened One Health collaboratives and relationships built through this project; OR
· how Youth in Agriculture network, relationships, or program activities helped in your state’s fight against COVID
either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership.

YES
Example from email received from Iowa 4-H Extension agent: 

“We did a similar event up in [another county] on Saturday! It went so well I’m really really really liking doing the activities. We had kids of all ages, mostly young, who really understood the concepts afterwards!”

· Would it be valuable for your site if the Youth in Agriculture program developed a standardized set of learning objectives, lessons, etc. to expand the reach of the program beyond your site? If so, would you be interested in contributing or being further involved in discussions around the development of a national standardized curriculum?

Iowa has already taken a national approach with their materials, and have recently been able to align with various national and state curriculum standards, including the National Agricultural Literacy Outcomes, Common Core standards, Next Generation Science Standards, National Health Education Standards, and Iowa Core Standards. This enabled the curriculum to be considered for and approved to be integrated into the National Agriculture in the Classroom matrix and the Iowa Agriculture Literacy Foundation lesson plans, which have significant reach among agriculture educators. The courses have also passed National 4-H peer review and Iowa 4-H peer review. We would potentially be interested in being further involved in discussions which would facilitate incorporation of our materials into other states’ standards/lesson plans/matrices, and are happy to contribute to discussions around the national standardized curriculum. 




· Are there other areas of interest or suggestions that CSTE/CDC could work with sites to improve national reach of the Youth in Agriculture program? Please describe as you see fit.

The all-site calls are nice to hear updates from other sites to spur ideas for our own site and the program as a whole. However, the upcoming all-site meeting will be especially valuable as it’s difficult to have much back-and-forth exchange of ideas during the all-site calls due to the limited time available. I do think that once meetings are able to be held in-person again that would be a much better format for this.

· With the revamp of the Youth in Agriculture resource repository underway, we welcome feedback on changes you would like to see addressed during this update. The intent of the revamp is to make the resource repository more user-friendly for YIA sites and for users seeking educational resources. Current re-design plans are listed below; if you have additional suggestions, please provide them below and/or feel free to comment on the usefulness of the bulleted items below:

		Current redesign plans include:
· User-friendly, visually appealing layout with mobile-friendly design 
· Resources appear as card-style design with preview content (e.g., picture, short description, tags, author)
· Resources can be filtered by content area, audience, format, etc.
· Each individual resource has a static link for ease of sharing and has social media share buttons
· We are exploring the feasibility for sites to upload their own content 
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Interim Progress Report
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	We suggest a website modeled similarly to the Ready Kids resource library, which incorporates most of the plans described above: https://www.ready.gov/kids/resource-library (although could be improved in some areas such as visual appeal/in-focus icons, etc.). I believe all of the plans outlined above are useful and important. 
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2021 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2021 to X total youth aged 11-15
	Only counted the number of actual youths who attended the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	“Bring Home the Blue, Not the Flu!” online course (www.bluenotflu.org) 
	2020 Values:

Total visitors to the website: 1,731

Unique visitors to the website: 1,451

Took the middle/high school course: 360

Took the elementary course: 155

Logins to the password-protected instructor version of the website: 70
	Unique visitors
	Anyone with internet access
	Values from January 1, 2021 through July 19, 2021: 

Total visitors to the website: 1,366

Unique visitors to the website: 1,184

Took the middle/high school course: 11

Took the elementary course: 22

Logins to the password-protected instructor version of the website: 13
	N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete; NE has unique online form from 2019 collaboration
	Yes; 31 (incl. 2 from NE); optional for individuals who completed online course 
	Yes; 31 (incl. 2 from NE); optional for individuals who completed online course


	Course availability on the National Agriculture Literacy Curriculum Matrix:  https://agclassroom.org/matrix/search_result/?search=bluenotflu 
	None
	N/A
	Anyone with internet access; primary users are Ag Ed teachers
	Bring Home the Blue, Not the Flu (Grades 3-5): 
225 pageviews

Bring Home the Blue, Not the Flu (Grades 6-8): 
167 pageviews

Bring Home the Blue, Not the Flu (Grades 9-12): 
130 pageviews

Bring Home the Blue, Not the Flu online modules: 
71 pageviews
	N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete
	N/A
	N/A

	Course availability on the Iowa Agriculture Literacy Foundation Matrix: https://www.iowaagliteracy.org/Search?q=bring+home+the+blue+not+the+flu 
	None
	N/A
	Anyone with internet access; primary users are Ag Ed teachers in Iowa
	78 total pageviews:

Lesson 1 – 21 views
Lesson 2 – 19 views
Lesson 3 – 11 views
Lesson 4 – 11 views
Lesson 5 – 9 views
Lesson 6 – 7 views
	N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete
	N/A
	N/A

	Activity-based, in-person workshops
	Previous activity-based workshops have impacted approximately 600 youth over previous funding cycles
	Only counted the number of individuals who attended the workshops
	Youth (ranged from young children to high school students) 4-H and FFA members and fair attendees
	250 attendees total
 
State FFA Workshop: 75 attendees

State 4-H Conference Workshop: 25 attendees

Worth County Fair- 4-H Community Action Project:
75 attendees

Franklin County Fair outreach: 
75 attendees
	 Branded stickers, “stress ball” animals, and informational handouts available to all attendees
	N/A
	N/A
	N/A

	Virtual or recorded workshops
	8 youth attendees participate in 2020 virtual Animal Cy-ience Academy
	We measured only the number of youth and adults that attended the session. 
	Youth participating in the WFP IYI and the WISE STEM conference
	World Food Prize Iowa Youth Institute Immersion: 20 attendees

Women in Science and Engineering ‘Go Further’ STEM session: How to be a Disease Detective ( https://www.youtube.com/watch?v=dUlaP4y_wOA): 7 views
	
	N/A
	N/A
	N/A






