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Please return completed Interim Progress Report to CSTE at mhuynh@cste.org by July 31, 2021.
Note: Please submit one response per site.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Online training for 4-H and FFA students on novel influenza and other zoonotic diseases using a One Health approach. 

Accomplishments/Progress to-date: We utilized the existing Maryland and West Virginia 4-H Animal Husbandry and Quality Assurance (AH&QA) online training as a platform for delivering novel influenza and other zoonotic disease subject matter content in a One Health framework to 4-H and FFA students in Maryland and West Virginia. The system opened 4/15/21 and closed 8/10/21 Preliminary completion results show 900 junior and 2,350 intermediate/senior aged youth registered and completed the online training.

Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 2: Healthy Animals | Healthy YOUth Activity Kits - Train-the-Trainer Training and NEW Teen Ambassadors program.  

Accomplishments/Progress to-date: One train-the-trainer event was held in for 17 new adult in March. Twenty-five teens trained at two training sessions held in June to serve as Ambassadors to facilitate activities from the Zoonosis Activity Kit. Lessons were used at a July 6 – Frederick Animal Health Day for 20 youth and on July 20 & 23 as part of the Maryland 4-H Camp in a Box program for 110 youth. Teen Ambassadors led several sessions at recent summer camp programs (outreach data is still being collected).

Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 3: NEW Healthy Animals | Healthy YOUth Interactive Displays 

Accomplishments/Progress to-date: Interactive displays about zoonotic disease awareness and prevention topics have been created for use at County and State Fairs targeting Fair Livestock Exhibitors, and Fair-going General Public. The displays are being launched at the West Virginia State Fair during August 12-21, 2021 and the Maryland State Fair during August 26-September 6, 2021.

Did this deliverable include an educational intervention: Yes / No (In progress)
(If Yes, please complete the Impact Chart appended to this report.)


· Deliverable 4: Production of permanent signage to encourage zoonotic disease prevention at Maryland and West Virginia agricultural fairs. 

Accomplishments/Progress to-date: A set of 7 different hand washing signs were produced on high quality aluminum (12x18”). A set was provided to each county and state fair across Maryland and West Virginia. The signs are being posted in livestock barn and public areas to encourage hand washing by exhibitors and the public after interacting with animal exhibits.

Did this deliverable include an educational intervention: Yes / No (In progress)
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 5: 2021 “Stay Healthy at (Maryland) Fairs” Symposium 

Accomplishments/Progress to-date: The 2021 “Stay Healthy at Maryland Fairs” Symposium will be the first event of its kind being offered by the Maryland Department of Health and its partner academic institution, University of Maryland Extension 4-H Youth Development. The event is scheduled for November 4th and though originally planned as an in-person event, it will most likely need to shift to virtual delivery because of growing restrictions on in-person events due to COVID-19.

Did this deliverable include an educational intervention: Yes / No (YES, will occur in November)
(If Yes, please complete the Impact Chart appended to this report.)

2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H/FFA, State PH, State Animal Health).

	 Collaborators involved to-date.

	Agency/Organization
	Position Titles involved
	Role in the Project

	Maryland Department of Health
	State Public Health Veterinarian
	Project lead. Human and Animal Health expertise

	University of Maryland Extension
	 4-H Youth Development Specialist, 4-H Program Coordinator, 4-H Youth Development Educators
	Project co-lead. Coordinates work team for creation of deliverables. Serves as curriculum writers and provides project training and distribution of deliverables.

	West Virginia University Extension Service
	4-H Youth Ag Program Coordinator, Extension Wildlife Specialist
	Contributes to content development and project training and distribution

	Maryland Department of Agriculture
	State Animal Health Veterinarian
	Animal Health expertise






3) As relevant, describe areas of concern or challenges in meeting the objectives or providing deliverables especially as it relates to COVID-19.

The return to in-person programs in the latter part of Phase one permitted delivery of zoonosis education lessons to youth at camp and field day settings. Similarly, plans have been progressing to conduct the Stay Healthy at Maryland Fairs 2021 Symposium scheduled for November 4th as an in-person event. However, the changing dynamics of the pandemic and return to some restrictions for holding in-person programs may lead to the need to conduct the fall Fairs symposium virtually.

4) Please outline your evaluation goals and timeline for the remainder of the project period (August 1 – December 31, 2021). 

	Phase 2

	Dates
	Activities
	Details

	August 1, 2021-December 31, 2021
	Convene One Health Advisory Committee – conduct regular meetings to develop plan for educational materials and track progress, conduct prior to each check-in calls with national partners.
	Invite reps. from Maryland 4-H, MDH, MDA, Maryland Association of Fairs and Shows 

	September 1, 2021 -October 1, 2021
	Conduct evaluations of fair signage 
	

	October 1, 2021 – December 15, 2021
	Conduct statistical analysis of AH&QA pre and post-test data.
	1,977 youth consented to include their test responses in the evaluation study

	November 4, 2021
	Conduct “Stay Healthy at Maryland Fairs” Symposium. 
	

	November 4, 2021 – December 15, 2021
	Conduct “Stay Healthy at Maryland Fairs evaluation of Symposium.
	



5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424). For Basecamp access, please email mhuynh@cste.org. 

Items to be uploaded soon include:

· Files of the set of 7 handwashing signs produced for MD and WV fairs.
· Images and files of the items included in the new Healthy Animals | Healthy YOUth Interactive Displays produced for use at MD and WV fairs.


OPTIONAL (responses to these prompts are not required but your input is greatly appreciated and welcome):

· If you have a story or anecdotal example of:

· how an individual, group, or community was positively impacted as a result of your YIA project’s interventions; 
· how an outbreak response that was better facilitated as a result of strengthened One Health collaboratives and relationships built through this project; OR
· how Youth in Agriculture network, relationships, or program activities helped in your state’s fight against COVID
either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership.

YES to the first bulleted item.

· Would it be valuable for your site if the Youth in Agriculture program developed a standardized set of learning objectives, lessons, etc. to expand the reach of the program beyond your site? If so, would you be interested in contributing or being further involved in discussions around the development of a national standardized curriculum?

Suggestion: A standardized curriculum that is compiled by the participating sites in partnership with CSTE/CDC could be a valuable resource. However, continuing to have the different curriculum resources created by individual sites is also very valuable. The two would complement each other. Maryland would be interested in contributing or being further involved in discussions around the development of a national standardized curriculum.

· Are there other areas of interest or suggestions that CSTE/CDC could work with sites to improve national reach of the Youth in Agriculture program? Please describe as you see fit.

Suggestion: Once the repository is revamped, share the link and a short overview with 4-H and FFA programs to include on national, state, and local webpages. Many have a webpage with resources for youth engaged in animal agriculture and for school teachers.

· With the revamp of the Youth in Agriculture resource repository underway, we welcome feedback on changes you would like to see addressed during this update. The intent of the revamp is to make the resource repository more user-friendly for YIA sites and for users seeking educational resources. Current re-design plans are listed below; if you have additional suggestions, please provide them below and/or feel free to comment on the usefulness of the bulleted items below:

		Current redesign plans include:
· User-friendly, visually appealing layout with mobile-friendly design 
· Resources appear as card-style design with preview content (e.g., picture, short description, tags, author)
· Resources can be filtered by content area, audience, format, etc.
· Each individual resource has a static link for ease of sharing and has social media share buttons
· We are exploring the feasibility for sites to upload their own content 
	
2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Interim Progress Report
Site: _____Maryland___________________________
Completed by: ____Anderson and Crum___________________
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Additional Suggestion. Have site users provide basic information prior to download of resources to better track use.
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2021 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2021 to X total youth aged 11-15
	Only counted the number of actual youths who attended the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	850 junior and 2,200 intermediate/senior
	
	
	

	MD and WV Online AH&QA Program
	1859 junior and intermediate/senior aged youth registered and completed the online training in 2020
	Online training module – Site opened between 4/15/21 – 8/10/21. Individuals register and are assigned unique passcode
	MD and WV 4-H and FFA youth, ages 8-18. Parents, club leaders, and others can complete the program as guests
	Between 4/15/21-8/10/21, 
902 junior and 2,355 intermediate/senior aged youth completed the online training
	3,257 individuals completed the curriculum online 
	Maryland and West Virginia collaborated on the AH&QA program
	3,357 youth completed the Online AH&QA Training Pre-test.
1,977 consented to include their responses in the AH&QA program study.
	3,257 youth completed the Online AH&QA Training Post-test

	Train the Trainer Session
	42 facilitators trained in 2021. 
	Adults registered and participated in the training conducted via Zoom. Teens were trained at two in-person events.
	UMD and WVU faculty/staff / volunteers / fair officials and Zoonosis team members and guest speakers. 4-H teens in Maryland.
	17 new facilitators trained on March 18, 2021 via distance training. 25 teens trained as Zoonosis Ambassadors trained on June 5 and 28.
	40 kits to be distributed in MD County Health Depts. in conjunction with the November Healthy Maryland Fairs Symposium.
	Maryland and West Virginia
	0
	0

	National 4-H Youth Summit Presentations to Youth
	N/A
	Individuals registered for Conference and logged into virtual conference seminars
	Teens from various states 
	55 teens from multiple states learned about Healthy Animals |Healthy YOUth kits and lesson plans on March 6, 2021.
	Seminars conducted via 3 web-conferences 
	
	0
	14

	Activity Kits Resource Notebook/Lesson Plans used to conduct youth activities
	
	Sessions held in-person and virtually, Participants counted.
	4-H Youth 
	Frederick Animal Health Day        reached 20 youth on July 6.
 Maryland 4-H Camp in a Box reached 110 youth on July 20 & 23
	Sessions were conducted in-person and via web-conferences
	
	0
	0






