
Please return completed Interim Progress Report to CSTE at mhuynh@cste.org by July 31, 2021.
Note: Please submit one response per site.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Monthly Leadership Team meetings 
Accomplishments/Progress to-date: 
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 2: Pop Up/One Day Show Zoonotic Disease Education
Accomplishments/Progress to-date:
1. Develop print ready materials for dissemination that highlight One Health, manure management best practices; include signage and hand washing stations for one day shows.
2. Put together informational packets for sanctioning show groups (Michigan Show Pig, Michigan Lamb Shows, Farm Bureau and others)
3. Compile a list of 2021 pop up show contacts
4. Develop a social media campaign that will feature five professional social media messages that exhibition events and county fairs can utilize to help educate their participants and attendees on zoonotic diseases.
5. Produce 3 high quality videos for youth preparing for animal shows.
6. Develop a brochure that highlights zoonotic disease resources available on the MSUE Zoonotic Disease webpage.
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 3: Host a multi-state webinar for Extension staff in states not funded for CSTE YIA programs
Accomplishments/Progress to-date:
1. The webinar is scheduled to take place on November 9, 2021 at 3:00p.m. EDT
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)
· Deliverable 4: Develop Resources for Agritourism Businesses to employ best practices to protect human health
Accomplishments/Progress to-date:
1. Developing a needs assessment for Michigan Agrotourism Businesses that sell food and have onsite animals 
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)
· Deliverable 5: MDHHS:  Host Michigan 4-H Exploration Days “Be a Disease Detective” session
Accomplishments/Progress to-date:  Session was held June 24, 2021
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)



2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H/FFA, State PH, State Animal Health).
a. State Animal Health-presented on zoonotic disease prevention measures during the Pre-fair webinar hosted by MSU Extension on May 26, 2021. 

3) As relevant, describe areas of concern or challenges in meeting the objectives or providing deliverables especially as it relates to COVID-19.

4) Please outline your evaluation goals and timeline for the remainder of the project period (August 1 – December 31, 2021). 

· Continue to share resources created by Michigan and other organizations as part of the 2021 Influenza and Zoonoses Education among Youth in Agriculture Program (July- December)
· Create three short videos focused on Zoonotic Disease Prevention (July- October)
· Identify Agritourism businesses in Michigan and conduct a needs assessment for those businesses related to zoonotic disease awareness and prevention (July-September)
· Provide educational resources to Agritourism business identified in the goal above. (September- December)
· Develop marketing materials to highlight Zoonotic Disease Resources available on the MSU Extension website (June- September)
· Host a multistate webinar to share developed resources as part of the 2021 Influenza and Zoonoses Education among Youth in Agriculture Program (November)
5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424). For Basecamp access, please email mhuynh@cste.org. 



OPTIONAL (responses to these prompts are not required but your input is greatly appreciated and welcome):

· If you have a story or anecdotal example of:

· how an individual, group, or community was positively impacted as a result of your YIA project’s interventions; 
· how an outbreak response that was better facilitated as a result of strengthened One Health collaboratives and relationships built through this project; OR
· how Youth in Agriculture network, relationships, or program activities helped in your state’s fight against COVID
either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership.

· Would it be valuable for your site if the Youth in Agriculture program developed a standardized set of learning objectives, lessons, etc. to expand the reach of the program beyond your site? If so, would you be interested in contributing or being further involved in discussions around the development of a national standardized curriculum?

Yes, MSU Extension would be interested in contributing to a national standardized curriculum. 

· Are there other areas of interest or suggestions that CSTE/CDC could work with sites to improve national reach of the Youth in Agriculture program? Please describe as you see fit.

Could the CSTE/CDC partner with the Youth for the Quality Care of Animals (YQCA) to address zoonotic disease issues as part of their curriculum?  

· With the revamp of the Youth in Agriculture resource repository underway, we welcome feedback on changes you would like to see addressed during this update. The intent of the revamp is to make the resource repository more user-friendly for YIA sites and for users seeking educational resources. Current re-design plans are listed below; if you have additional suggestions, please provide them below and/or feel free to comment on the usefulness of the bulleted items below:

		Current redesign plans include:
· User-friendly, visually appealing layout with mobile-friendly design Yes, and making sure that they are Americans with Disability Act compliant for blind users for screen readers and other assistive technologies. 
· Resources appear as card-style design with preview content (e.g., picture, short description, tags, author)
· Resources can be filtered by content area, audience, format, etc. 
· Each individual resource has a static link for ease of sharing and has social media share buttons


2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Interim Progress Report
Site: ___Michigan_____________________________
Completed by: ___N. Babcock, K. Signs____________________
Date: ___7/30/2021____________________________

· We are exploring the feasibility for sites to upload their own content 
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2021 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2021 to X total youth aged 11-15
	Only counted the number of actual youths who attended the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	Host “Be a Disease Detective” Session during the virtual MSUE Exploration Days
	1 session, 8 youth participants
	Counted number of youth that participated
	Ages 13-18 years
	8
	One webinar
	No
	N/A
	N/A

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2021 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	






