## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened? What materials have been developed or produced as a result?) | Outcomes (What is the impact and reach of these activities? How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics))
1. Enhance existing Youth in Agriculture course | CFSPH began researching how to incorporate the existing course into the national 4-H curriculum through national 4-H development standards and peer review. CFSPH made edits to the existing course, as needed, to maintain content accuracy and timeliness. As a collaborating center with the OIE, CFSPH began pursuing OIE-logo placement on the existing course. | Incorporating the existing course into the national 4-H curriculum and obtaining OIE's support of the course through the addition of their logo would allow us to greatly expand the reach of our message to our target audience and would result in a much larger impact on both a national and international scale.
2. Promote and increase existing course distribution and implementation | CFSPH designed and printed materials for display and distribution at upcoming events (as listed in the project proposal). CFSPH hosted an exhibit table at the Iowa FFA Association Leadership Conference and State Convention (April 10-11, 2017; Ames, IA). Printed materials for youth, educators, and others at the State FFA Convention were provided. CFSPH hosted an exhibit table at the Iowa Association of Agricultural Educators Summer Conference (June 27, 2017; Ankeny, IA). Printed materials for youth, educators, and others at the Summer Conference were provided. CFSPH worked with the Ohio Department of Public Health and the Ohio State University (Dr. Andrew Bowman) to engage youth participation in the course at the 2017 World Pork Expo (June 5-9, 2017; Des Moines, IA) through the use of tablets. CFSPH also provided printed materials for youth, educators, and others at the World Pork Expo. CFSPH began making travel arrangements to host an exhibit table and possibly an interactive workshop at the National FFA Leadership Conference (October 25-28, 2017; Indianapolis, IN). CFSPH will began making arrangements to host an interactive event at the International Association of Fairs and Expositions Annual Convention (November 26-29, 2017; Las Vegas, NV). | Our attendance and participation in distributing our course materials at numerous exhibition venues has allowed us to directly interact not only with youth who will be taking the course but with educators that will be using our existing course in their science and agriculture curricula. We have received very positive feedback from exhibition attendees regarding the course and real-time information on user data associated with course web page views has shown extensive national and international distribution since release. Additionally, an optional evaluation component has indicated an increase in knowledge and plans to adopt disease prevention habits upon post-course completion.
3. Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course | CFSPH developed an outline and began researching content to create the new course. | The new course curriculum will build upon the existing course structure and will continue to be interactive and engaging. The expanded course curriculum will also focus on influenza and other zoonotic disease prevention, but it will be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons. Creating a course for this target audience will enable us to broaden the reach of these important educational materials to all ages.