Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. Hosted final Zone meeting in Michigan’s Upper Peninsula (Marquette) in May, 2018 with fair organizers, 4-H youth leaders, local public health, MSU Extension staff and state agriculture staff.  
b. Hosted our now annual “Be A Disease Detective” Session during the MSU Extension 4-H Exploration Days for 19 youth.  Session incorporates 5 hours of instruction over two half-day sessions.  This session introduces youth to disease agents and how they spread, what epidemiologists do, vocabulary and tools used in epidemiologic investigations, actions taken to stop an outbreak and methods for sharing information and preventing future outbreaks.  We were delighted to also host two fellow-grant recipients from Maine to showcase some of the activities that Michigan has developed for youth.
c. MSU Extension has hired Nick Babcock as the next Livestock and Veterinary Science Educator.  Nick will be starting in September and will be the primary liaison with MDHHS on completing the remaining activities funded by this grant.	
d. Presented at the annual MDHHS Communicable Disease Conference on April 24, 2018 about the Youth Ag Education project and its impact.  We provided Michigan local health department attendees with “Be Healthy at the Fair” posters to share with the fairs and festivals in their communities.
		 
2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
a.  MSU Extension 4-H staff:  continue to work with Jake DeDecker and look forward to working with Nick Babcock. Regional MSUE staff, Nancy Thelen, participated in the Marquette Zone meeting and presented on MSUE’s role in educating youth and their participation in the Educating Youth in Agriculture grant.
b. Fair administration:  MDHHS continues to partner with the Michigan Association of Fairs and Exhibitions executive staff (Steve Thelen and Lisa Reiff) completing the hosting of a series of meetings around the state for fair organizers, 4-H volunteers, animal superintendents and others to provide education about zoonotic disease risks, with an emphasis on influenza, associated with fairs and how to reduce risk and plan/prepare in the case of an outbreak at their fair. MDHHS also continues to work with MAFE to plan a training for Fair administrators on zoonotic disease awareness and prevention at fairs, with an emphasis on swine influenza, scheduled for October, 2018.
c. Public Health: MDHHS is encouraging Michigan local health departments to engage with their local fair organizers and 4-H volunteers to provide support and expert guidance regarding disease risk mitigation and also education for their exhibitors and the public.  We are emphasizing the value of establishing relationships before the event.  A response to ill animals or people at the fair can be better coordinated and carried out if plans are made in advance.  We presented at the annual MDHHS Communicable Disease Conference about the Youth Ag Education project and its impact.  We provided Michigan local health department attendees with “Be Healthy at the Fair” posters to share with the fairs and festivals in their communities. We are also in the process of working with our MDHHS Influenza staff on developing a Swine Influenza Response Toolkit for Michigan local health departments to utilize when pigs at an agricultural event in their jurisdiction are infected with swine influenza, or people are diagnosed with variant influenza.
d. Animal Health:  the Michigan Department of Agriculture and Rural Development regional veterinarian (Dr. Robinson) attended the “Be Healthy at the Fair” meeting and provided information about their role in animal health and disease response in the fair setting.
e. Two staff from the Maine Department of Agriculture, Conservation and Forestry, Cindy Kilgore and Donna Flint, visited Michigan June 20-22 to observe our MSUE 4-H Exploration Days “Be a Disease Detective” session.  They brought “Germo” games and taught the kids how to play. These games were a great way to reinforce the information they were learning about types of pathogens (viruses, bacteria, parasites) and the variety of species they can infect. Cindy and Donna also talked with the kids about biosecurity and how they can protect both their animals and themselves from diseases that animals and people can share. 
f. Utilized parts of the curriculum developed for this project to provide a session during an MSU summer program for Gifted and Talented Elementary-aged students.
g. International Association of Fairs and Exhibitions:  MDHHS has arranged with IAFE to provide their zoonotic disease prevention training workshop and to also address concerns about swine influenza.  These workshops are valued by fair organizers and in the past have focused on the risk of E. coli exposure at fairs.  Event is planned for October 13, 2018 on the campus of MSU.


3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
a. [bookmark: _GoBack]The MSU Extension Educator and primary partner in this project has now been hired, Nick Babcock. We look forward to moving ahead with ideas for videos and additional curriculum units on Epidemiology and Outbreak Response, “Healthy Habits” videos and Veterinary Science Camp curriculum. 
4. Please include an updated project timeline.
	April 2017:
	Notification of Award

	May-August 2017:  
Zone Meeting: COMPLETED
Camp: NOT DONE


Reprint signs: COMPLETED

Curriculum and videos:
September 2018-December 2018
	
Plan and invite attendees to the seven Zone Fall meetings
Develop curriculum for Veterinary Science Camp with partners (camp has been paused for 2018-pending hiring of MSU Extension staff)
Reprint and distribute “Be Healthy Around Animals” signage 

Creation of three short videos about healthy habits (pending hiring of MSU Extension staff)

	May 2017: NOT DONE
	Begin process of hiring additional student for part-time work (ongoing)

	August-November 2017:
COMPLETED 

	Conduct 7 zone meetings across the state in coordination with MAFE/MSUE/MDARD 

	TBD 2017:  
COMPLETED
	Three Michigan partners travel and participate in national CSTE Grantee Meeting

	June 21-23, 2017 
COMPLETED
	Present session “Be a Disease Detective” during 201 4-H Exploration Days  (Completed a Session for-June 21-22, 2018 too).

	June 26-30, 2017: 
COMPLETED  
	Organize/present “One Health” sessions at 4-H Animal and Veterinary Science Camp; hire 1 veterinary student mentor for each 10 campers

	May-November 2017:  
January 1-April 2018
(Postponed to October, 2018)
	Develop two Animal Science Anywhere curriculum units; 1) Epidemiology and 2) Outbreak Response
Develop “One Health” youth signage with ANR Communications



	October-December 2017:
COMPLETED

January 1 – April 2018
COMPLETED
	Compile questions and concerns from Zone meetings and prepare resources as needed

Contact IAFE about adapting their one day zoonotic disease training to include Swine Influenza (ongoing)

	January 11-13, 2018:
COMPLETED

	Michigan Association of Fairs Convention including a MDHHS/MSUE session about the Youth Ag Education Grant accomplishments; distributed copies of the NASPHV “Compendium of Measures to Prevent Disease Associated with Animals in Public Settings, 2017”

	March 2018:
FALL 2018
	Follow-up with Zone Meeting attendees to help prepare for 20189fairs, conduct follow-up KAP survey. 

	April May 2018: 
April 25, 2018
COMPLETED
	Combine evaluation data from presentations to determine impact
Present results from “Be Healthy at the Fair” meetings to Michigan Local Public Health staff at the annual Michigan Communicable Disease Conference 

	May 12, 2018
COMPLETED
	Host Last Zone Meeting with Upper Peninsula fairs and local health department staff, using remote webinar capabilities

	June 21-22, 2018
COMPLETED
	Host “Be a Disease Detective” Session at the MSU Extension Ag Exploration Days

	September-December 2018
	Host IAFE Fair Organizer Zoonotic Disease Prevention Training 





5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 


6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.


7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.


OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions , either describe it here or just write ‘YES’ and we will follow up with you via phone or at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 



