## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Summary of what was done (200 words or less). What activities have taken place over the past 4 months? How have these activities addressed one or more of the project objectives? | Impact If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
|  | Intervention Activity (and location) | Baseline # prior to 2017-18 grant period | How did you measure the baseline? Did you include direct participants, families, etc? | 2017-18 Audience (youth, community leaders, etc?) | # of attendees/participants | # of materials distributed | Pre-test administered? (How many? To whom?) | Post-test administered? (How many? To whom?) | Did you collaborate with another state? If so, which one(s)?
|  | EXAMPLE: Four Scenario based training exercises | X# of training sessions held in 2017 to X total youth aged 11-15 | Only counted the number of actual youth who attended the session | Youth aged between 12 and 16 | X # attendees per training; total of X attendees
Deliverable 1: (please inculde project deliverable here) Hosted "Be a Disease Detective" Session during MSUE Exploration Days | In June, 2017 MDHHS Epidemiologists and Laboratorians provided two half-day sessions for youth involved in 4-H around the activity of being a disease detective and solving an outbreak of variant influenza in a group of school children. This is the second year MDHHS has provided this activity during the annual MSU Extension Exploration Days. Participants learned how to investigate an outbreak, perform laboratory tests, analyze data to find the most likely source of the outbreak, and communicate information on prevention and control to the public. For the 2018, MDHHS again provided the session for Exploration Days, with 19 youth participating. We were fortunate to host two staff from the Maine Department of Agriculture, Conservation and Forestry, who were in Michigan to observe our program activities developed under this grant. They taught the kids how to play Germo and provided a session of biosecurity to the group. | For both the the 2017 and 2018 sessions, 20 and 19 youth enrolled, repectively. Through this activity, we met 1- 4 of the stated project objectives (improve awareness and knowledge of influenza and other zoonotic diseases, motivate participants to adopt behaviors to prevent zoonotic disease transmission, increase awareness of careers in public and animal health and facilitate a better understanding among participants of the role of the public and animal health play in disease prevention). | One session held in 2016, with about 30 participants. Class size was reduced for subsequent sessions due to time contraints of the activities that are part of the session. | Only counted the number of actual youth who attended the session | 2017: 20 youth; 2018: 19 youth | 2017: 20 youth; 2018: 19 youth | Each participant received a "Be a Disease Detective" workbook. | No | No | in 2018, staff from the Maine Department of Agriculture, Conservation and Forestry observed and participated in the session, as part of their grant-funded activities.
Deliverable 2: Provided a session for an MSU Gifted and Talented summer program for elemetary-aged students, June 29-July 1, 2018. | Curriculum and activities developed as part of this grant were utilized to develop lessions about veterinary medicine, epidemiology and One Health for 25 middle-school aged kids. | 3-90 minute educational sessions | new activity |  | Youth aged between 11-14 | 25 |  | No | No | No
Deliverable 3: Provide a 30 minute session about this project at the annual MDHHS Communicable Disease Conference on April 24, 2018. | Provided an overview of the Influenza and Zoonoses Education among Youth in Agriculture grant to Michigan local health department staff attending the annual MDHHS-hosted conference. We also distributed over 300 "Be Healthy at the Fair" signs to local health departments that attended, and encouraged them to utilize the signs to facilitate a dialogue with their local agricultural fair organizers. | Eudcational meeting of Michigan Local Health Department staff |  |  |  | 275 | 300+ "Be Healty at the Fair" posters | No | No | No
Deliverable 4: Successfully accomplish "Be Healthy at the Fair" Zone meetings | Met with project partners from MSU Extension and Michigan Association of Fairs and Exhibitions to plan for a series of evening meetings to foster collaborations at the local level on the topic of zoonotic disease prevention and control during community fair events. Invitees include fair organizers, 4-H leaders and animal superintendents, fair veterinarians, local public health, as well as state agriculture and public health staff and MSU extension staff. The meetings were planned for the evening, understanding that most people involved in local fairs are volunteers. Dinner was provided. This activity addresses the first 5 stated project objectives and in particular was focused on developing relationships among local stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues, in particular, outbreaks. | Seven Zone meetings were held between October 18, 2017 and May 12, 2018; October 18, 2017-Midland, MI; October 19, 2017-Marshall, MI; October 26, 2017-Saline, MI; November 1, 2017-Greenville, MI; November 8, 2017-Alpena, MI; November 9, 2017-Kalkaska, MI; May 12, 2018-Marquette, MI. | N/A | N/A |  | Midland: 24; Marshall: 22; Saline: 37; Greenville: 37; Alpena: 25; Kalkaska: 41; Marquette: 34 | N/A | Midland: 23; Marshall: 21; Saline: 33; Greenville: 33; Alpena: 25; Kalkaska: 40; Marquette: 33 | Midland: 22; Marshall: 19; Saline: 34; Greenville: 32; Alpena: 25; Kalkaska: 40; Marquette: 34 | No
Deliverable 5: Successfully fill MSUE Animal Science Educator position | MSUE was successful in recruiting and hiring Nick Babcock to fill this position. The person in this position has been a vital link and instrumental partner in working with youth involved in agriculture education. In Michigan, MSU Extension reaches over 200,000 youth through their programs. It is the single largest organization educating youth in agriculture in the state. Nick will start in September, 2018 and we look forward to working with him on the items that remain to be completed for this grant cycle.
Deliverable 6: Provide an additional training for Fair Organizers on biosecurity and zoonotic disease prevention for agricultural events in Michigan. | MDHHS facilitated an conference call with Ms. Marla Calico with the International Association of Fairs and Exhibitions (IAFE) to discuss the possibility of engaging her organization to provide a workshop on the topic of Zoonotic Disease Prevention, with an emphasis on Swine Influenza. IAFE has been offering this workshop targeted to fair orgainzers for a number of years around the U.S. and it has been well received by this audience. They are willing to adapt the workshop to include information about Swine Influenza. MDHHS and MAFE plan to host the Michigan day-long workshop on October 12, 2018. MDHHS will utilized funds from this grant to financially support up to 40 participants to attend. | Workshop, campus of MSU
Deliverable 7: Two additional "Animal Science Anywhere" curriculum units on Epidemiology and Outbreak Response. | Developing these units has been dependent on MSUE hiring a person for the vacant Livestock and Veterinary Science Educator position that served as our MSUE liaison for this grant. That person has been selected and will be starting September 10. He is aware of this project and this deliverable and we look forward to working with him to complete these curriculum units. | Two curriculum units
Deliverable 8: Up to three short videos for youth involved in agricultural programs around healthy habits. | Developing these units has been dependent on MSUE hiring a person for the vacant Livestock and Veterinary Science Educator position that served as our MSUE liaison for this grant. That person has been selected and will be starting September 10. He is aware of this project and this deliverable and we look forward to working with him to complete these videos. | Three "healthy habits" videos for youth involved in agricultural education
Deliverable 9: Work with partners to develop Veterinary Science Camp "One Health" curriculum. | In the past, MSUE has offered a Veterinary Science Camp to students who are interested in pursuing a career in Veterinary Medicine. This program was suspended for 2018 due to the vacancy in the Livestock and Veterinary Science Educator position. A candidate has been selected and will begin Sept. 10, 2018. MDHHS will work with MSUE to utilize many of the materials already developed as a result of this grant to renew the curriculum for this activity to include a "One Health" focus. | Update Veterinay Science Camp curriculum to include "One Health" priciples.