Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 

· Hired a summer intern to perform the following duties:
· Fair observations at county fairs and the ND state fair
· Design unique posters for barns containing animals
· Demonstrate Glo-germ and saliva swap (“train-the-trainer”)

· Hosted four-state summit (ND, SD, MT, WY) in May, 2018
· “Working Together for Healthier Fairs”
· Collaborated on various YIA topics throughout a two-day meeting

· Creation and distribution of a fair newsletter
· Highlighted resources for fair staff and fairgoers 
· 4-H website, NDDoH Disease Control website, NASPHV guide on “measures to prevent injuries and disease with animals”
· FYI on zoonotic diseases and why handwashing is important
· “6 C’s” of caring for livestock health at the fair


2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).

North Dakota:  
· ND Dept of Health, 
· ND Dept of Agriculture, Animal Division, 
· ND State Fair Director, 
· ND 4-H Youth in Agriculture Director.
South Dakota:
· SD Dept of Health
· SD Public Health Veterinarian
· SD Animal Industry Board 
Montana:
· MT Dept of Health & Human Services
· MT 4-H Youth Director
· USDA APHIS VS
· MT Public Health Veterinarian
Wyoming:
· WY Dept of Health
· USDA
· WY Public Health Veterinarian

*All organizations contributed to the meeting through presentations and group discussions. 

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
· Remaining in contact with rural fairs regarding feedback 
· Student intern retention with school starting up in early/mid-August
· When contacting the state fair to hold events or workshops the schedule was full and they weren’t able to fit us in. In the future, we will need to contact the state fair in advance (previous fall) to reserve times. 

4. Please include an updated project timeline.


	Objective One – Collaborative Development
	
	
	
	

	
	Activity
	
	Completion Date
	
	Updated Timeline

	
	
	
	
	
	

	
	Hire Student Intern
	
	September 30 2018
	
	10-Jun-18

	
	Meet with 4-H Youth Livestock Specialist
	
	31-Jul-17
	
	completed

	
	Meet with FFA Leaders
	
	31-Jul-17
	
	10-Aug-18

	
	Develop stakeholder meeting
	
	16-Aug-17
	
	completed

	
	
	
	
	
	

	Objective Two – Training Activities
	
	
	
	

	
	
	
	
	
	

	
	Activity
	
	Completion Date
	
	

	
	
	
	
	
	

	
	Iowa State University online training
	
	1-May-18
	
	completed

	
	MN Fair posters/placards/postcards
	
	1-Jun-18
	
	completed

	
	Georgia 4-H Friends Magazine
	
	1-Jun-18
	
	completed

	
	
	
	
	
	

	Objective Three – Summit
	
	
	
	

	
	
	
	
	
	

	
	Activity
	
	Completion Date
	
	

	
	
	
	
	
	

	
	    Invite MT/SD/WY to Summit
	
	21-Jul-17
	
	completed

	
	    Hold Summit
	
	29-Sep-17
	
	completed

	  
	    Finalize minutes and initial summit report
	
	31-Oct-17
	
	completed

	
	
	
	
	
	

	Objective Four – Evaluation
	
	
	
	

	
	
	
	Completion Date
	
	

	
	Activity
	
	
	
	

	
	
	
	
	
	

	
	In-person training evaluation survey
	
	31-Aug-17
	
	1-Oct-18

	
	Evaluation of online trainings and format
	
	20-Oct-17
	
	1-Oct-18

	
	Development of fair survey evaluation
	
	29-Dec-17
	
	1-Oct-18

	
	Evaluation of stakeholder’s strategic plan
	
	12-Jan-18
	
	1-Oct-18

	
	Finalize initial stakeholder report and send out
	
	9-Feb-18
	
	1-Oct-18




5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 

· [bookmark: _GoBack]Handwashing posters intended to be hung up at county fairs to remind fairgoers to wash their hands have been drafted and are currently being reviewed for printing. 

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.

· Provide connection or information from other states regarding their experiences connecting with rural fairs. This would be helpful for us as we find it difficult to contact and remain in contact with rural fair boards. 

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.


OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions , either describe it here or just write ‘YES’ and we will follow up with you via phone or at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 




