## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Summary of what was done (200 words or less). What activities have taken place over the past 4 months? How have these activities addressed one or more of the project objectives? | Impact If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
|  | Intervention Activity (and location) | Baseline # prior to 2017-18 grant period | How did you measure the baseline? Did you include direct participants, families, etc.? | 2017-18 Audience (youth, community leaders, etc.?) | # of attendees/participants | # of materials distributed | Pre-test administered? (How many? To whom?) | Post-test administered? (How many? To whom?) | Did you collaborate with another state? If so, which one(s)?
|  | EXAMPLE: Four Scenario based training exercises | X# of training sessions held in 2016 to X total youth aged 11-15 | Only counted the number of actual youth who attended the session | Youth aged between 12 and 16 | X # attendees per training; total of X attendees
1. Enhance existing Excellence in Exhibition course | CFSPH received official Iowa and National 4-H peer reviewed status for the middle–high school course. CFSPH finalized updates, including 508 compliance, to the currently available Excellence in Exhibition course for middle–high school youth. Certificate badges were created to be "earned" by completing lessons and the evaluation. | Offered course continuously through this time period | Began tracking course use April 24, 2017. Website www.bluenotflu.org was viewed by 68 unique users, and the online course was accessed 13 times by users in 7 states during April 24–May 1, 2017. | Counted unique users/views (did not count multiple views on same computer) | Target audience is youth aged 13–18 years but is open to anyone freely on the website | Website was viewed by 2,560 unique users, and the online course was accessed 1,458 times by users in 41 states during current funding period (May 1, 2017–June 30, 2018). |  | Combination pre/post test - 63 - youth, advisors, and parents | 63 - youth, advisors, and parents | Course available nationally Worked with National Pork Board to approve course Ohio used course at World Pork Expo activity North Dakota implementing course as training for 4-H skillathon | The optional evaluation component has indicated an increase in knowledge and plans to adopt disease prevention habits upon post-course completion.
2. Promote and increase existing course distribution and implementation | CFSPH hosted four interactive workshops for 115 Eastern Iowa youth participating in FSQA at Iowa State University (April 11). CFSPH hosted an exhibit table at the 2018 State FFA Leadership Convention April 23–24, 2018. Printed materials for attendees were provided. Plush animals, brushes, feed, and Glo Germ were used to demonstrate disease transmission. CFSPH presented a seminar and hosted an exhibit table at the 2018 Iowa Association of Agriculture Educators (IAAE) annual meeting June 26–27, 2018 in Ankeny, IA. Printed materials for attendees were provided. Plush animals, brushes, feed, and Glo Germ were used to demonstrate disease transmission. CFSPH hosted three interactive workshops at the Iowa 4-H Youth Conference, presented a seminar for the opening session at 4-H Animal Science Roundup, and hosted a swine-specific workshop at 4-H Animal Science Roundup (June 26–28, 2018). Interactive activities were used to demonstrate disease transmission, biosecurity, disease, prevention, and epidemiology. About 200 youth participated. All participants in 4-H Animal Science Roundup were required to take the Excellence in Exhibition course as their official biosecurity training prior to the conference. CFSPH attended North Dakota's "Healthy Fairs" meeting and workshop to present information about the Excellence in Exhibition course and experiences. CFSPH and the Iowa Department of Public Health presented an abstract at the CSTE annual meeting. CFSPH attended the World Pork Expo to distribute printed materials, promote the course, review the Ohio State University’s interactive booth, and seek donations for the enhanced evaluation incentives for youth (June 6–7, 2018). CFSPH worked with the National Pork Board to place a link to the course on the show pig section of the NPB website. | FSQA workshop, Ames, IA Iowa State FFA Leadership Convention exhibit table, Ames, IA IAAE workshop, Ankeny IA IAAE exhibit table, Ankeny, IA Iowa 4-H Youth Conference workshops (3) Iowa 4-H Animal Science Roundup opening session (3), Ames, IA Iowa 4-H Animal Science Roundup swine workshop, Ames, IA Healthy Fairs Workshop, Bismarck, ND CSTE annual meeting, West Palm Beach, FL World Pork Expo, Des Moines, IA | NA | Counted total conference and workshop attendees Counted total stickers distributed to date | FSQA - middle-high school aged youth Iowa FFA - Iowa high school aged youth and agriculture educators IAAE - Iowa agriculture educators Iowa 4-H Conference - Iowa high school aged youth who signed up for workshop Iowa 4-H Animal Science Roundup - Iowa high school aged youth Healthy Fairs Workshop - fair organizers, public health professionals, animal health professionals from ND, SD, MT, and WY CSTE - public health professionals World Pork Expo - youth exhibiting swine and parents | FSQA - 115 Iowa FFA - 5,000 IAAE exhibit table - 120 IAAE workshop - 3 Iowa 4-H Conference - 70 youth, approximately 6 adult volunteers Iowa 4-H Animal Science Roundup swine session workshop - 15 youth, 2 adult volunteers Iowa 4-H Animal Science Roundup opening session - 89 youth, approximately 10 adult volunteers Healthy Fairs Workshop - Approximately 25 CSTE - Approximately 150 World Pork Expo - Approximately 1,350 youth | Approximately 20,400 Bluenotflu.org stickers have been distributed | NA | NA | Collaborated with IAAE, Iowa FFA, Iowa 4-H, Ohio, North Dakota
3. Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course | CFSPH continued to develop the new course for a younger audience. | NA | 0 | NA | Youth aged 7–12 years | NA | NA | NA | NA | NA | The new course curriculum will build upon the existing course structure and will continue to be interactive and engaging. The expanded course curriculum will also focus on influenza and other zoonotic disease prevention, but it will be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons. Creating a course for this target audience will enable us to broaden the reach of these important educational materials to all ages.
4. Complete enhanced evaluation of educational materials | CFSPH developed an enhanced evaluation component, including a learning management system, pretest, and posttest. CFSPH ordered supplies for enhanced evaluation incentives, “biosecurity buckets,” and workshops. Biosecurity buckets included items such as a scrub brush, soap, gloves, boot covers, hand wipes, a Pork Checkoff "Passport" to track animal movement, and other educational materials. All participants in 4-H Animal Science Roundup and 4-H Youth Conference workshops were required to complete the pretest, Excellence in Exhibition course, and posttest evaluations. All received a “biosecurity bucket” incentive and were entered into a drawing for a $25 gift card. CFSPH and Iowa 4-H partners began advertising train-the-trainer sessions and recruiting volunteers. | Delivered Excellence in Exhibition course, pretest, and posttest (online) | NA | NA | Iowa high school aged 4-H youth participating in Animal Science Roundup or Iowa 4-H Conference | 96 | Biosecurity buckets - 160 Local feed store gift cards ($25 each) - 8 | Iowa high school aged 4-H youth participating in Animal Science Roundup or Iowa 4-H Conference - 96 | Iowa high school aged 4-H youth participating in Animal Science Roundup or Iowa 4-H Conference - 96 | CDC and CSTE evaluation experts assisted in developing the enhanced evaluation. Additional evaluation questions were added from the question bank from other states. The National Pork Board supplied animal movement "passports" and educational material.