Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. The Center for Food Security and Public Health (CFSPH) finalized updates, including improved 508 compliance, to the currently available Excellence in Exhibition course for middle–high school youth developed during the 2016–2017 funding cycle (www.BlueNotFlu.org); the course achieved official Iowa and National 4-H peer reviewed status.
b. The CFSPH hosted workshops, seminars, and table top exhibits at the Iowa FFA State Leadership Conference, Iowa 4-H Youth Conference, Iowa 4-H Animal Science Roundup, and Iowa Association of Agriculture Educators annual meeting during this quarter.
c. The CFSPH developed an enhanced evaluation competent, including a learning management system, pretest, and posttest, and delivered the evaluation and course to 96 youth. 

2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
a. National 4-H – Peer review of currently available course
b. Iowa 4-H – Partnered to host Iowa 4-H Youth Conference and Animal Science Roundup workshops and deliver online Excellence in Exhibition course
c. Iowa Department of Public Health – Delivered a presentation at the annual CSTE conference
d. National Pork Board – placed link to Excellence in Exhibition course on NPB website and supplied material for biosecurity buckets and Animal Science Roundup swine workshops
e. Ohio – Used course at World Pork Expo exhibit table
f. North Dakota – Used course as training for 4-H skillathon

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

We are experiencing challenges in identifying adult volunteers to participate in the in-person train-the-trainer workshops for the enhanced evaluation. This is likely due to full schedules during summer fair season. 
4. Please include an updated project timeline.

	May 1–Oct 31, 2017
	· Enhance existing course
· CFSPH continued to research how to incorporate the course into state and national 4-H curriculum through state and national 4-H development standards and peer review.
· CFSPH continued to make course edits as appropriate to maintain content accuracy and timeliness. 
· As a collaborating center with the OIE, CFSPH explored placing the OIE logo on the course.
· CFSPH modified the Google Analytics tracking of the course to better capture course use.
· Promote and increase existing course distribution and implementation
· CFSPH continued to distribute materials at events listed in the project proposal.
· CFSPH presented a seminar during the 2017 American Association of Extension Veterinarians’ annual meeting (held during the United States Animal Health Association meeting) and distributed promotional materials.
· CFSPH hosted an exhibit table at the National FFA Convention. CFSPH also provided printed material for youth, educators, and others at the National FFA Convention.
· CFSPH registered, researched, and began making travel arrangements to host an exhibit table and interactive teacher/student workshop at the International Association of Fairs and Expositions Annual Convention.
· CFSPH registered, researched, and began making travel arrangements to host an exhibit table at the National Association of Agriculture Educators conference.  
· Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course
· CFSPH continued to develop the outline, researched content, and researched best practices in online course development for the new course.

	Nov 1, 2017–Feb 28, 2018
	· Enhance existing course
· CFSPH consulted with CDC to revise the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH worked with CDC and CSTE to participate in any evaluation framework to assess implementation of the project on a national level.
· CFSPH submitted the current course for state and national 4-H review. The course was approved as official Iowa 4-H curriculum in January 2018.
· Promote and increase existing course distribution and implementation
· CFSPH and collaborating agencies pursued additional opportunities to engage participation among Iowa youth through exhibits, formal presentations, and/or demonstrations/workshops.
· CFSPH and IDPH submitted an abstract to the Council of State and Territorial Epidemiologists Annual Conference (2018).
· At all venues, CFSPH displayed interactive elements of the course on laptops and tablets, distributed informational flyers, handouts, stickers, and other material developed by CFSPH advertising the free course, and distributed zoonotic disease resources developed by CFSPH, other states, and CDC.
· Develop new course for younger audiences based on existing course
· CFSPH identified a DVM/MPH student intern to help with course development. 
· CFSPH expanded course curriculum to build upon the current course structure and be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons.
· CFSPH finalized an outline for the new course.

	March 1–June 30, 2018
	· Enhance existing course
· CFSPH finalized review of content and updates, including improved compliance of Section 508 of the Rehabilitation Act, ensuring accessibility for all learners and allowing distribution through federal partners, to the currently available Excellence in Exhibition course for middle–high school youth. 
· CFSPH created certificate badges to be "earned" by completing lessons and the evaluation. 
· CFSPH received official Iowa and National 4-H peer reviewed status for the available course. 
· Promote and increase existing course distribution and implementation
· CFSPH worked with the National Pork Board to add a link to the course on the Pork Checkoff website. https://lms.pork.org/Tools/View/show-pigs 
· CFSPH attended North Dakota's "Healthy Fairs" meeting and workshop to present information about the Excellence in Exhibition course and experiences. 
· CFSPH and the Iowa Department of Public Health presented an abstract at the CSTE annual convention.
· CFSPH attended the World Pork Expo to distribute printed materials, promote the course, review the Ohio State University’s interactive booth, and seek donations for the enhanced evaluation incentives for youth (June 6–7, 2018).
· CFSPH hosted the following workshops, seminars, and exhibit tables:
· FFA State Leadership Convention exhibit table – April 23–24, 2018, with 5,000 attendees. 
· Eastern Iowa 4-H Food Safety Quality Assurance workshops – April 11, 2018. Four workshops with 115 youth. 
· Iowa 4-H Youth Conference workshops (2018) – Three workshops with 70 youth and six adult volunteers.
· Iowa 4-H Animal Science Roundup opening session (2018)— Three interactive seminars to 89 youth and 10 adult volunteers. 
· Iowa 4-H Animal Science Roundup swine session workshop (2018) – One interactive workshop to 15 youth and two adult volunteers.
· Iowa Association of Agriculture Educators (IAAE) annual meeting exhibit table and workshop – June 26–27, 2018, with approximately 120 attendees (table) and 3 attendees (workshop). 
· At all exhibit table venues, CFSPH displayed interactive elements of the course on laptops and tablets, distributed informational flyers, handouts, stickers, and other material developed by CFSPH advertising the free course, and distributed zoonotic disease resources developed by CFSPH, other states, and CDC.
· Develop new course for younger audiences based on existing course
· CFSPH continued to write content, design graphics, and develop the course. 
· Complete enhanced evaluation of educational materials
· CFSPH developed an enhanced evaluation component, including a learning management system, pretest, and posttest. 
· CFSPH ordered supplies for enhanced evaluation incentives, “biosecurity buckets,” and workshops. Biosecurity buckets included items such as a scrub brush, soap, gloves, boot covers, hand wipes, a Pork Checkoff "Passport" to track animal movement, and other educational materials. 
· All participants in 4-H Animal Science Roundup and 4-H Youth Conference workshops were required to complete the pretest, Excellence in Exhibition course, and posttest evaluations. All received a “biosecurity bucket” incentive and were entered into a drawing for a $25 gift card. 
· CFSPH and Iowa 4-H partners began advertising train-the-trainer sessions and recruiting volunteers.

	July 1–Oct 31, 2018
	· Enhance existing course
· CFSPH will revise the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH will work with CDC and CSTE to participate in any evaluation framework to assess implementation of the project on a national level.
· CFSPH will post the updated course during July.
· Promote and increase existing course distribution and implementation
· Develop new course for younger audiences based on existing course
· CFSPH will continue course development and send to collaborating agencies and partners for review. 
· CFSPH will finalize and post the live.
· CFSPH will advertise the new course top appropriate audiences once released. 
· [bookmark: _GoBack]CFSPH will develop an evaluation component comparable to the existing course and consistent with any guidelines outlined by CDC and CSTE. 
· Complete enhanced evaluation of educational materials
· CFSPH will continue to work with Iowa 4-H partners to advertise train-the-trainer sessions and recruit volunteers.
· CFSPH will schedule and host train-the-trainer sessions to describe how to use the PPT presentations, demonstrate hands-on activities, and provide additional information to volunteers.
· CFSPH will distribute incentives to adult volunteers and youth. 
· CFSPH will collect data from the pre and posttests and share with project partners.  




5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 

All materials are posted to the Basecamp site. 

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.

Continued assistance in promoting the course at the national level would be valuable. 

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.


OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions , either describe it here or just write ‘YES’ and we will follow up with you via phone or at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 

YES

