2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Progress Report
Site: __Ohio__________________________
Completed by: _Jacqueline Nolting_______
Date: _October 28, 2021________________


Please return completed progress report to CSTE at mhuynh@cste.org by October 29, 2021.
Note: Please submit one response per site.

1. Provide a brief update (2-3 sentences) on progress made towards each deliverable between August 1 – October 31, 2021. 
A. Host “Becoming a Swientist” programming with OH-pigs Ohio Summer Swine Circuit. 
The OH-pigs Summer Swine Circuit awards banquet was held in August 2021. During the awards banquet we awarded prizes for the biosecurity poster contest hosted by the Swientist program, did a short lesson on the importance of biosecurity, and distributed Intervention disinfectant to all circuit participants to aide in biosecurity on their home farms. 
We have also had informal interviews with the show organizer and some families who participate heavily in Swientist activities to evaluate the existing program and develop plans for future direction.

B. Collaborate with the National Junior Swine Association to engage national level swine jackpot show participants at various shows across the country.
Swientist training activities were held at the National Barrow Show in Austin, MN with content focused on immunology. Materials were sent to Eastern Regional NJSA show to be disseminated to participants in registration bags and plans are underway for in-person activities at the North American International Livestock Exhibition held in November. 
[bookmark: _GoBack] In addition, we met with NJSA show organizers to evaluate the existing program and develop plans for future direction.
C. Partner with the Ohio FFA Association to develop and disseminate zoonotic disease risk and prevention curriculum in accordance with Ohio Department of Education standards for middle school agricultural education students. 
High school level curriculum is ready to disseminate as soon as videographer collaborators have the last video completed. Content is being developed for the middle school level curriculum and will be completed by contract end. Since many of the activities included in the curriculum contain optional hands-on activities, supply kits were assembled and are available to be requested by educators to use in their classrooms. The AIEERP website is being revised to include a landing page for all curriculum materials developed by our research group to be downloaded by educators. 

D. Collaborate with the American Association of Swine Veterinarians to build awareness for swine health careers in youth who show swine at a state and national level. 
Several studies show that for youth to pursue STEM careers, they must be exposed to career opportunities before they are 12 years old. To that end, a swine careers coloring booking is being created to use alongside Swientist, NJSA, AASV, and Team Purebred activities that is focused on the multitude of careers in the swine industry. 
E. Collaborate with Team Purebred to engage national level swine jackpot show participants at various shows across the country 
No activity was completed for this objective during the reporting period.
F. Host Becoming a Swientist events to youth involved in jackpot shows with multiple species in Pennsylvania. 
Our collaborator with PennAg made a career change, and the new project director has faced challenges brought about by the workload transition. It was not possible to host a training session in October as planned, however plans are underway for a training session at a Pennsylvania swine show in December.

2. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
We don’t anticipate any challenges to completing deliverables.

3. As we are nearing the end of the project period, please indicate whether or not you would like to request a project extension and through what end date. To note, CSTE is able to extend the project to July 31, 2022.
We would like to extend our end date to March 31, 2022 to attend winter pig shows. A couple Autumn shows we planned to attend had low registration numbers and travel costs were high enough the return on investment was not reasonable. The winter shows are well attended, and we will be able to reach hundreds more youth than at the autumn shows. 

4. Given the virtual workshop in October, individual site calls planned for October/November are optional. If you would like to have a quick check-in call with CSTE and CDC to discuss project updates or questions, please indicate below your project coordination team’s availability for the month of November.
We are happy to have a call if there are specific questions from CSTE/CDC, otherwise we will forgo the check-in call. 

5. Please describe the personnel involved and the number of hours spent by each to perform the deliverables between August 1 – October 31, 2021. Note: If there are not enough rows to accommodate all personnel, please feel free to add more rows.

	 Detail of assistance provided between August 1 – October 31, 2021

	Personnel (First & Last Name)
	Position Title
	Project-Specific Activities Performed
	Quantity/ Hours 

	Jacqueline Nolting
	Laboratory Operations Manager
	Coordinated all activities with collaborators, developed curriculum,  hosted IL and OH state fair workshops, attended OH-Pigs banquet, hosted booth at Farm Science Review
	117 hours

	Heather Nicholson
	Research Associate-2
	Developed curriculum,  hosted IL and OH state fair workshops, held workshop at National Barrow Show, hosted booth at Farm Science Review
	65 hours

	Andrew Bowman
	Associate Professor
	Subject matter expert, hosted IL and OH state fair workshops, attended OH-Pigs banquet
	24 hours

	Avy Pollock
	Student Research Assistant
	Assisted with lesson preparation, attend national pig show and Farm Science Review to assist with Swientist activities
	139 hours

	Kailie Plotnik
	Student Research Assistant
	Assisted with lesson preparation and attended Farm Science Review to assist with Swientist activities
	35 hours

	Estimated Total Hours
	380 hours





