

2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Progress Report
Site: __Michigan______________________________
Completed by: _Erica Tobe and Kim Signs______________________
Date: _10/28/2021______________________________


Please return completed progress report to CSTE at mhuynh@cste.org by October 29, 2021.
Note: Please submit one response per site.

1. Provide a brief update (2-3 sentences) on progress made towards each deliverable between August 1 – October 31, 2021. 

Deliverable 1: Monthly Leadership Team meetings 
Actively meeting monthly among the grant team. 
Deliverable 2: Pop Up/One Day Show Zoonotic Disease Education
Actively working on the development of 3 – 90 second videos. The script has been drafted by MSUE staff and is getting reviewed by MDHHS colleagues. Met with the video production company and dates set for taping in mid-November. Three video focuses will include: Cleaning and Disinfecting Livestock and Horse Trailers Video; Identifying Sick Animals Video; and Preparing for a Show or Exhibition. 
Social media biosecurity graphics previously developed have been posted on MSUE animal health website and posted on Basecamp for other state’s usage. The site is: https://www.canr.msu.edu/animal_science/zoonotic-disease 
Deliverable 3: Host a multi-state webinar for Extension staff in states not funded for CSTE YIA programs
A multi-state webinar date has been set for December 1, 2021 at 1 pm. Currently in progress with identifying the agenda and setting up the session/event registration. Focus will be on information sharing specifically with a focus on states that have not been funded with CSTE funds.  Information to be sent out soon to interested parties. 
Deliverable 4: Develop Resources for Agritourism Businesses to employ best practices to protect human health
Drafted and submitted a survey to MSU IRB office with a target to garner feedback from agritourism businesses who have animals on their property to address zoonotic disease education and assess their interest in receiving materials to support promotion of good and safe practices. Survey has been approved and initially disseminated to approximately 250 businesses some of whom have animals on property. The survey is currently open and already garnering good feedback and interest. 

2. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

MSUE staff member is presently on leave. Other MSUE colleagues have stepped in to support the grant and all project deliverables are moving forward. 
3. As we are nearing the end of the project period, please indicate whether or not you would like to request a project extension and through what end date. To note, CSTE is able to extend the project to July 31, 2022.
At this point, no request for a project extension is being made.
4. Given the virtual workshop in October, individual site calls planned for October/November are optional. If you would like to have a quick check-in call with CSTE and CDC to discuss project updates or questions, please indicate below your project coordination team’s availability for the month of November.

We don’t feel the need for a check-in call but would gladly participate in one if CSTE requested it.
5. Please describe the personnel involved and the number of hours spent by each to perform the deliverables between August 1 – October 31, 2021. Note: If there are not enough rows to accommodate all personnel, please feel free to add more rows.

	 Detail of assistance provided between August 1 – October 31, 2021

	Personnel (First & Last Name)
	Position Title
	Project-Specific Activities Performed
	Quantity/ Hours 

	Nick Babcock
	Extension Educator
	Leading grant initiatives August -Mid September
	30 hours

	Erica Tobe
	Director, Children and Youth Institute
	Leading grant initiatives mid-September – October; attended CSTE meeting; meeting with grant team; supporting financial/contract grant needs; meeting with MDHHS colleagues; supported the IRB application process
	30 hours

	Beth Ferry
	Extension Educator
	Supporting grant initiatives; wrote script for videos; edited article; worked with events management to begin event planning; met with project team to plan deliverable completion; edited and provided feedback on survey
	30 hours

	Dave Thompson
	Extension Educator
	Supporting grant initiatives; wrote/edited script for videos; edited article; met with project team to plan deliverable completion; edited and provided feedback on survey
	16 hours

	Will Cronin
	Extension Educator
	Supporting grant initiatives; drafted survey; connecting with MI AgriTourism Industry to get access to contacts, submitted IRB application; drafted article to promote survey
	30 hours

	Kim Signs
	Epidemiologist
	Review materials developed by MSUE, grant management and paperwork
	20 hours

	
	

	Estimated Total Hours
	156








