2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Progress Report
Site: ______Maryland__________________________
Completed by: ____C. Anderson and D. Crum___________________
Date: ______10/27/2021_________________________


Please return completed progress report to CSTE at mhuynh@cste.org by October 29, 2021.
Note: Please submit one response per site.

1. Provide a brief update (2-3 sentences) on progress made towards each deliverable between August 1 – October 31, 2021. 

· Deliverable 1: Online training for 4-H and FFA students on novel influenza and other zoonotic diseases using a One Health approach - We utilized the existing Maryland and West Virginia 4-H Animal Husbandry and Quality Assurance (AH&QA) online training as a platform for delivering novel influenza and other zoonotic disease subject matter content in a One Health framework to 4-H and FFA students in Maryland and West Virginia. The system opened 4/15/21 and closed 8/10/21.  3,253 youth (904 junior and 2,253 intermediate / senior aged youth) registered and completed the online training in 2021.
 
· Deliverable 2: Healthy Animals | Healthy YOUth Activity Kits - Train-the-Trainer Training and NEW Teen Ambassadors program – Activity Kit Lessons were used at the Frederick County 4-H Showcase held October 10-13, 2021.

· Deliverable 3: NEW Healthy Animals | Healthy YOUth Interactive Displays  -  Interactive displays about zoonotic disease awareness and prevention topics have been created for use at County and State Fairs targeting Fair Livestock Exhibitors, and Fair-going General Public. The displays were launched at the West Virginia State Fair held August 12-21, 2021 and the Maryland State Fair held August 26-September 6, 2021. The displays were used at two county 4-H fairs (St Mary’s and Frederick) during September.

· Deliverable 4: Production of permanent signage to encourage zoonotic disease prevention at Maryland and West Virginia agricultural fairs. - A set of 7 different hand washing signs were produced and provided to each county and state fair across Maryland and West Virginia. The signs were posted in livestock barns and public areas to encourage hand washing by exhibitors and the public after interacting with animal exhibits. The signs were used at the West Virginia State Fair held August 12-21, 2021 and the Maryland State Fair held August 26-September 6, 2021. The signs were used at three county 4-H fairs (Anne Arundel, Charles, and St Mary’s) during September.

· Deliverable 5: 2021 “Stay Healthy at (Maryland) Fairs” Symposium - The 2021 “Stay Healthy at Maryland Fairs” Symposium will be offered by the Maryland Department of Health and University of Maryland Extension 4-H Youth Development. This symposium is designed to engage Maryland’s agricultural community, fair organizers, Extension/4-H and FFA, and state and local health department staff in discussions about strategies for minimizing health risks associated with animal contact in public settings. We had hoped to hold the event on November 4th, 2021 but the event is being postponed until Spring 2022 due to continued restrictions associated with COVID-19.

2. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

The changing dynamics of the pandemic and return to some restrictions for holding in-person programs has led to the need to reschedule the Fairs symposium planned for Fall 2021 to Spring 2022.

3. As we are nearing the end of the project period, please indicate whether or not you would like to request a project extension and through what end date. To note, CSTE is able to extend the project to July 31, 2022.

Yes, we have already requested a project extension.

4. Given the virtual workshop in October, individual site calls planned for October/November are optional. If you would like to have a quick check-in call with CSTE and CDC to discuss project updates or questions, please indicate below your project coordination team’s availability for the month of November.

We were able to receive valuable information, suggestions, and answers to questions during the virtual workshop. An individual site call is not needed this November.

5. Please describe the personnel involved and the number of hours spent by each to perform the deliverables between August 1 – October 31, 2021. Note: If there are not enough rows to accommodate all personnel, please feel free to add more rows.

	 Detail of assistance provided between August 1 – October 31, 2021

	Personnel (First & Last Name)
	Position Title
	Project-Specific Activities Performed
	Quantity/ Hours 

	David Crum, DVM
	State Public Health Veterinarian
	Project lead. Human and Animal Health expertise
	

	Chris Anderson
	 4-H Youth Development Specialist, UME
	Project co-lead. Coordinates work team for creation of deliverables
	 60 hrs.

	Carrie Wivell
	 4-H Program Coordinator, UME
	Coordinates logistics. Serves as curriculum writer under the direction of PI and key personnel.
	 100 hrs.

	Lacie Ashby

	 4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	8 hrs.

	Donielle Axline
	Principal Agent Assoc., 4-H Youth Develop., UME
	Contributes to content development and project training and distribution
	16 hrs.

	April Barczewski

	4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	10 hrs.

	Sheryl Bennett

	4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	8 hrs.

	Ashley Travis

	4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	[bookmark: _GoBack]12 hrs.

	Sarah Owen

	4-H Youth Ag Program Coordinator, WVU Extension Service
	Contributes to content development and project training and distribution
	20 hrs.

	Sheldon Owen
	Extension Wildlife Specialist, WVU Extension Service
	Contributes to content development and project training and distribution
	10 hrs.

	Michael Odian, DVM 
of Health
	State Animal Health Veterinarian
	Animal Health expertise
	

	Total Flu
	 
	 
	 



