2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Progress Report
Site: _Iowa_________________________
Completed by: _Molly Lee, CFSPH______
Date: _10-27-21_____________________


Please return completed progress report to CSTE at mhuynh@cste.org by October 29, 2021.
Note: Please submit one response per site.

1. Provide a brief update (2-3 sentences) on progress made towards each deliverable between August 1 – October 31, 2021. 

Spanish versions of the “Bring Home the Blue, Not the Flu!” content, including both courses (elementary and middle/high school versions) supplemental resources, and a Spanish version of the BlueNotFlu.org website have been developed. Resources have been adapted to Google Classroom and Seesaw for ease in K-12 learning. Courses and supplemental material developed during previous funding cycles have been maintained and outreach has been conducted to youth and adults in Iowa using the courses, supplemental materials, and hands-on activities previously developed. 

2. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

Personnel changes and inconsistent communications within partner entities (University of Nebraska, Reno (UNR)) have delayed completion of outreach to adults and youth in Nevada. Work will proceed in organizing web-based train-the-trainer sessions so that all materials will be immediately available upon selection of event dates by UNR. These challenges could also be mitigated by recording a train-the-trainer session to be offered when convenient for our partners at UNR. 

3. As we are nearing the end of the project period, please indicate whether or not you would like to request a project extension and through what end date. To note, CSTE is able to extend the project to July 31, 2022.

We would like to further discuss this with CSTE to determine how to proceed as far as modifying deliverables vs. requesting a project extension. 

4. Given the virtual workshop in October, individual site calls planned for October/November are optional. If you would like to have a quick check-in call with CSTE and CDC to discuss project updates or questions, please indicate below your project coordination team’s availability for the month of November.

Available mornings (8-12 Central): 11/8, 11/9, 11/12 (8-11am), 11/16, 11/17, 11/23, 11/30
Available afternoons (1-5 Central): 11/8, 11/12, 11/15, 11/17, 11/29

5. Please describe the personnel involved and the number of hours spent by each to perform the deliverables between August 1 – October 31, 2021. Note: If there are not enough rows to accommodate all personnel, please feel free to add more rows.


	 Detail of assistance provided between August 1 – October 31, 2021

	Personnel (First & Last Name)
	Position Title
	Project-Specific Activities Performed
	Quantity/ Hours 

	Molly Lee
	Public Health Veterinarian
	Project management
	40 hours 

	Victoria Lenardon
	Public Health Veterinarian
	Translation 
	70 hours

	Laura Lenardon
	P&S Temporary
	Translation editing
	70 hours

	Andrew Kingsbury
	Graphic Design Team
	Development and maintenance of graphics for the project
	34 hours

	Vered Friedberg
	IT Team
	Development and maintenance of web-based project activities
	38 hours

	Varies
	Student hourly assistance
	Assist project manager
	640 hours

	Estimated Total Hours
	892 hours
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