Please return completed progress report to CSTE at mhuynh@cste.org by October 29, 2021.

Note: Please submit one response per site.

- Provide a brief update (2-3 sentences) on progress made towards each deliverable between August 1 – October 31, 2021.

Spanish versions of the “Bring Home the Blue, Not the Flu!” content, including both courses (elementary and middle/high school versions) supplemental resources, and a Spanish version of the BlueNotFlu.org website have been developed. Resources have been adapted to Google Classroom and Seesaw for ease in K-12 learning. Courses and supplemental material developed during previous funding cycles have been maintained and outreach has been conducted to youth and adults in Iowa using the courses, supplemental materials, and hands-on activities previously developed.

- Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

Personnel changes and inconsistent communications within partner entities (University of Nebraska, Reno (UNR)) have delayed completion of outreach to adults and youth in Nevada. Work will proceed in organizing web-based train-the-trainer sessions so that all materials will be immediately available upon selection of event dates by UNR. These challenges could also be mitigated by recording a train-the-trainer session to be offered when convenient for our partners at UNR.

- As we are nearing the end of the project period, please indicate whether or not you would like to request a project extension and through what end date. To note, CSTE is able to extend the project to July 31, 2022.

We would like to further discuss this with CSTE to determine how to proceed as far as modifying deliverables vs. requesting a project extension.

- Given the virtual workshop in October, individual site calls planned for October/November are optional. If you would like to have a quick check-in call with CSTE and CDC to discuss project updates or questions, please indicate below your project coordination team’s availability for the month of November.

Available mornings (8-12 Central): 11/8, 11/9, 11/12 (8-11am), 11/16, 11/17, 11/23, 11/30

Available afternoons (1-5 Central): 11/8, 11/12, 11/15, 11/17, 11/29

- Please describe the personnel involved and the number of hours spent by each to perform the deliverables between August 1 – October 31, 2021. Note: If there are not enough rows to accommodate all personnel, please feel free to add more rows.

| Detail of assistance provided between August 1 – October 31, 2021 |  |  |  |
| --- | --- | --- | --- |
| Personnel (First & Last Name) | Position Title | Project-Specific Activities Performed | Quantity/ Hours |
| Molly Lee | Public Health Veterinarian | Project management | 40 hours |
| Victoria Lenardon | Public Health Veterinarian | Translation | 70 hours |
| Laura Lenardon | P&S Temporary | Translation editing | 70 hours |
| Andrew Kingsbury | Graphic Design Team | Development and maintenance of graphics for the project | 34 hours |
| Vered Friedberg | IT Team | Development and maintenance of web-based project activities | 38 hours |
| Varies | Student hourly assistance | Assist project manager | 640 hours |
| Estimated Total Hours |  |  | 892 hours |