2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Interim Progress Report
Site: _Iowa___________________________
Completed by: _Molly Lee_______________
Date: _21 December 2021____________________

Please return completed Interim Progress Report to mpuckett@cste.org by December 30, 2021.
Note: Please submit one response per site.

1) List project deliverables and describe progress made towards completion of these deliverables:  
*Note: Deliverables are numbered according to the order in which they appear in the Iowa 2021 application (e.g., Tier 1, Phase 1, first deliverable listed is “Deliverable 1.” In some cases where it makes sense, deliverables are combined for reporting purposes; this is clearly indicated.

· Deliverable 1: 
· Develop Spanish versions of the "Bring Home the Blue, Not the Flu!" content and courses (complete)
Accomplishments/Progress to-date:
· Elementary and middle/high school course content, including the interactive courses, supplemental resources for students, workshop materials, and resources for educators have been translated to Spanish and reviewed/edited for accuracy, consistency, and clarity of the translated content.
· Courses have been updated to portray diversity and a welcoming culture/environment for all youth passionate about agriculture
· Supportive and explanatory website content has been translated into Spanish
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.) 
· N/A (release of the website is pending final edits as clarified below; tracking will not occur until after release in Q1 of 2022)

· Deliverable 2: Maintain the courses and supplemental material developed during previous funding cycles and Deliverable 5: establish procedures for sustainability of the existing courses with minimal input (complete)
Accomplishments/Progress to-date:
· Track visits to the course webpage and courses
· Ensure proper functionality of the course webpage and courses 
· Answer requests for help/information
· Offer support to adult educators and educational organizations to facilitate use of the courses in youth outreach and education
· Establish procedures for hosting, maintenance, and updates for a 5- year period 
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 3: Create, finalize and release a responsive and visually appealing Spanish version of the BlueNotFlu.org website (partially complete)
Accomplishments/Progress to-date:
· The web server, database, and visual theme for the site has been developed
· Privacy and site use policies have been developed, accessibility standards have been achieved, and a technical and user support team have been established
· Systems for tracking and reporting site activity are in place
· The website has been populated with supportive and explanatory website content
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)
· N/A (release of the website is pending final edits as clarified below; tracking will not occur until after release in Q1 of 2022)

· Deliverable 6: Modify and adapt "Bring Home the Blue, Not the Flu!" resources to share content with teachers directly via free, ready-to-use Google Classroom and Seesaw "lessons" for ease of use in K-12 learning and Deliverable 7: add resources to the BlueNotFlu.org website (complete)
Accomplishments/Progress to-date: 
· Google Classroom and Seesaw activities, notes, and supplemental resources for multiple grade levels have been created
· Instructional guides for teachers utilizing Seesaw and Google Classroom have been created
· Procedures for the future use of Seesaw and Google Classroom have been established
· Seesaw and Google Classroom lessons have been added to the BlueNotFlu.org website.
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)
· N/A (promotion of available resources is pending final edits to website on which they will be made available as clarified below; tracking will not occur until after release in Q1 of 2022)

· Deliverable 8: Promote Google Classroom and Seesaw lessons to educators within Iowa and across the U.S. (partially complete) 
Accomplishments/Progress to-date:
· A press release has been drafted to highlight the availability of these resources 
· Repositories with which the “Bring Home the Blue, Not the Flu!” curriculum has been integrated have been updated
· Content has been added to the Teachers Pay Teachers website as a free resource
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)
· N/A (promotion of available resources is pending final edits to website on which they will be made available as clarified below; tracking will not occur until after release in Q1 of 2022)

· Deliverable 9: Conduct outreach to youth and adults in Iowa by using the “Bring Home the Blue, Not the Flu!” courses, supplemental materials, and hands-on activities developed by the CFSPH, other states, and CDC during previous four fiscal years (complete)
Accomplishments/Progress to-date: 
· Present an interactive, in-person workshop at the Iowa FFA Association Leadership Conference to youth
· Present an interactive, in-person workshop at the 4-H State Conference to youth
· Present an interactive, virtual workshop at the World Food Prize Iowa Youth Institute to youth
· Host a train-the-trainer workshop for adults and youth in 4-H leadership positions at the Worth County Fair (youth Community Action Plan [CAP] project); participate in interactive, in-person workshop at the Worth County Fair
· Host an interactive, in-person workshop for youth in Franklin County
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 10: Conduct outreach to youth and adults in Nevada by introducing the “Bring Home the Blue, Not the Flu!” courses, supplemental materials, and hands-on activities developed by the CFSPH, other states, and CDC during previous four fiscal years through web-based train-the-trainer sessions (partially complete)
Accomplishments/Progress to-date:
· A web-based train-the-trainer session was organized, hosted, and facilitated to provide outreach to adults in Nevada using the courses, supplemental materials, and hands-on activities previously developed.
· Access to all content was provided to webinar attendees.
· All webinar attendees are prepared to host their own training session for additional youth educators AND youth within their impact areas
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

2) As relevant, describe areas of concern or challenges in meeting the objectives or providing deliverables especially as it relates to COVID-19.
· Some proposed workshops that were a part of the planned outreach to youth and adults in Iowa were unable to be held due to modified schedules or increased demand for workshops due to the outreach events being cancelled the year prior (e.g., Iowa Association of Agricultural Educators Conference, Iowa FFA Association Immersion Activity, and Iowa FFA Association Precision Ag Days). However, we feel that the lack of our presence at these events was adequately balanced with unexpected opportunities to engage with additional audiences (e.g., train-the-trainer and workshop at Worth County Fair, presentation by 4-H collaborator at National Ag in the Classroom conference and sharing info with local ag teachers), and the trickle-down effect of the adult educators who we engaged with that we are aware are conducting this outreach on their own.

3) Please provide an update on your evaluation goals and timeline.
· Deliverable 3: Create, finalize and release a responsive and visually appealing Spanish version of the BlueNotFlu.org website
· Once “behind-the-scenes” course design issues are resolved in the first quarter of 2022, the courses will be uploaded to the website and the site will be finalized and released.
· Deliverable 4: Promote the Spanish website to users within Iowa and across the U.S.
· Once “behind-the-scenes” course design issues are resolved in the first quarter of 2022, the draft press release written in preparation for release of materials will be updated and CFSPH will partner with UNR and collaborating organizations to circulate information about the site to state and national partners including the target audience.
· Deliverable 8: Promote Google Classroom and Seesaw lessons to educators within Iowa and across the U.S.
· Once “behind-the-scenes” course design issues are resolved in the first quarter of 2022, the draft press release written in preparation for release of materials will be updated and CFSPH will partner with UNR and collaborating organizations to circulate information about the site to state and national partners including the target audience.
· Deliverable 10: Conduct outreach to youth and adults in Nevada by introducing the “Bring Home the Blue, Not the Flu!” courses, supplemental materials, and hands-on activities developed by the CFSPH, other states, and CDC during previous four fiscal years through web-based train-the-trainer sessions
· The train-the-trainer session was recorded and will be edited slightly before posting on the CFSPH’s YouTube channel to facilitate Nevada 4-H leadership sharing the training session with additional 4-H and other youth educators. Sharing the recorded session will take place in the first quarter of 2022.
· Deliverable 11: Conduct outreach to youth in Nevada by using the “Bring Home the Blue, Not the Flu!” courses, supplemental materials, and hands-on activities developed by the CFSPH, other states, and CDC during previous four fiscal years
· Difficulties in connecting with partner entity (University of Nebraska, Reno (UNR)) have been resolved, but these resulted in delays to the project. The train-the-trainer was able to be held in mid-December but adult educators will not have had the opportunity to conduct youth outreach (thus prohibiting our ability to support/collect information about their youth outreach) before the end of the calendar year. We do not anticipate further challenges with this aspect of the project moving forward and expect objectives to be met in the first quarter of 2022.

4) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424). For Basecamp access, please email mpuckett@cste.org. 

5) Do you anticipate reapplying for this opportunity for the 2022 project period? If so, what suggestions would you like to share for consideration by CSTE and CDC?

Yes, we anticipate reapplying. It will be helpful to see the new all-site resource repository to facilitate exposure to other site’s projects and be able to build off of successes implemented in other states and/or avoid duplicative efforts. Additionally, CDC and CSTE priorities or areas of concern related to youth influenza and zoonotic disease education would help guide our proposed educational interventions to be of most utility. An additional consideration would be creation of a listserv to facilitate sharing resources and/or asking questions for sites currently and previously involved in the Influenza Education Among Youth in Agriculture project. 




Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline # prior to current grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2021 Audience (youth, community leaders, etc?)
	# of attendees/
participants
	# of materials distributed
	Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2021 to X total youth aged 11-15
	Only counted the number of actual youths who attended the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	“Bring Home the Blue, Not the Flu!” online course (https://bluenotflu.org/) 
	2020 Values:

Total visitors to the website: 1,731

Unique visitors to the website: 1,451

Took the middle/high school course: 360

Took the elementary course: 155

Logins to the password-protected instructor version of the website: 70
	Unique visitors
	Anyone with internet access
	Values from January 1, 2021 through December 21, 2021: 

Total visitors to the website: 3,325

Unique visitors to the website: 2,668

Took the middle/high school course: 1002

Took the elementary course: 686

Logins to the password-protected instructor version of the website: 43
	N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete; NE has unique online form from 2019 collaboration
	Yes; 113 (incl. 9 from NE); optional for individuals who completed online course 
	Yes; 113 (incl. 9 from NE); optional for individuals who completed online course


	Course availability on the National Agriculture Literacy Curriculum Matrix:  https://agclassroom.org/matrix/search_result/?search=bluenotflu 
	None
	N/A
	Anyone with internet access; primary users are Ag Ed teachers
	Values from January 1, 2021 through December 16, 2021:

Bring Home the Blue, Not the Flu (Grades 3-5): 
330 pageviews

Bring Home the Blue, Not the Flu (Grades 6-8): 
592 pageviews

Bring Home the Blue, Not the Flu (Grades 9-12): 
426 pageviews

Bring Home the Blue, Not the Flu online modules: 
98 pageviews
	N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete
	N/A
	N/A

	Course availability on the Iowa Agriculture Literacy Foundation Matrix: https://www.iowaagliteracy.org/Search?q=bring+home+the+blue+not+the+flu 
	None
	N/A
	Anyone with internet access; primary users are Ag Ed teachers in Iowa
	Values from February 1, 2021 through July 21, 2021 (note: updated numbers are pending but delayed due to staff turnover at IALF):

78 total pageviews:

Lesson 1 – 21 views
Lesson 2 – 19 views
Lesson 3 – 11 views
Lesson 4 – 11 views
Lesson 5 – 9 views
Lesson 6 – 7 views
	N/A (full access to all materials on website, including both online courses)
	Users nationwide could complete
	N/A
	N/A

	Activity-based, in-person workshops
	Previous activity-based workshops have impacted approximately 600 youth over previous funding cycles
	Only counted the number of individuals who attended the workshops
	Youth (ranged from young children to high school students) 4-H and FFA members and fair attendees
	250 attendees total
 
State FFA Workshop: 75 attendees

State 4-H Conference Workshop: 25 attendees

Worth County Fair- 4-H Community Action Project:
75 attendees

Franklin County Fair outreach: 
75 attendees
	 Branded stickers, “stress ball” animals, and informational handouts available to all attendees
	N/A
	N/A
	N/A

	Virtual or recorded workshops
	8 youth attendees participate in 2020 virtual Animal Cy-ience Academy
	We measured only the number of youth and adults that attended the session. 
	Youth participating in the WFP IYI and the WISE STEM conference
	World Food Prize Iowa Youth Institute Immersion: 20 attendees

Women in Science and Engineering ‘Go Further’ STEM session: How to be a Disease Detective ( https://www.youtube.com/watch?v=dUlaP4y_wOA): 7 views
	N/A (link shared to website which includes both courses and all materials)
	N/A
	N/A
	N/A


	National Agriculture in the Classroom conference
	None
	Direct participants
	Adult educators, primary ag teachers
	60
	N/A (link shared to website which includes both courses and all materials)
	Attendees were from all over the US
	N/A
	N/A

	Train-the-Trainer for 4-H director and area coordinators in Nevada
	N/A
	Direct participants
	4-H leadership
	6
	Full access to all materials on website, including both online courses
	Nevada
	N/A
	N/A






7

