2021 Influenza and Zoonoses Education among Youth in Agriculture Program
Invoice Report
Site: _______Maryland_________________________
Completed by: ____Chris Anderson and David Crum ___________________
Date: ________12/28/2021_______________________


Please return completed Final Progress Report to CSTE at mpuckett@cste.org by December 30, 2021.
Note: Please submit one response per site.

1. Provide a brief update (2-3 sentences) on progress made towards each deliverable between November 1 – December 31, 2021. 
a. Online training for 4-H and FFA students on novel influenza and other zoonotic diseases using a One Health approach. 3,253 youth completed the Online AH&QA Training program in 2021. Raw Pre and Post survey data is currently being analyzed. 
b. Healthy Animals | Healthy YOUth Activity Kits - Train-the-Trainer Training and NEW Teen Ambassadors program.  No updates for this time period.
c. NEW Healthy Animals | Healthy YOUth Interactive Displays. A promotional session about the displays was provided to Maryland 4-H faculty and staff during a statewide animal science program in-service. Attended by 35.
d. Production of permanent signage to encourage zoonotic disease prevention at Maryland and West Virginia agricultural fairs. No updates for this time period.
e. 2021 “Stay Healthy at (Maryland) Fairs” Symposium - The 2021 “Stay Healthy at Maryland Fairs” Symposium will be the first event of its kind being offered by the Maryland Department of Health and its partner academic institution, University of Maryland Extension 4-H Youth Development. We had planned to hold the event on November 4th, 2021 but the event has been postponed until Spring 2022 due to continued restrictions associated with COVID-19.

2. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

Plans to conduct the Stay Healthy at Maryland Fairs 2021 Symposium on November 4, 2021 as an in-person event were changed. The symposium has been rescheduled for Spring 2022.

3. Please describe the personnel involved and the number of hours spent by each to perform the deliverables between November 1 – October 31, 2021. Note: If there are not enough rows to accommodate all personnel, please feel free to add more rows.

	 Detail of assistance provided between November 1 – December 31, 2021

	Personnel (First & Last Name)
	Position Title
	Project-Specific Activities Performed
	Quantity/ Hours 

	David Crum, DVM
	State Public Health Veterinarian
	Project lead. Human and Animal Health expertise
	

	Chris Anderson
	 4-H Youth Development Specialist, UME
	Project co-lead. Coordinates work team for creation of deliverables
	 20 hrs.

	Carrie Wivell
	 4-H Program Coordinator, UME
	Coordinates logistics. Serves as curriculum writer under the direction of PI and key personnel.
	 40 hrs.

	Lacie Ashby

	 4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	2 hrs.

	Donielle Axline
	Principal Agent Assoc., 4-H Youth Develop., UME
	Contributes to content development and project training and distribution
	2 hrs.

	April Barczewski

	4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	2 hrs.

	Sheryl Bennett

	4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	8 hrs.

	Ashley Travis

	4-H Youth Development Educator, UME
	Contributes to content development and project training and distribution
	2 hrs.

	Sarah Owen

	4-H Youth Ag Program Coordinator, WVU Extension Service
	Contributes to content development and project training and distribution
	

	Sheldon Owen
	Extension Wildlife Specialist, WVU Extension Service
	Contributedsto content development and project training and distribution
	

	Michael Odian, DVM 
of Health
	State Animal Health Veterinarian
	Animal Health expertise
	

	Total Flu
	 
	 
	 



