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Please return completed Final Progress Report to CSTE at mpuckett@cste.org by December 30, 2021.
Note: Please submit one response per site.

1. Provide a brief update (2-3 sentences) on progress made towards each deliverable between November 1 – December 31, 2021. 
Host “Becoming a Swientist” programming with OH-pigs Ohio Summer Swine Circuit. 
Dates have been set for the 2022 show season and plans are underway for Swientist programming.

Collaborate with the National Junior Swine Association to engage national level swine jackpot show participants at various shows across the country.
Swientist training activities were held at the North American International Livestock Exposition in Louisville, KY with content focused on biosecurity. Materials were sent to Western Regional NJSA show to be disseminated to participants in registration bags and plans are underway for in-person activities at the Southeast Regional held in Perry, GA in January. 
 In addition, an article was written for publication in the Seedstock Edge magazine sent to all NSR members in the January/February edition. The article featured one page of content and one page of activities for youth to apply knowledge. The article also included a QR code for youth to submit a secret code revealed after completing the activities to receive a Swientist branded prize. 
Partner with the Ohio FFA Association to develop and disseminate zoonotic disease risk and prevention curriculum in accordance with Ohio Department of Education standards for middle school agricultural education students. 
High school level curriculum is ready to disseminate and can be found at www.go.osu.edu/teachbiosecurity. Content is being developed for the middle school level curriculum and will be completed by contract end. Since many of the activities included in the curriculum contain optional hands-on activities, supply kits were assembled and are available to be requested by educators to use in their classrooms. The AIEERP website revision to include a landing page for all curriculum materials developed by our research group to be downloaded by educators. 

Collaborate with the American Association of Swine Veterinarians to build awareness for swine health careers in youth who show swine at a state and national level. 
Several studies show that for youth to pursue STEM careers, they must be exposed to career opportunities before they are 12 years old. To that end, a swine careers coloring book is being created to use alongside Swientist, NJSA, AASV, and Team Purebred activities that is focused on the multitude of careers in the swine industry. 
Collaborate with Team Purebred to engage national level swine jackpot show participants at various shows across the country 
No activity was completed for this objective during the reporting period.
Host Becoming a Swientist events to youth involved in jackpot shows with multiple species in Pennsylvania. 
Our collaborator with PennAg made a career change, and the new project director has faced challenges brought about by the workload transition. It was not possible to host a training session in December as planned, however plans are underway for a training session at a Pennsylvania Farm show in January.

2. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
Our collaborators in Pennsylvania have been struggling to follow through with the originally planned schedule of activities. They plan to host a second Swientist event, however it may occur after the project period.

3. Please describe the personnel involved and the number of hours spent by each to perform the deliverables between November 1 – December 31, 2021. Note: If there are not enough rows to accommodate all personnel, please feel free to add more rows.



	 Detail of assistance provided between August 1 – October 31, 2021

	Personnel (First & Last Name)
	Position Title
	Project-Specific Activities Performed
	Quantity/ Hours 

	Jacqueline Nolting
	Laboratory Operations Manager
	Coordinated all activities with collaborators, developed curriculum, attended national swine show
	15 hours

	Heather Nicholson
	Research Associate-2
	Developed curriculum, attended national swine show
	30 hours

	Kailie Plotnik
	Student Research Assistant
	Assisted with assembly of swientist on the go kits for registration kits at Western Regional show.
	8.5 hours

	Estimated Total Hours
	53.5 hours



