Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
Top 3 activities include:
 6/11/18 Morehead Livestock Expo Training, Morehead, KY
6/13/18: Western KY District Show, Muhlenburg, KY
6/19/18: Livestock Judging Contest Training: Muhlenburg, KY

Activities at these events include:
 Glo Germ activities to demonstrate disease spread, effective handwashing, germ transfer
Pig eraser give-aways
Display board with information on Swine influenza and zoonotic diseases

2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).

4-H: Student intern put together the display board, did the Glo Germ training
4-H provided the give-aways (pig erasers for visiting the booth and participating in Glo-germ activities)
State Public Health Veterinarian: provided glo germ and over sight

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.
Biggest challenge is lack of personnel to do things. There is one student attending the fairs to do the training and Glo Germ activities. At the KY State Fair, the PH Vet and the Intern will be there to conduct activities and assist with training.
4. Please include an updated project timeline.
July 17-18, 2018: State PH Vet to participate in the USDA/APHIS HPAI Tabletop exercise. This is a chance to learn more about how to respond to and coordinate with other agencies in the event of an HPAI outbreak, regardless of if it is a backyard flock, a large producer or a 4-H youth raising chickens. 
7/13-19/2018: Bowling Green, KY: “Top 12 Week”, 4-H Judging event 
[bookmark: _GoBack]7/20/18: Bowling Green Livestock Expo: variety of livestock, youth contact for education and Glo Germ activities
The KY State Fair is August 16-26, 2018. We will have a booth there with educational “grab bags”, Glo Germ activities, and a disease prevention scavenger hunt.
August 30, the Fairs will be over and no future activities are planned after this time.

5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.
Thank you for the Resources page on Basecamp. This has been a wonderful way to share and gather ideas for trainings and activities.

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.


OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions , either describe it here or just write ‘YES’ and we will follow up with you via phone or at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 



