## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Summary of what was done (200 words or less). What activities have taken place over the past 4 months? How have these activities addressed one or more of the project objectives? | Impact If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
|  | Intervention Activity (and location) | Baseline # prior to 2017-18 grant period | How did you measure the baseline? Did you include direct participants, families, etc.? | 2017-18 Audience (youth, community leaders, etc.?) | # of attendees/participants | # of materials distributed | Pre-test administered? (How many? To whom?) | Post-test administered? (How many? To whom?) | Did you collaborate with another state? If so, which one(s)?
|  | EXAMPLE: Four Scenario based training exercises | X# of training sessions held in 2016 to X total youth aged 11-15 | Only counted the number of actual youth who attended the session | Youth aged between 12 and 16 | X # attendees per training; total of X attendees
1. Enhance existing Excellence in Exhibition course | CFSPH continued to host the course and track use during this time period. | Offered course continuously through this time period | Began tracking course use April 24, 2017. Website www.bluenotflu.org was viewed by 68 unique users, and the online course was accessed 13 times by users in 7 states during April 24–May 1, 2017. | Counted unique users/views (did not count multiple views on same computer) | Target audience is youth aged 13–18 years but is open to anyone freely on the website | Website was viewed 4,617 times by 3,698 unique users, and the online course was accessed 1,755 times by users in 44 states during current funding period (May 1, 2017–Dec 28, 2018). | NA | NA | NA | Course available nationally. Worked with National Pork Board to approve course. Ohio used course at World Pork Expo activity. North Dakota implementing course as training for 4-H skillathon | The optional evaluation component has indicated an increase in knowledge and plans to adopt disease prevention habits upon post-course completion.
2. Promote and increase existing course distribution and implementation | CFSPH participated in CDC's ZOHU One Health call and described and promoted the courses. | Webinar | 0 | Number of participants | Public and animal health professionals | 311 attendees in live audience | Approximately 20,400 Bluenotflu.org stickers have been distributed | NA | NA | Collaborated with IAAE, Iowa FFA, Iowa 4-H, Ohio, North Dakota
3. Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course | The elementary aged Excellence in Exhibition online course received National 4-H Peer Review status during December 2018. | Offered course beginning October 31, 2018 | Began tracking course November 1, 2018. | Counted unique users/views (did not count multiple views on same computer) | Youth aged 7–12 years | The online course was accessed 87 times by users in 18 states during Oct 31, 2018–Dec 28, 2018). | NA | NA | NA | CDC, Ohio, National Pork Board reviewed course
4. Complete enhanced evaluation of educational materials | CFSPH completed analysis of data collected from the online and in person sessions and shared results with stakeholders. |  | 0 | NA | 4-H County Youth Coordinators and other adults Iowa high school aged youth enrolled in agriculture courses participating in livestock workshop | 4-H County Youth Coordinators and other adults - 23 Iowa high school aged youth enrolled in agriculture courses participating in livestock workshop - 120 | Biosecurity buckets - 120 Glo Germ kits for adults - 2 | Iowa high school aged youth enrolled in agriculture courses participating in livestock workshop - 120 | Iowa high school aged youth enrolled in agriculture courses participating in livestock workshop - 120 | CDC and CSTE evaluation experts assisted in developing the enhanced evaluation. Additional evaluation questions were added from the question bank from other states. The National Pork Board supplied animal movement "passports" and educational material. A youth organization specialist who attended a train-the-train session held two workshops using the materials | The last train-the-trainer session was held October 29, 2018, with 19 participants.