Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. The Center for Food Security and Public Health (CFSPH) completed analysis of evaluation data collected from online and in-person sessions as part of the supplemental enhanced evaluation award.
b. The CFSPH continued to host the online Excellence in Exhibition courses, supplemental material including PowerPoint presentations and hands-on activity guides, and the evaluations, available at www.BlueNotFlu.org.
c. The new Excellence in Exhibition course for elementary aged youth received National 4-H Peer Review status.

2. [bookmark: _GoBack]Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
a. National 4-H – Peer review of elementary course

3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

None
4. Please include an updated project timeline.

	May 1–Oct 31, 2017
	· Enhance existing course
· CFSPH continued to research how to incorporate the course into state and national 4-H curriculum through state and national 4-H development standards and peer review.
· CFSPH continued to make course edits as appropriate to maintain content accuracy and timeliness. 
· As a collaborating center with the OIE, CFSPH explored placing the OIE logo on the course.
· CFSPH modified the Google Analytics tracking of the course to better capture course use.
· Promote and increase existing course distribution and implementation
· CFSPH continued to distribute materials at events listed in the project proposal.
· CFSPH presented a seminar during the 2017 American Association of Extension Veterinarians’ annual meeting (held during the United States Animal Health Association meeting) and distributed promotional materials.
· CFSPH hosted an exhibit table at the National FFA Convention. CFSPH also provided printed material for youth, educators, and others at the National FFA Convention.
· CFSPH registered, researched, and began making travel arrangements to host an exhibit table and interactive teacher/student workshop at the International Association of Fairs and Expositions Annual Convention.
· CFSPH registered, researched, and began making travel arrangements to host an exhibit table at the National Association of Agriculture Educators conference.  
· Develop new course for younger audiences (specifically, children aged 7–12 years) based on existing course
· CFSPH continued to develop the outline, researched content, and researched best practices in online course development for the new course.

	Nov 1, 2017–Feb 28, 2018
	· Enhance existing course
· CFSPH consulted with CDC to revise the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH worked with CDC and CSTE to participate in any evaluation framework to assess implementation of the project on a national level.
· CFSPH submitted the current course for state and national 4-H review. The course was approved as official Iowa 4-H curriculum in January 2018.
· Promote and increase existing course distribution and implementation
· CFSPH and collaborating agencies pursued additional opportunities to engage participation among Iowa youth through exhibits, formal presentations, and/or demonstrations/workshops.
· CFSPH and IDPH submitted an abstract to the Council of State and Territorial Epidemiologists Annual Conference (2018).
· At all venues, CFSPH displayed interactive elements of the course on laptops and tablets, distributed informational flyers, handouts, stickers, and other material developed by CFSPH advertising the free course, and distributed zoonotic disease resources developed by CFSPH, other states, and CDC.
· Develop new course for younger audiences based on existing course
· CFSPH identified a DVM/MPH student intern to help with course development. 
· CFSPH expanded course curriculum to build upon the current course structure and be age appropriate for younger children, including more gamification, less text, a lower reading level, and shorter lessons.
· CFSPH finalized an outline for the new course.

	March 1–June 30, 2018
	· Enhance existing course
· CFSPH finalized review of content and updates, including improved compliance of Section 508 of the Rehabilitation Act, ensuring accessibility for all learners and allowing distribution through federal partners, to the currently available Excellence in Exhibition course for middle–high school youth. 
· CFSPH created certificate badges to be "earned" by completing lessons and the evaluation. 
· CFSPH received official Iowa and National 4-H peer reviewed status for the available course. 
· Promote and increase existing course distribution and implementation
· CFSPH worked with the National Pork Board to add a link to the course on the Pork Checkoff website. https://lms.pork.org/Tools/View/show-pigs 
· CFSPH attended North Dakota's "Healthy Fairs" meeting and workshop to present information about the Excellence in Exhibition course and experiences. 
· CFSPH and the Iowa Department of Public Health presented an abstract at the CSTE annual convention.
· CFSPH attended the World Pork Expo to distribute printed materials, promote the course, review the Ohio State University’s interactive booth, and seek donations for the enhanced evaluation incentives for youth (June 6–7, 2018).
· CFSPH hosted the following workshops, seminars, and exhibit tables:
· FFA State Leadership Convention exhibit table – April 23–24, 2018, with 5,000 attendees. 
· Eastern Iowa 4-H Food Safety Quality Assurance workshops – April 11, 2018. Four workshops with 115 youth. 
· Iowa 4-H Youth Conference workshops (2018) – Three workshops with 70 youth and six adult volunteers.
· Iowa 4-H Animal Science Roundup opening session (2018)— Three interactive seminars to 89 youth and 10 adult volunteers. 
· Iowa 4-H Animal Science Roundup swine session workshop (2018) – One interactive workshop to 15 youth and two adult volunteers.
· Iowa Association of Agriculture Educators (IAAE) annual meeting exhibit table and workshop – June 26–27, 2018, with approximately 120 attendees (table) and 3 attendees (workshop). 
· At all exhibit table venues, CFSPH displayed interactive elements of the course on laptops and tablets, distributed informational flyers, handouts, stickers, and other material developed by CFSPH advertising the free course, and distributed zoonotic disease resources developed by CFSPH, other states, and CDC.
· Develop new course for younger audiences based on existing course
· CFSPH continued to write content, design graphics, and develop the course. 
· Complete enhanced evaluation of educational materials
· CFSPH developed an enhanced evaluation component, including a learning management system, pretest, and posttest. 
· CFSPH ordered supplies for enhanced evaluation incentives, “biosecurity buckets,” and workshops. Biosecurity buckets included items such as a scrub brush, soap, gloves, boot covers, hand wipes, a Pork Checkoff "Passport" to track animal movement, and other educational materials. 
· All participants in 4-H Animal Science Roundup and 4-H Youth Conference workshops were required to complete the pretest, Excellence in Exhibition course, and posttest evaluations. All received a “biosecurity bucket” incentive and were entered into a drawing for a $25 gift card. 
· CFSPH and Iowa 4-H partners began advertising train-the-trainer sessions and recruiting volunteers.

	July 1–Oct 31, 2018
	· Enhance existing course
· CFSPH revised the evaluation component to collect the most useful data to improve the course.
· CFSPH worked with CDC and CSTE to participate evaluations to assess implementation of the project on a national level.
· CFSPH posted the updated middle/high school course during July.
· Promote and increase existing course distribution and implementation
· CFSPH hosted a webinar describing the course and resources to Iowa 4-H and Extension specialists. 
· Develop new course for younger audiences based on existing course
· CFSPH finalized course development and sent to collaborating agencies and partners for review. 
· CFSPH posted the new course.
· CFSPH developed an evaluation component comparable to the existing course and consistent with recommendations outlined by CDC and CSTE. 
· Complete enhanced evaluation of educational materials
· CFSPH continued to work with Iowa 4-H partners to advertise train-the-trainer sessions and recruit volunteers.
· CFSPH scheduled and hosted train-the-trainer sessions to describe how to use the PPT presentations, demonstrate hands-on activities, and provide additional information to volunteers.
· CFSPH ordered supplies for enhanced evaluation incentives, “biosecurity buckets,” and workshops. Biosecurity buckets included items such as a scrub brush, soap, gloves, boot covers, hand wipes, a Pork Checkoff "Passport" to track animal movement, and other educational materials. 
· CFSPH distributed incentives to adult volunteers (Glo Germ kits) and youth (biosecurity buckets). 
· CFSPH collected data from the pre and posttests.

	Oct 31–Dec 31, 2018
	· Develop new course for younger audiences based on existing course
· CFSPH advertised the new course to appropriate audiences.
· CFSPH began tracking use.
· The new course received National 4-H Peer Review status.
· Complete enhanced evaluation of educational materials
· CFSPH completed data analysis from the pre and posttests and shared with project partners.  




5. If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mschroeder@cste.org. 

All materials are posted to the Basecamp site. 

6. Please list suggestions for CSTE and CDC for how we can best facilitate your progress.

Continued assistance in promoting the course at the national level would be valuable. 

7. Please complete the attached spreadsheet to indicate progress made towards project deliverables.

OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions , either describe it here or just write ‘YES’ and we will follow up with you via phone or at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 

From National 4-H Peer Review of elementary edition: 

Reviewer 1: This 3rd party vendor submission is a highly engaging, science-based curriculum. It is well suited for the target audience.

Reviewer 2: I really like the different activities in this set of lessons. There are many different types of interactions which keep it from getting boring. Also, the learning is reinforced throughout the entire program so it is a good way to teach the concepts and have the kids remember them. The information is factual and is understandable to youth. I really liked the lesson which had music and a video. For future offerings, it would be nice to have some "sound segments" interspersed into the lessons as they help to make it even more interactive. 

Reviewer 3: Great set of activities!!! This is a great way to introduce or reinforce safe fair practices for 4-H members and volunteers.

From National 4-H Peer Review of high school edition: 

Reviewer 1: I look forward to using this website as a resource in the years ahead! You have a very thorough and strong product that will be valuable for many.

Reviewer 2: I found the slides and evaluation to be engaging and I thought you could expand the target audience to include 4-H professionals and the general public.

Reviewer 3: The lessons are easily accessible and engaging. Great user interaction and supplemental materials. I believe adding an audio component for those who wish to use would enhance the lessons. I
also believe these lessons would greatly benefit 4-H professionals, as all do not enter the profession with this knowledge.

