Influenza and Zoonoses Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. The signed contract between OSU and ODH was executed on December 19, 2018, providing the funds to complete the awarded project.
b. The Ohio State IRB has approved human subject protocols for both phases of the anthropology study as “exempt”. Anthropological observations were completed at swine jackpot shows and fairs and all data has been categorized and is ready for analysis.
c. Economic data collection is complete and data analysis is underway. 

2. Please list the collaborators on this quarter’s achievements and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
a. OSU Extension collaborators were instrumental in identifying and collecting economic data from swine exhibitors needed to build the desired models. 
b. The Animal Influenza Ecology and Epidemiology Research Program (AIEERP) staff collaborated with OSU extension educators to collect economic data from swine exhibitors who participate at local, state, and national levels. All data has been shared with the collaborating agricultural economist and data analysis is underway. AIEERP obtained OSU IRB exemption approval for both phases of the anthropology study and data collection has been ongoing. An anthropologist conducted observations of swine exhibitions at local, state, and national level shows. All collected data has been coded and data analysis will be conducted upon completion of focus groups. Key groups have been identified to participate in focus group discussions and they will be held during winter 2019.


3. Please describe areas of concern or challenges in meeting the objectives or providing deliverables.

[bookmark: _GoBack]Funds were not received from ODH until December 2018, making it difficult for progress to be made with collaborators who could not fund efforts through alternative means.

4. Please include an updated project timeline.
Focus groups are the last data collection activities needed, and will be completed during January – February 2019. Anthropology data analysis will be completed after focus group data is collected, and a final report will be written. Economics data analysis is currently underway, and the final report will be completed spring 2019.  All tasks are expected to be completed by April 31, 2019.


