
Please return completed Progress Report to CSTE at mhuynh@cste.org by May 17, 2019.
Note: Please submit one response per jurisdiction.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Zoonotic content enhancement to Maryland and West Virginia Online Animal Husbandry and Quality Assurance program)
Accomplishments/Progress to-date: Updates made. The site went live on April 10, 2019
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 2: Video production- two videos (handwashing, conducting Animal Health Self-Certification) 
Accomplishments/Progress to-date: Permissions to shoot videos on campus farm underway. Storyboards being drafted.
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 3: Zoonosis Activity Kits- 80 (1 per county in MD and WV)
Accomplishments/Progress to-date: Draft outline of kit activities, Draft supply list under development. Roll-out date for faculty/staff/volunteers/fair officials scheduled for June 11 at three sites across MD – each MD county invited to bring a team of 4 individuals.
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 4: Zoonosis Awareness Signs for Fairs and Expos
Accomplishments/Progress to-date: Review of existing and possible designs underway
Did this deliverable include an educational intervention: Yes / No
(If Yes, please complete the Impact Chart appended to this report.)

2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).  

Maryland Department of Health: Coordinates regular meetings with partner agencies and provides additional support to Maryland 4-H as needed.   Subject matter experts for zoonotic disease material content and liaison with CSTE.  

University of Maryland Extension 4-H:  Main focus is development of content for AH& QA online program and zoonosis activity kits.  Collaborations with MDH to develop signage.

Maryland Department of Agriculture:  Subject matter expert for animal zoonosis, liaison for fairgoers and animal health professionals regarding zoonotic disease.

West Virginia Extension:  Assisting University of Maryland 4H develop content with AH & QA online program and zoonosis activity kits.  

3) Describe areas of concern or challenges in meeting the objectives or providing deliverables.

Logistics surrounding completing proposed educational videos.  Gaining permission to shoot videos, narration, etc….
[bookmark: _GoBack]
4) Include an updated project timeline, if relevant.

5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 

https://www.agnr.umd.edu/ahqa/

6) List suggestions for CSTE and CDC for how we can best facilitate your progress.

7) List any topics or questions you would like to add for discussion on an upcoming all-site conference call.  

Continue conversation on sharing project created resources across stateliness - permissions

8) Would you like to request an extension on your contract? If so, please provide an estimated project end date in which all activities and deliverables will be completed.  Please note, this does not guarantee approval of extension.  Additional information may be requested, as relevant, including revised workplan, timeline, and budget.  CSTE will be in touch following review of your report to discuss next steps for contract amendment. 

YES – particularly for completing proposed videos and the opportunity to continue to add to the Zoonosis Activity Kits.  Potentially extend 60 days to assist with facilitating permission to shoot from the university and complete videos.  Additional time would be helpful to modify Zoonosis Kits based on the initial response. 


OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions, either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2018-19 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2018-19 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	MD and WV Online AH&QA Program
	Online training module – site opened Apr 10 and close Aug 10, 2019
	444 as of 5/13/19
	
	Individual online completion
	
	West Virginia
	444
	444

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	





