
Please return completed Progress Report to CSTE at mhuynh@cste.org by May 17, 2019.
Note: Please submit one response per jurisdiction.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Expanded curriculum for annual 4-H “Teens as Teachers – Biosecurity” workshop via a partnership with Dr. Bowman and The Ohio State University (OSU). 
· Accomplishments/Progress to-date: The ISDH had a conference call with Dr. Bowman and his colleagues at OSU on February 15th, 2019. During this call, Dr. Bowman presented the materials and programs he has developed in Ohio. The purpose of the call was to discuss how some content could be applied in Indiana. Dr. Bowman has also had follow up calls with 4-H staff to discuss ways to expand their Teens as Teachers program, which will be held early next year. 
· Did this deliverable include an educational intervention: Yes / No
· (If Yes, please complete the Impact Chart appended to this report.)- TBD. Intervention has not been completed.

· Deliverable 2: Pre-test/post-test for workshop participants to evaluate expanded 4-H curriculum.
· Accomplishments/Progress to-date: N/A, workshop has not been fully developed yet. 
· Did this deliverable include an educational intervention: Yes / No

· Deliverable 3: Materials for INAF workshop. 
· Accomplishments/Progress to-date: This deliverable is complete. The ISDH Enteric Epidemiologist, State Public Health Veterinarian, Epidemic Intelligence Service Officer, and Respiratory Epidemiologist developed content for an educational workshop directed at fair and festival planners across the state of Indiana. Developed content included an overview of zoonotic diseases within the context of fair and festival planning, and a full overview of the Compendium of Measures to Prevent Disease Associated with Animals in Public Settings, 2017 developed by the National Association of State Public Health Veterinarians.   
· Did this deliverable include an educational intervention: Yes / No

· Deliverable 4: State and county fair self-assessment and scoring rubric based on the Compendium of Measures to Prevent Disease Associated with Animals in Public Settings.
· Accomplishments/Progress to-date: This deliverable is complete. A county fair/festival self-assessment survey was developed in order to evaluate how Indiana fairs and festivals align with the recommendations presented in the Compendium. This self-assessment was disseminated to all INAF attendees. 
· Did this deliverable include an educational intervention: Yes / No

· Deliverable 5: Installation of 6 handwashing stations and biosecurity signs at local agricultural events in greatest need of assistance. 
· Accomplishments/Progress to-date: Incomplete. ISDH has not received funding as of 5/17. 
· Did this deliverable include an educational intervention: Yes / No

· Deliverable 6: Attendance of INAF staff at the IAFE training on zoonotic disease prevention. 
· Accomplishments/Progress to-date: This deliverable is complete. ISDH staff presented at the INAF convention on January 5, 2019. This was also presented as a webinar to local health department staff. 
· Did this deliverable include an educational intervention: Yes / No

2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).

[bookmark: _GoBack]Indiana 4-H is responsible for conducting the Teens as Teachers training to 4-H youth. They have an existing program in place that we are working on expanding. ISDH was responsible for completing a training at the INAF annual convention and conducting agency self-assessments. The Indiana State Board of Animal Health has several training tools and resources, including an interactive card game, which will be disseminated to 4-H youth. ISDH, BOAH, and INAF were all involved in an on-site visit with CDC and CSTE.

3) Describe areas of concern or challenges in meeting the objectives or providing deliverables.

Indiana has not received the needed funding to complete the remaining deliverables. 

4) Include an updated project timeline, if relevant.

5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 

6) List suggestions for CSTE and CDC for how we can best facilitate your progress.
The main priority is to receive prompt communication about the release of funds. 

7) List any topics or questions you would like to add for discussion on an upcoming all-site conference call.  

8) Would you like to request an extension on your contract? If so, please provide an estimated project end date in which all activities and deliverables will be completed.  Please note, this does not guarantee approval of extension.  Additional information may be requested, as relevant, including revised workplan, timeline, and budget.  CSTE will be in touch following review of your report to discuss next steps for contract amendment. 

Yes. We would like to request an extension through February 29, 2020. Because the funds were not received in a timely manner, we will need to fund our programs, including the IAFE training and the Teens as Teachers Biosecurity Workshop for the 2019-2020 year. 

OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions, either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2018-19 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2018-19 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	INAF Compendium Review
	0
	INAF has not partnered with ISDH in the past
	Fair and Festival Planners across the state of Indiana
	50
	150
	N/A
	Pre-test administered to each participating fair or festival
	N/A

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	





