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Please return completed Progress Report to CSTE at mhuynh@cste.org by May 17, 2019.
Note: Please submit one response per jurisdiction.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Create a Disease Prevention Activity Kit geared toward younger 4-H participants.
Accomplishments/Progress to-date: This deliverable will begin when MSU has received funding.
Did this deliverable include an educational intervention: No

· Deliverable 2: Create a Zoonotic Disease/Swine Influenza educational session targeted to high school-aged 4-H and FFA participants
Accomplishments/Progress to-date: During the development of this proposal, this deliverable was intended to be met during the Michigan FFA Annual Convention in March of 2019. This was not accomplished, as the funding for this proposal was still uncertain at the time of the convention. 
Did this deliverable include an educational intervention: No

· Deliverable 3: Reprinting of “Be Healthy Around Animals” signage
Accomplishments/Progress to-date: 800 signs were printed with 400 being distributed at the Michigan Association of Fairs and Exhibitions Annual Convention in January 2019. The remaining signs will be available for distribution to fairs during the 2019 fair season.  
Did this deliverable include an educational intervention:  No

· Deliverable 4: Sessions for 4-H Exploration Days.
Accomplishments/Progress to-date: The Be a Disease Detective session for the Michigan 4-H Exploration Days is scheduled for June 20 - 21, 2019 at Michigan State University. 
Did this deliverable include an educational intervention: Yes, education session is not scheduled until June 2019. 

· Deliverable 5: Michigan 4-H Animal and Veterinary Science Camp
Accomplishments/Progress to-date: The camp is scheduled to run June 24-28, 2019. There will be 50 youth in attendance of the camp from six states and one individual from China. MSU Extension is currently in the review process of veterinary students to serve as camp counselors. The camp schedule has included a daily “One Health” presentation for the youth in attendance. 
Did this deliverable include an educational intervention: Yes, education session is not scheduled until June 2019. 


· Deliverable 6: Print copies of The Junior Disease Detectives: Operation Outbreak Graphic Novel.
Accomplishments/Progress to-date: printed 500, to be used at events with youth, and also as part of a new curriculum unit on Epidemiology in development by MSU Extension and MDHHS (this is an activity funded by the 2018 grant-currently in the review stage).
Did this deliverable include an educational intervention: No


· Deliverable 7: Design a specific MSUE Extension Webpage designated to hosting all the materials developed as a result of the CDC/CSTE Youth in Agriculture funding received in Michigan.
Accomplishments/Progress to-date: This deliverable will begin when MSU has received funding. 
Did this deliverable include an educational intervention: No

· Deliverable 8: Development of an evaluation plan
Accomplishments/Progress to-date: IRB approval has been submitted to MSU’S Office of Regulatory Affairs for approval.  This deliverable will begin when MSU has received funding.
Did this deliverable include an educational intervention: No

· Deliverable 9: Continue Outreach with Fair Boards and Local Public Health in Michigan.
Accomplishments/Progress to-date: MDHHS staff and the Emergency Preparedness Coordinator with the Livingston County Health Department provided a Roundtable Session at the 2019 Michigan Association of Fairs and Exhibitions annual conference about the 2018 response to an outbreak of swine influenza at a fair in Livingston County.  30 people attended.
Did this deliverable include an educational intervention: No

· Deliverable 10: Conduct a Regional Meeting with State Partners.
Accomplishments/Progress to-date: This deliverable will begin when MSU has received funding.
Did this deliverable include an educational intervention: No

· Deliverable 11: Sustainability.
Accomplishments/Progress to-date: 
Did this deliverable include an educational intervention: No


2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
MSU Extension 4-H program supported the following deliverables in relationship to this grant.
	- Michigan Association of Fairs and Exhibitions Annual Convention in January 2019
	- Storage of “Be Healthy Around Animals” signage
	- Michigan 4-H Exploration Days
	- Michigan 4-H Veterinary Science Camp 

3) Describe areas of concern or challenges in meeting the objectives or providing deliverables.
At this time the biggest challenge for MSU Extension will be receiving funds, or confirmation for the receiving of fund, in a timely manner to accomplish the deliverables within the timeline established by the grant. 

4) Include an updated project timeline, if relevant.
	December 2018
May 2019
	Notification of Award
Establish financial contracts with partners (CSTE, MSUE)

	May-December, 2019
(if extension approved)
	Create youth activity kit and Influenza outbreak educational session for high school youth, both to include an evaluation component

	January 10-12, 2019:
DONE
	Michigan Association of Fairs Convention including a MDHHS/MSUE session about the Youth Ag Education Grant accomplishments


	June 19-21, 2019
	Present session “Be a Disease Detective” during 4-H Exploration Days

	June 2019
	Organize/present “One Health” sessions at 4-H Animal and Veterinary Science Camp; hire 1 veterinary student mentor for each 10 campers

	Fall 2019
(if extension approved)
	Host regional training session with 4-H partners 

	January-June, 2019
DONE
	Print and distribute additional previously developed resources for 4-H youth and fairs

	June-December, 2019
(if extension approved)
	Develop a dedicated webpage on the MSUE website for the products developed to date for this collaboration




5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 

6) List suggestions for CSTE and CDC for how we can best facilitate your progress.

7) List any topics or questions you would like to add for discussion on an upcoming all-site conference call.  

8) Would you like to request an extension on your contract? If so, please provide an estimated project end date in which all activities and deliverables will be completed.  Please note, this does not guarantee approval of extension.  Additional information may be requested, as relevant, including revised workplan, timeline, and budget.  CSTE will be in touch following review of your report to discuss next steps for contract amendment. 

Yes, estimated project end date would be 31DEC2019. 

OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions, either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2018-19 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2018-19 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	MSU 4-H Exploration Days Session “Be a Disease Detective” 
	We have hosted 3 previous sessions, one each in 2016, 17 and 18.
	Counted number of youth that attended each session
	Youth aged between 12-18
	20 per training x 3 = 60 total attendees to date
	Be a Disease Detective Workbooks
	In 2018, two representatives from the Maine Dept of Agriculture, Conservation and Forestry attended the session
	Planned for 2019
	Planned for 2019

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	





