
Please return completed Progress Report to CSTE at mhuynh@cste.org by May 17, 2019.
Note: Please submit one response per jurisdiction.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: Maintain and promote existing courses and supplemental material

Accomplishments/Progress to-date: Modified the existing online courses to remove references specifically to Iowa so that the course is more "generic" for use by multiple states. Modified the last page of the courses to redirect to a page external to the course where users can select which state or group they are from, which will allow us to have multiple/different surveys for different states, but still allow us to track this data. Created a Nebraska-specific webpage similar to www.bluenotflu.org (this allows us to still track usage data of the course, but target the page specifically towards NE users which was important to NE). Submitted application for IRB approval, in order to publish youth engagement activities and results from evaluation components.

Did this deliverable include an educational intervention: Yes 
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 2: Conduct outreach to youth by using the courses and hands-on activities developed by CFSPH, other states, and CDC during previous funding cycles. FY16 and FY17

Accomplishments/Progress to-date: Outreach was performed at the following events: State FFA Convention and World Food Prize Iowa Youth Institute. For all events, participants were either provided information about the course in the form of a flyer and in-person reference (State FFA) or were required to take the course, as well as a pre- and post-course survey, before attending the event (World Food Prize immersion). During the event, in-person activities were performed with the students (e.g., mucous swap, PPE activity, glo germ activity) and associated learning objectives were discussed. Students had the opportunity to engage with the presenter(s) and ask and answer questions.

Did this deliverable include an educational intervention: Yes
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 3: Conduct outreach, support, and training to adults by using the materials developed during previous funding cycles and expanding training materials to build capacity and ability for others to train youth

Accomplishments/Progress to-date: Outreach was performed at the ISU Extension and Outreach Annual Conference Learning Fair, and a train-the trainer session was held at the Midwest Vet Conference in Ohio. A presentation was delivered during the March monthly call to project partners on Iowa's experiences with reaching older youth and identifying and leveraging funding sources. CFSPH engaged with adult mentors/teachers at the World Food Prize Iowa Youth Institute to offer materials and support for use in their classrooms

Did this deliverable include an educational intervention: Yes
(If Yes, please complete the Impact Chart appended to this report.) 

2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
a. Iowa FFA- partnered to host workshop at State Convention about the Excellence in Exhibition Course
b. ISU Extension and Outreach- partnered to host an exhibit at the Annual Conference during the Learning Fair about the Excellence in Exhibition course
c. World Food Prize Iowa Youth Institute- partnered to host two immersion activities for youth about the Excellence in Exhibition course
d. Nebraska- using Excellence in Exhibition course in their outreach

3) Describe areas of concern or challenges in meeting the objectives or providing deliverables.
a. We began pursuing external funding to be able to hold 1-2 Biosecurity Camps for youth. However, because we were not able to identify a mechanism to fund personnel time to develop agendas and activities, facilitate the events, and collect and report any evaluation data collected, we are not likely to be able to complete this outreach activity (was included as an additional objective contingent upon receiving external funding). 

4) Include an updated project timeline, if relevant.

	February 1- April 30, 2019
	· Maintain and promote existing courses and supplemental material
· CFSPH made course edits as appropriate to maintain content accuracy and timeliness.
· CFSPH continued to host and maintain the courses on the current website, ensuring that software and programming are kept updated to allow continued access for a variety of users (including common mobile devices and laptops/computers) to courses and website content, and work with users to address any problems with content access and usability. 
· CFSPH distributed and collected evaluation data from course use, as well as selected in-person events, and will analyze and report to other states, CSTE, and CDC any pertinent information gained from the evaluations. CFSPH will revise the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH will continue to track and report to other states, CSTE, and CDC visits to the course webpage and the courses themselves to monitor the need for and impact of these materials
· Conduct outreach to youth by using the courses and hands-on activities developed by CFSPH, other states, and CDC during previous funding cycles
· CFSPH held interactive workshops to directly reach our target audience of Iowa youth as we did in the previous year at Iowa 4-H State Conference and Animal Science Roundup. During the workshops, we shared some of the hands-on activities developed by CFSPH, other states, and CDC in previous years. Workshops were held during the following events:
· Iowa FFA Association Leadership Conference and State Convention (2019)
· World Food Prize Iowa Youth Institute (WFP IAYI)
· In order to participate in the workshop at the WFP IAYI, interested youth were required to complete the online course ahead of time, including the evaluation component that was developed in 2018. 
· CFSPH has pursued additional funding sources to develop, implement, and facilitate 1–2 biosecurity camps for middle–high school aged youth, to be held at Iowa State University, in partnership with previously engaged Iowa 4-H and Iowa FFA partners. No additional funding has been secured at this time. 
· Conduct outreach, support, and training to adults by using the materials developed during previous funding cycles and expanding training materials to build capacity and ability for others to train youth
· CFSPH held a train-the-trainer session at the Midwest Vet Conference in Ohio. 
· CFSPH continues to initiate contact with and offer support to Iowa 4-H leaders, County Youth Coordinators, Agricultural educators, and other adults to facilitate use of the courses in their youth outreach and education.  
· CFSPH continues to support health and agriculture departments, educational institutions, and other organizations in other states and regions in adopting and adapting the courses for youth education in those areas.

	May 1- July 31, 2019
	· Maintain and promote existing courses and supplemental material
· CFSPH will continue to make course edits as appropriate to maintain content accuracy and timeliness.
· CFSPH will continue to host and maintain the courses on the current website, ensuring that software and programming are kept updated to allow continued access for a variety of users (including common mobile devices and laptops/computers) to courses and website content, and work with users to address any problems with content access and usability. 
· CFSPH will work with CDC and CSTE to continue to participate in any evaluation framework to assess implementation of the project on a national level.
· CFSPH will continue to collect, analyze, and report to other states, CSTE, and CDC any pertinent information gained from the evaluations. CFSPH will revise the evaluation component as necessary to collect the most useful data to improve the course.
· CFSPH will continue to track and report to other states, CSTE, and CDC visits to the course webpage and the courses themselves to monitor the need for and impact of these materials.
· Conduct outreach to youth by using the courses and hands-on activities developed by CFSPH, other states, and CDC during previous funding cycles.
· CFSPH will hold interactive workshops to directly reach our target audience of Iowa youth as we did in the previous year at Iowa 4-H State Conference and Animal Science Roundup. During the workshops, we will share some of the hands-on activities developed by CFSPH, other states, and CDC in previous years. In order to participate in the workshops interested youth will be required to complete the online course ahead of time, including the evaluation component that was developed in 2018. Proposed workshops will be held during the following events:
· 4-H State Conference and Animal Science Roundup
· Conduct outreach, support, and training to adults by using the materials developed during previous funding cycles and expanding training materials to build capacity and ability for others to train youth.
· CFSPH will pursue hosting an interactive workshop including recommendations for using the courses within the 4-H curriculum during Youthfest, the annual conference for 4-H County Youth Coordinators and staff in Iowa. 
· CFSPH will continues to initiate contact with and offer support to Iowa 4-H leaders, County Youth Coordinators, Agricultural educators, and other adults to facilitate use of the courses in their youth outreach and education.  
· CFSPH will continue to support health and agriculture departments, educational institutions, and other organizations in other states and regions in adopting and adapting the courses for youth education in those areas.




5) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 
a. All materials are posted to the Basecamp site.

6) List suggestions for CSTE and CDC for how we can best facilitate your progress.
a. Continued assistance in promoting the course at the national level would be valuable.

7) List any topics or questions you would like to add for discussion on an upcoming all-site conference call.  
a. None

8) Would you like to request an extension on your contract? If so, please provide an estimated project end date in which all activities and deliverables will be completed.  Please note, this does not guarantee approval of extension.  Additional information may be requested, as relevant, including revised workplan, timeline, and budget.  CSTE will be in touch following review of your report to discuss next steps for contract amendment. 

a. An extension is not requested. 



OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions, either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2018-19 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2018-19 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	NA

	Website was viewed 4,617 times by 3,698 unique users, and the online course was accessed 1,755 times by users in 44 states during the previous funding period (May 1, 2017–Dec 28, 2018).

	Counted unique users/views (did not count multiple views on same computer)

	Target audience is youth aged 13–18 years for the middle/high school course and aged 7-12 years for the elementary course but is open to anyone freely on the website

	During this quarter thus far, the website was viewed 1,057 times by 877 unique users in 37 different states.

	NA

	Course available nationally 

Worked directly with NE to create a landing page specifically for their target audience and to create a google survey specific to their audience.

	NA

	NA


	Two activity-based workshops

	In previous funding cycles, 5 activity-based workshops were held in conjunction with the Iowa 4-H Conference and Animal Science Roundup, and one workshop with the East Iowa Extension FSQA.

	Only counted the number of individuals who attended the workshops

	
High school aged FFA members 

High school aged WFP participants

	
State FFA workshop with interactive activities-- 130 participants

Immersion interactive activity for youth at the World Food Prize Iowa Youth Institute (WFP IAYI) -- 60 participants

	8 Biosecurity Buckets

Promotional flyers and educational handouts on disease prevention
  
Promotional stickers

	NA

	A pre-course survey was distributed to all participants in the WFP IAYI (41 students)

	A pre- and post- course survey and a post-activity evaluation was distributed to all participants in the WFP IAYI (41 students)


	One interactive booth 

One webinar 

One train-the-trainer seminar

One activity-based workshop

	In previous funding cycles, booths have been hosted at 7 events, one webinar was delivered, one train-the-trainer seminar was delivered, and 5 activity-based workshops were held.

	Only counted the number of individuals who attended the workshops

	Extension personnel

	Learning Fair at the ISU Extension and Outreach Annual Conference -- 450 attendees

50 participants at the train-the-trainer seminar

Webinar with project partners from 8 states, CDC, and CSTE

16 adult mentors/teachers at  WFP IAYI activity-based workshop

	Electronic resources distributed
[bookmark: _GoBack]
	National audience for webinar and train-the-trainer

	NA

	NA






