
Please return completed Progress Report to CSTE at mhuynh@cste.org by May 17, 2019.
Note: Please submit one response per jurisdiction.

1) List project deliverables and describe progress made towards completion of these deliverables:  

· Deliverable 1: (matching game)
Accomplishments/Progress to-date: Joe and I have had one design and content meeting and we have secured a company to produce a prototype for us. After the prototype is created we will spend time testing the game with age appropriate children through 4-H Clover Buds volunteers. 
Did this deliverable include an educational intervention: Yes
(If Yes, please complete the Impact Chart appended to this report.) 

· Deliverable 2: (breakout boxes)
Accomplishments/Progress to-date: We have not begun to create the content for the breakout boxes yet.
Did this deliverable include an educational intervention: Yes- it will but work has not begun on this deliverable yet
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 3: (zoonotic disease prevention intern)
Accomplishments/Progress to-date: Interviews have occurred for the undergraduate zoonotic disease prevention intern and an intern has been hired. Their first day will be this Friday, May 24th. 
Did this deliverable include an educational intervention: No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 4: (Zoonotic disease prevention entry category at county fairs across the state, and the Minnesota State fair.)
[bookmark: _GoBack]Accomplishments/Progress to-date: This entry category is being offered again with the hopes of doubling the number of entries this year from last year, which was 12. A promotional video advertising this disease category has already been created and is in the final stages of editing. 
Did this deliverable include an educational intervention: No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 5: (Promotional video for zoonotic disease prevention category)
Accomplishments/Progress to-date: The video has been created and is in the final stages of editing. 
Did this deliverable include an educational intervention: No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 6: (Safer FACES promotion)
Accomplishments/Progress to-date: Postage was purchased and already existing postcards advertising this program were sent out to all know agritourism and county fair venues in Minnesota. As a result of this mailing, there was a 6% registration increase for Safer FACES. There is a plan being established for paid Facebook posts but none have been posted yet. 
Did this deliverable include an educational intervention: No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverable 7: (Emerging Issues Breakfast)
Accomplishments/Progress to-date: No planning has begun on this yet because it is always held in November or December. 
Did this deliverable include an educational intervention: No
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverables 8 & 9: (Agritourism Workshops)
Accomplishments/Progress to-date: Our first agritourism workshop is taking place on Thursday, May 16th. There are 31 people registered from 20 different venues. Our booklet, presentations, and evaluations are prepared and ready for the workshop.
Did this deliverable include an educational intervention: Yes
(If Yes, please complete the Impact Chart appended to this report.)

· Deliverables 10: (Emerging Issues Breakfast)
Accomplishments/Progress to-date: No planning has begun on this yet because it is always held in November or December. 
Did this deliverable include an educational intervention: No
(If Yes, please complete the Impact Chart appended to this report.)


2) List the collaborators involved to-date and briefly describe their role in the project (i.e. 4H, State PH, State Animal Health).
1) 4-H:  They have been instrumental and taking the lead on deliverables 1-5 and have been an equal partner with MDH.
2) MDH: We have been taking the lead on deliverables 6-10 and have also been partnering with   4-H on scientific content for deliverables 1-5.
3) Minnesota Board of Animal Health: They have consulted on the content for the Agritourism Workshops and the Emerging Issues Breakfast.
4) Minnesota Department of Agriculture: They are co-presenting the Agritourism Workshops with us. 


5) Describe areas of concern or challenges in meeting the objectives or providing deliverables.
		Our main area of concern is the timeline to complete all of the deliverables. 

6) Include an updated project timeline, if relevant.
	
	See attachment. 

7) If you have materials you are already distributing, please upload a PDF or a link to the Basecamp site (https://3.basecamp.com/3164497/buckets/2026830/vaults/306679424) For Basecamp access, please email mhuynh@cste.org. 

8) List suggestions for CSTE and CDC for how we can best facilitate your progress.

9) List any topics or questions you would like to add for discussion on an upcoming all-site conference call.  

10) Would you like to request an extension on your contract? If so, please provide an estimated project end date in which all activities and deliverables will be completed.  Please note, this does not guarantee approval of extension.  Additional information may be requested, as relevant, including revised workplan, timeline, and budget.  CSTE will be in touch following review of your report to discuss next steps for contract amendment. 

	Yes, we would like to request an extension to our contract through 12/31/2019. We are planning to hold our 4th Annual Emerging Issues Breakfast in late November/early December and we would also like to hold a second Agritourism Workshop sometime in December after the fall agritourism season is complete. 



OPTIONAL (but please complete if relevant)
If you have a story or anecdotal example of how an individual, group, or community was positively impacted OR an outbreak response that was better facilitated as a result of your YIA project’s interventions, either describe it here or just write ‘YES’ and we will follow up with you at a later date.  These ‘success’ stories combined with quantitative impact numbers will be used to share project successes with leadership. 


Influenza and Zoonoses Education among Youth in Agriculture
Interim Progress Report
Jurisdiction: Minnesota
Date: 5/7/19

	Yes, we have one related to a 4-H group last year that entered a project in the new Zoonotic disease prevention category the Minnesota State fair. They created a really good video about zoonotic disease prevention in a fair setting and as a result they have had the opportunity to work with a professional videographer to make a promotional video for the Science of Ag projects, which include the Zoonotic  disease prevention category. This team, called Future Generations, has also taken  it upon themselves to work with their county fair to raise money in order to install handwashing stations and produce a “how to” handwashing video that will play at the handwashing stations. Our grant will be providing them with a small amount of money to purchase screens that will be attached to the handwashing stations. We couldn’t’ be more proud of these girls and feel as though this grant is what got them interested in the idea of disease prevention and now they are leaders at their own county fair. 
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Impact Chart 
If the activity/deliverable described is/included an Educational Intervention, please complete this portion of the report
	Impact 
	Evaluation

	Intervention Activity
	Baseline #  prior to 2018-19 grant period
	How did you measure the baseline? Did you include direct participants, families, etc?
	2018-19 Audience (youth, community leaders, etc?)
	# of attendees/participants
	# of materials distributed
	



Did you collaborate with another state? If so, which one(s)?
	Pre-test administered? (How many? To whom?)
	Post-test administered? (How many? To whom?)

	EXAMPLE: Four Scenario based training exercises
	X# of training sessions held in 2016 to X total youth aged 11-15
	Only counted the number of actual youth who attended  the session
	Youth aged between 12 and 16
	X # attendees per training; total of X attendees
	
	
	
	

	Matching Game
	There is no baseline
	Will count the number of 4-H clubs that get the match game
	Kindergarten through 2nd graders
	Unknown at this time
	1,300 will be made
	No
	Will be sent along with the game
	Will be provided to club leader after game is played

	Agritourism Workshops
	145 people have attended previous workshops
	Will count the number of people who actually attend not just those who registered
	Anyone working in agritourism or is interested in getting started
	Unknown until the events occur
	We have 4 types of laminated posters, refrigerator thermometers, mental health tools and more but we don’t know how many will be taken because the workshops haven’t occurred yet 
	No
	We will be using Turning Point to quiz attendees live during the workshop
	We will send a small post-quiz after the workshop

	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	



