## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes (What is the impact and reach of these activities? How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics))
1. Web-based, interactive educational modules addressing zoonotic disease prevention and biosecurity measures | Course content and learning objectives were finalized for all six modules. Content was circulated among IDPH, 4-H, and FFA staff. Web-based course delivery options were explored and tested on multiple devices. Articulate Storyline was chosen as the mode of course delivery. Web modules were designed and population of all six modules with content, graphics, and interactive elements is underway. | Content was developed and approved for all six modules. Module 1 describes influenza and other zoonotic diseases, their importance, and risk factors for infection. Module 2 describes the five routes of disease transmission, provides examples of zoonotic diseases transmitted by each route, and offers suggestions for prevention of disease transmission. Module 3 teaches users the importance of biosecurity and describes measures that can be taken to prevent disease transmission to people and animals on farm and at exhibitions. Module 4 describes the 2015 highly pathogenic avian influenza outbreak and its impact on animal agriculture and potential impact on public health. Module 5 describes the H3N2v influenza outbreak associated with swine exhibitions and prevention measures exhibitors should take. Module 6 introduces users to agencies involved in animal and public health and career opportunities for those interested in animal and public health.
2. Development of supplemental materials on zoonotic disease prevention and biosecurity measures | Ideas for supplemental materials were recorded throughout content development based on the results of the ag educator and youth surveys. | Supplemental materials for all modules will be developed to support classroom education or zoonotic disease preventive practices. Supplemental materials will be developed for Module 1 relating to common zoonoses and the diseases they cause in both animals and humans. Supplemental materials will be developed for Module 2 relating to the routes of disease transmission. Supplemental materials will be developed for Module 3 relating to biosecurity practices that should be implemented to prevent zoonotic disease transmission. Supplemental materials will be developed for Modules 4 and 5 to aid in understanding of influenza viruses, prevention measures, and potential impacts on animals, agriculture, and public health. Supplemental materials will be developed for Module 6 relating to animal and public health agencies and careers.