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Please return completed Progress Report to CSTE at mschroeder@cste.org.  
1. Identify your top three achievements over the last quarter. 
A. The Center for Food Security and Public Health (CFSPH) researched and tested web-based course delivery options and determined the best mode of delivery for this audience.
B. CFSPH developed learning objectives and drafted content outlines for all six modules; IDPH reviewed and approved all six content outlines.
C. CFSPH began developing the web-based modules and populating the modules with content, graphics, and interactive teaching elements.   
2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
CFSPH developed learning objectives and content for all six modules. The content was circulated among the Iowa Department of Public Health, 4-H, and FFA partners for review and approval.   
3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
No challenges or concerns have been identified at this time. 
4. Please include an updated project timeline.
	Present–June 30, 2016
	· Conduct ag educator and youth focus group surveys; summarize findings
· Explore and determine different web-based course delivery options
· Hold technology development meetings to determine best method of course delivery and evaluation component
· Develop module content outlines and learning objectives for modules 1–6
· Research and draft content for modules 1–3
· Circulate outline, learning objectives, and draft content for review by IDPH, CFSPH, 4-H, and FFA staff for modules 1–3

	July 1–August 31, 2016
	· Determine interactive elements needed for modules 1–3
· Research and draft content for modules 4–6
· Determine interactive elements needed for 4–6
· Circulate outline and learning objectives for review by IDPH, CFSPH, 4-H, and FFA staff for modules 4–6
· Begin web module design and programming

	September 1–October 31, 2016
	· Finalize content for all modules
· Continue with technology development and course design
· Populate web pages with content, graphics, and interactive elements
· Circulate all module content for review by IDPH, CFSPH, 4-H, and FFA staff
· Circulate all module content for review by youth in agriculture and ag educator focus group members
· Incorporate evaluation component into modules
· Begin drafting supplemental module content (handouts, instructor guide, signage, etc.)

	November 1–December 31, 2016
	· Finalize six web-based modules
· Complete supplemental materials based on module content (handouts, instructor guide, signage, etc.)



5. If you have materials you are already distributing, please include a sample PDF or link of those materials. 
Content outline and learning objectives for all six modules have been developed. These are not being distributed to the public but are included in this report. 

6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
We look forward to participating in the conference call to be held during September. Knowing what other states are working on might improve the final outcomes of this project.  
7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.  



