## Arizona 6.10.16
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes ( What is the reach and impact of these activities? How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics)
1. One Health Social Media Messaging | Blog shared by ADHS Director on One Health on 3/16/16 (see attached) | Addressed objective 1. Blog shared through facebook and on ADHS website. Reach was estimated to be ~72 unique individuals.
| 10 social media posts shared on outdoor prevention efforts for mosquito-borne and zoonotic diseases | Addressed objectives 1, 2, 3, and 4
Meeting scheduled with Bureau chief to develop schedule for One Health social media and blog posts
| Drafted 25 social media messages and one blog post on importance of handwashing when interacting with animals | Addresses objectives 1, 2, 3, and 4
2. One Health Camp/One Health Exploration Day (OHED) | Conference call on 4/19/16 with project partners to plan and discuss grant activities | Brainstormed agenda and disease scenario topics for One Health Exploration Day with collaborating agencies. Addresses objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth
| Hired project coordinator to overseeand assist with grant activities | Project coordinator is responsible for keeping deliverables on track, facilitating planning and coordination of One Health Exploration Day, as well as dvelopment of materials required for promoting and implementing One Health activities in Arizona
| Agenda (working draft) developed for One Health Exploration Day (to be held August 16, 2016) | See attached
| Meeting between project lead (Hayley) and project coordinator on 5/10/16 | Coordinate efficient planning
| Key partners to participate in One Health Exploration Day identified | Addressed objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth
| Invitation to partners identified to attend and present at One Health Exploration Day | Addressed objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth. Activity modules for One Health Exploration Day requested from collaborating agencies by June 20th.
| Developed and disseminated One Health Logo Contest and One Health Fact Sheet | Addresses objective 1, 2, 3, and 4. Logo contest will build interest in One Health and encourage participation of target age group (~7-17 years) in activity to help "brand" One Health for Arizona. One-page fact sheet on One Health accompanies the logo contest and will be widely distributed at public education events. Fact sheet will increase awareness and knowledge of One Health (including careers in human and animal health), motivate participants to adopt behavior that can help prevent zoonotic disease transmission, and facilitate understanding among youth about roles of Arizona professionals in One Health
| Discussed One Health Exploration Day with animal, public, and environmental health partners in Arizona on 4/4, 5/9, and 6/6 | Addressed objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth
3. Other | Reviewed toolkit developed in 2014 for animal vendors at agricultural fairs (state/county) and youth events | Impact is to enhance awareness of zoonotic disease transmission mechanisms and understand preventive measures that can be taken at various public settings.
| Planning 10-year data analysis review and report development for enteric illnesses with animal exposures | Addresses objectives 1, 2, 3, 4, and 5. In progress, to begin June 20th.
Participated on CSTE/CDC Kick-off call with other recipient states for Influenza Education among Youth in Agriculture Project
| Developed mission statement for One Health in Arizona | See attached draft

## Arizona 9.6.16
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes ( What is the reach and impact of these activities? How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics)
1. One Health Social Media Messaging | Blog shared by ADHS Director on One Health Event on 8/24/16 (see attached) | Addressed objective 1. Blog shared through facebook and on ADHS website. Reach was estimated to be 100+ unique individuals.
| 10 social media posts shared on outdoor prevention efforts for mosquito-borne and zoonotic diseases | Addressed objectives 1, 2, 3, and 4
| In the process of developing content for One Health website | In progress
| Social media messages scheduled to run every other week on One Health, zoonotic disease prevention, food safety, and importance of handwashing when interacting with animals | Addresses objectives 1, 2, 3, and 4
2. One Health Career Exploration Day (OHCED) | Conference call on 7/11/16 and 8/8/17 with project partners to plan and discuss grant activities | Finalized agenda and disease scenario topics for One Health Exploration Day with collaborating agencies. Addresses objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth
| Hosted One Health Career Exploration Day, included finalizing all materials for booklet and presentations | Addressed multiple objectives, all materials attached. Addressed objective 5. Building collaborations with various federal, state and local agencies working in One Health and developing mechanisms to conduct outreach to Arizona youth
| Developed and disseminated One Health Fact Sheet | Addresses objective 1, 2, 3, and 4. Logo contest will build interest in One Health and encourage participation of target age group (~7-17 years) in activity to help "brand" One Health for Arizona. One-page fact sheet on One Health accompanies the logo contest and will be widely distributed at public education events. Fact sheet will increase awareness and knowledge of One Health (including careers in human and animal health), motivate participants to adopt behavior that can help prevent zoonotic disease transmission, and facilitate understanding among youth about roles of Arizona professionals in One Health
3. Other | Disseminated revised toolkit for animal vendors at agricultural fairs (state/county) and youth events. | Impact is to enhance awareness of zoonotic disease transmission mechanisms and understand preventive measures that can be taken at various public settings.
| 5-year data analysis review and report compiled for Salmonellosis infections with animal exposures, final review pending | Addresses objectives 1, 2, 3, 4, and 5. In progress, to begin June 20th.
Hosted 2-hour One Health Capacity Building conference call with partners in Arizona on August 15
| Developed mission statement for One Health in Arizona | See attached draft