Influenza Education among Youth in Agriculture

Progress Report

Please return completed Progress Report to CSTE at mschroeder@cste.org.

- Identify your top three achievements over the last quarter.

  - Successfully hosted One Health Career Exploration Day on August 16th for 45 high school students in Arizona.

  - Compiled booklet of educational and interactive activities with supplemental materials for One Health Career Exploration Day.

  - Wide distribution of One Health fact sheet to high schools around Arizona, 4H, FFA, and youth agriculture partners.

- Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)

Many remained the same…

- Arizona Department of Health Services: main leader for project activities, coordinating and developing structure and objectives for One Health Career Exploration Day and One Health outreach in Arizona. Identification and bringing together of key partners for One Health and zoonoses prevention and response are conducted by ADHS. Social media messaging created by ADHS and sent through ADHS housed platforms (Facebook, website, director’s blog). Completed planning for One Health Career Exploration Day and hosted event on August 16th. Colleagues from Enteric Disease Team and Office of Environmental Health participated in a larger capacity on the execution of One Health Career Exploration Day.

- Maricopa County Department of Public Health: secondary lead for project activities and plays large role in developing and implementing outreach objectives for One Health message. Assisted with activity for One Health Career Exploration Day and participated in statewide One Health Capacity Discussion.

- Arizona Department of Agriculture: participatory role in project activity development and outreach. Assisted with activity for One Health Career Exploration Day and participated in statewide One Health Capacity Discussion. –

- Arizona Game and Fish Department: participatory role in project activity development and outreach.

- USDA Wildlife Services: participatory role in project activity development and outreach. Assisted with activity for One Health Career Exploration Day and participated in statewide One Health Capacity Discussion.

- Midwestern University College of Veterinary Medicine: assisted with activity for One Health Career Exploration Day and participated in statewide One Health Capacity Discussion.

- University of Arizona: colleagues from school of public health and epidemiology participated in statewide One Health Capacity discussion and expressed interest as future collaborator for project/grant.

- Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.

- Our key challenges were 1) time to develop all necessary materials for the One Health Career Exploration Day, particularly because we lost the veterinary student who was acting as project coordinator and 2) maintain high number of participants for One Health Career Exploration Day, due to a school cancelling last minutes because of transportation issues.

- Please include an updated project timeline (see below, only included relevant components).

Ongoing throughout Grant Period

- Key partners from Arizona Department of Health Services, Arizona Department of Agriculture, Arizona Game and Fish Department, Maricopa County Department of Public Health, Midwestern University College of Veterinary Medicine meet on a monthly basis via teleconference to plan deliverables throughout grant period.

- Social media or blog posts (once a month) for One Health and zoonotic disease awareness and prevention

June - August 2016

- Disseminated One Health Fact Sheet to schools and youth programs

- Ordered supplies for One Health Career Exploration Day (August 16th), including keychains with Zoonotic disease prevention slogans

- Completed activity booklet, modules, and presentations for One Health Career Exploration Day

- Developed One Health Logo for Arizona’s Initiatives

August 15 & 16 2016

- Hosted One Health Capacity Building conference call with Arizona partners (Arizona Department of Health Services, Arizona Department of Agriculture, Arizona Game and Fish Department, Maricopa County Department of Public Health, Midwestern University College of Veterinary Medicine, University of Arizona)

- Hosted One Health Career Exploration Day

September 2016

- Complete analysis of evaluations from One Health Career Exploration Day and compile report to share with key partners

- Host a hot wash with planners and facilitators for One Health Career Exploration Day

- Draft content for and launch Arizona One Health website

October - December 2016

- Attend Arizona State Fair Public Safety Days and distribute One Health materials

- Veterinary student will be interning for 4 weeks and will be tasked with developing One Health training module to be shared online with activities and curriculum for youth

- Create guidelines for One Health poster contest how to be “SAFE” around animals, announce and host

- Coordinate meeting with leadership from youth agriculture and science/health/animal groups to plan for sustainability (will rely on AZ Department of Agriculture for assistance)

- If you have materials you are already distributing, please include a sample PDF or link of those materials.

Attached.

Supplemental items include One Health Fact Sheet and materials from One Health Career Exploration Day.

- Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.

Arizona does not require additional assistance at this time. We enjoyed the site visit by Emily and Monica in August and felt it very beneficial to have you participate in the conference call for One Health Capacity Building. Identifying potential slide sets for One Health concepts with or without CE attached for an array of audiences would be very beneficial.

- Please complete the attached spreadsheet, to indicate progress made towards project deliverables.

Attached.