## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes (How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics))
1. Develop educational sessions for: 4-H Exploration Days & 4-H Animal and Veterinary Science Camp at Michigan State University | Educational sessions have been taught at both 4-H Exploration Days and 4-H Animal and Veterinary Science Camp. MDHHS ran the educational session at 4-H Exploration Days. | 1. The educational sessions focused on teaching participants about general zoonotic knowledge including transmission and prevention. 2. Discussion of ways to prevent zoonotic disease and agencies that are crucial to monitoring zoonotic disease. 3. During the educational sessions the discussion around One Health helps participants to discover their role in zoonotic disease prevention. 4. Participants get to discuss the impact of zoonotic disease first hand through interactive case studies. 5. The MDHHS has created the curriculum and taught an educational session at 4-H Exploration Days.
2. Develop and conduct regional presentations in each of MSU Extension districts | We are currently conducting the Youth Zoonotic Disease Prevention Presentations around the State of Michigan. At the moment we have given 36 presentations in all 14 regions. Presentations were given at a wide variety of events to ensure that we are reaching a vast audience. Two more presentations are already scheduled to take place later in the year. | 1. The presentations focus on teaching participants about general zoonotic knowledge including transmission and prevention. 2. Through discussion of ways to prevent zoonotic disease and agencies that are crucial to monitoring zoonotic disease. 3. During the presentations the discussion around One Health helps participants to discover their role in zoonotic disease prevention. 4. Participants get to discuss the impact of zoonotic disease first hand through interactive case studies and also take home a Pathogen Prevention Package which has the supplies necessary for them to implement the skills discussed during the session. 5.The presentation specifically discusses various agencies and their rolls in preventing zoonosis. Additionally one of the case studies features a reportable disease which re-enforces the importance of having a strong relationship with local agencies.
4. Educate 4-H leaders and program coordinators | At each of our events there is a mix of 4-H leaders and program coordinators who have the opportunity to engage in our presentations. Additionally, through networking with 4-H leaders and program coordinators to set up the presentations we are increasing their zoonotic disease awareness; we provide them with valuable information that can be utilized to promote our events. | 1. The presentations focus on teaching participants about general zoonotic knowledge including transmission and prevention. 2. Through discussion of ways to prevent zoonotic disease and agencies that are crucial to monitoring zoonotic disease. 3. During the presentations the discussion around One Health helps participants to discover their role in zoonotic disease prevention. 4. Participants not only get to discuss the impact of zoonotic disease first hand through interactive case studies but they also take home a Pathogen Prevention Package which has the supplies necessary for them to implement the skills discussed during the session. 5.The presentation specifically discusses various agencies and their rolls in preventing zoonosis. Additionally one of the case studies features a reportable disease which re-enforces the importance of having a strong relationship with local agencies.
5. Develop new “Animal Science Anywhere” Curricula | Three new lesson plans have been developed: one lesson focusing on how the influenza virus mutates, one about careers in human and animal health, and one about the One Health initiative. The lesson plans are at the editor for final refinement. | 1. The curriculum features a lesson specifically about influenza, which focuses on influenza's role as a zoonotic pathogen. Additionally, the One Health lesson focuses on the tie between human and animal medicine, which discusses zoonosis. 2. One of the lessons focuses on careers in human and animal health. 3. All three lessons focus on the participants role in zoonotic diseases but primarily the influenza and One Health lessons focus on the preventative measures that participants can implement to reduce the impact of zoonosis with their own animals. 4. Each lesson provides a take home message, which focuses on motivating participants to utilize the techniques discussed in the lessons in their own lives. 5. Particularly the careers lesson work to strengthen the relationship between participants and agencies that work in human and animal health.
6. Design and develop additional educational materials/signage for zoonotic disease prevention | The pull up banners have been completed and were distributed to the districts in Michigan. The 11 by 17 signs are in the process of being printed. | 1. The signs are designed to motivate participants to utilize preventative measures in their own lives, from washing their hands to wearing the proper PPE the signs are improving community and participant knowledge about how to prevent zoonosis.