Influenza Education among Youth in Agriculture
Progress Report Two - Michigan

Please return completed Progress Report to CSTE at mschroeder@cste.org.  

1. Identify your top three achievements over the last quarter. 
· Directed through editing process three new Animal Science Anywhere lesson plans. Lessons currently at printers.
· Conducted a total of 36 Zoonotic Disease Prevention Presentations in all 14 of Michigan’s 4H Districts as well as presentations at 4-H Exploration Days and 4-H Animal and Veterinary Science Camp at Michigan State University
· Created and worked through the MSU ANR communications department “Biosecurity 1,2,3” signage to have in exhibition facilities. See attached File. Sign currently at printers.

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)
· Michigan State University (MSU) Extension and Michigan 4-H: 
· One staff member and two recent MSU alumni conducted programming and curriculum development throughout the quarter. 
· Edited three lesson plans focusing on careers in human and animal health, how influenza virus mutates, and the One Health initiative.
· Critiqued Youth Zoonotic Disease Prevention Presentations.
· Continued to provide promotional materials to counties to advertise the Youth Zoonotic Disease Prevention Presentations. 
· Designed the 11x17 sign that describes how to practice biosecurity when returning from a fair or animal exhibition event. Pushed through editing and now at printer.
· Worked with companies to arrange for estimates to fulfill printing needs and lesson plan supplies.
· Purchased needed supplies to make the 2,000 Zoonotic Disease Prevention Kits. Items purchased include the following per kit:
· Cardboard box
· Label on lid of box
· 3 bottles of water
· 4 cups
· 1 bag with 3 color fizzers
· 1 beach ball
· Pack of 52 Health Cards
· Influenza Message green cards (5 cards shrink wrapped)
· Distributed 14 pull-up banners to each 4H District Office.
· Conducted the third annual Michigan 4-H Animal and Veterinary Science Camp.
· Served as the point person on distributing expenses.
· Assisted in response to Swine Influenza cases in swine and humans.
· Michigan Department of Health and Human Services (MDHHS): 
· Grant PI/ Overall Coordination
· Reviewed and helped final all materials produced by MSUE. 
· Designed curriculum and presented day and a half session  at 4-H Exploration Days .
· Handled all award financial matters.
· Coordinated public health response to variant Swine Influenza cases in swine and humans at 3 different county fairs in Michigan, summer 2016.
· Hosted site visit with CDC Influenza staff involved in this project, Jun 26-27, 2016.
· MSU Agriculture and Natural Resources (ANR) Communications: 
· Editor: edited lesson plan content for three lesson and the 11x17 sign.
· Graphic designer: created the pull-up banner, 11x17 sign and the three lessons.
· Center for Disease Control and Prevention:
· Presentation at the 2016 MI 4-H Animal and Veterinary Science Camp (during their site visit to Michigan).
· Neogen Corporation: 
· Donation of over 200 additional gloves for the Pathogen Prevention Packets that are handed out to the youth at each presentation.
· Sam’s Club: 
· Donation of $25 towards supplies that will be placed in the Zoonotic Educational Kits that will be distributed this October.

3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
· Scheduling: it continued to be difficult to coordinate schedules for the presentations. Most counties already have events planned for the summer. If the grant would have been awarded earlier, this would have better fit the educational timeframe most counties are holding events.
· Existing knowledge: Both youth and adults have a limited knowledge base about zoonotic diseases.  Therefore, many counties’ adult leaders found it difficult to motivate youth to attend these events because they do not understand the relationship between human and animal health, themselves. 

4. Please include an updated project timeline.
· Timeline listed below indicates items that have changes in red.
	August 2016:
	Design and created 11x17 barn signage (replaced table top displays)

	September-October 2016:
	Compile 2,000 zoonotic packages with supplies for lessons

	October 25-26, 2016:
	Distribute Zoonotic Disease Prevention Packages to leaders 

	January 12-14, 2017:
	Distribute 11x17 signage to Michigan Association of Fairs members *No charge to grant



5. If you have materials you are already distributing, please include a sample PDF or link of those materials. 
· [bookmark: _GoBack]11x17 Biosecurity sign 1,2,3 - attached

6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
· Thank you to the staff members at CDC that were willing to review the lesson plans. That was very helpful to have a person at the CDC that was willing to review content of created curriculum. This would ensure a unified national message while taking some stress off of grantees.
· Offer the grant in the fall to better meet 4-H staff and leader schedules.
· Consider allowing the grant to go to two sites – example MDHHS and MSU Extension to avoid additional paperwork for staff.
· Increase the notification timeline so that progress can begin more rapidly on grant objectives based on a December deadline.
7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.
· Please see attached file.
