## Sheet1
Please describe the progress made towards completion of the following project deliverables. | Outputs (What activities have happened over the past 3 months? What materials have been developed or produced as a result?) | Outcomes (How have these activities addressed one or more of the project objectives? 1. Improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention, 2. Increase participant awareness and knowledge of careers in public and animal health, 3. Facilitate a better understanding among participants of the role public and animal health play in disease prevention, 4. Motivate participants to adopt behavior that can help prevent zoonotic disease transmission, 5. Develop relationships among stakeholders that could be used to facilitate more effective and efficient responses to important public and animal health issues (e.g., the response to infectious disease outbreaks or epidemics))
1. Conduct tabletop exercises/trainings at Ohio 4-H Conference and OSU Junior Swine Day | Completed during first quarter of project | Training materials improve participant awareness and knowledge of zoonotic diseases and encourage youth to adopt behavior to help prevent disease transmission by defining zoonotic diseases; demonstrating disease spread using a glittered pig; describing IAV in pigs and people; defining biosecurity allowing students to give examples; initiating discuss among participants through group activities; and providing 'what to do' before, during, and after agricultural exhibitions to minimize risk of disease transmission.
2. Social Media Campaign | Five social media messages, related to the information covered in onsite training modules, have been developed for both Facebook and Twitter. Messages have been posted from the Ohio 4-H animal science account each day, Monday - Friday, the week before each individual Ohio fair starts on their respective pages. The last message with be posted October 3-7, 2016. | The goal of these messages, once disseminated, is to improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention; and to motivate participants to adopt behavior that can help prevent zoonotic disease transmission,
3. Development of zoonotic disease educational curriculum for youth in agricultural education programs | Coordination among partners has resulted in an outline for the project book and skill-a-thon cirriculum. Draft materials are being edited by collaborators. | Materials are being written to improve participant awareness and knowledge of zoonotic diseases, including zoonotic disease transmission and prevention; increase participant awareness and knowledge of careers in public and animal health; facilitate a better understanding among participants of the role public and animal health play in disease prevention; and to motivate participants to adopt behavior that can help prevent zoonotic disease transmission.