Influenza Education among Youth in Agriculture
Progress Report 


Please return completed Progress Report to CSTE at mschroeder@cste.org.  


1. Identify your top three achievements over the last quarter. 
a. Conducted on-going surveillance in exhibition swine to estimate the prevalence of IAVs circulating in this unique animal-human interface.
b. Delivered messages via social media the week prior to each Ohio county’s fair.
c. Created outlines for a project book chapter and skill-thon station to submit to collaborators for feedback

2. Please list collaborators on this quarter’s achievements, and briefly describe roles of different organizations involved (i.e. 4H, State PH, State Animal Health)

Ohio Department of Health:  Provided support and expertise for all other partners.

Ohio 4-H Youth Development: Enabled access to state 4-H Animal Science social media venues; collaborated with AIEERP to develop an outline for writing project book chapter and skill-a-thon station.

Department of Agricultural Communication, Education, and Leadership: Coordinated with 4-H to set up social media pages; delivered message via social media the week prior to each Ohio county’s fair; began data collection for quantitating social media effectiveness using SYSOMOS software.

Animal Influenza Ecology and Epidemiology Research Program: Coordinated with 4-H to develop an outline for skill-a-thon and project book chapter; provided content to ACEL to create social media messages; Conducted on-going surveillance in exhibition swine to estimate the prevalence of IAVs circulating in this unique animal-human interface .


3. Please describe any areas of concern or challenges to meeting the objectives or providing deliverables.
Presently, no concerns or challenges to meeting objectives are anticipated. We have progressed according to the proposed timeline and all collaborators and stakeholders have been supportive.



4. Please include an updated project timeline.

  Feb-16	        Apr-16        Jun-16         Aug-16       Oct-16            Dec-16
































					

  Present education at state wide youth meetings


            Develop social media campaign

                         Implement social media campaign 

                Analyze Sysomos MAP data

        Develop content for zoonotic disease chapter

   Format, revise, edit zoonotic disease chapter 

                                          Develop skillathon station

   Present education materials to Extension Educators



5. If you have materials you are already distributing, please include a sample PDF or link of those materials. 
N/A                                        Develop skillathon station


6. Please list any suggestions for CSTE and CDC for how we can help best facilitate your progress.
N/A

7. Please complete the attached spreadsheet, to indicate progress made towards project deliverables.  
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