## Slide 1: NBS MMG Implementation Process Milestones
01 Initial NUG Call
08 Production Cutover
02 Develop/ Implement Page
03 Data Porting/ Migration
04 HL7 Message Created
05 Internal Validation
06 Full Cycle Validation
07.1-2 Structural Validation with MVPS
07.3-4 Program Validation
Primary Owner of Process
Red = CDC
Blue = TA Team
Notes: And here it is! This is our flowchart. Health departments follow this process to reach our goal of sending case notifications to CDC (or production cutover, in IT speak). Note that this is a sequential process with discrete steps making it especially useful for our purpose.

## Slide 2: NBS MMG Implementation Process Milestones
01 Initial NUG Call
08 Production Cutover
02 Develop/ Implement Page
03 Data Porting/ Migration
04 HL7 Message Created
05 Internal Validation
06 Full Cycle Validation
07.1-2 Structural Validation with MVPS
07.3-4 Program Validation
Primary Owner of Process
Red = CDC
Blue = TA Team (APHL was not involved in NBS TA)
Stage
Yellow = Pre-onboarding
Green = Onboarding
Gray = Cutover to production
Notes: And here it is! This is our flowchart. Health departments follow this process to reach our goal of sending case notifications to CDC (or production cutover, in IT speak). Note that this is a sequential process with discrete steps making it especially useful for our purpose.

## Slide 3: NBS MMG Implementation Processes: High-level steps
Pre-Onboarding (Phase 1)
Onboarding (Phase 2)
  Test Messaging
  Limited Production Messaging
Cutover to Production (Phase 3)
  Year to Date Messaging
Production (Phase 4)
  Production Messaging

## Slide 4: NBS MMG Implementation Processes: Phase 1:Pre-onboarding
Condition code library updates
Page Implementation
METS/MQF Validation
Data Porting
NEDSS.PROPERTIES Updates
SAMS/MVPS Dashboard
State-Specific NBS Application OIDs for Each NBS Environment
Other Pre-Onboarding Considerations

## Slide 5: NBS MMG Implementation Processes Phase 2: Onboarding
Test Messaging Activities
  Implementation Spreadsheet
  Test Case Scenarios
  Test Message Validation in METS (MQF, if Arbo)
  Notify CDC
  CDC Onboarding Kickoff Call
  Send Test Messages to Production PHIN MS Server
Send Limited Production Messages

## Slide 6: NBS MMG Implementation Processes: Phase 3: Cutover to Production
Year to date Legacy & HL7 messaging

## Slide 7: NBS MMG Implementation Processes Phase 4: Production Messaging
Send production messages