Objective 1. By June 2019, provide leadership and support for cross jurisdictional coordination of the implementation of the ISW9 report entitled “The Transition from ICD-9-CM to ICD-10-CM: Guidance for analysis and reporting of injuries by mechanism and intent ” on early releases of ICD-10-CM coded hospitalization and emergency department discharge data.

Activities:

CSTE will:

- Using CSTE's subcommittee and steering committee structures, develop an Injury workgroup addressing ICD-10-CM transition issues, such as external cause matrix application which would be the precursor to indicator case definitions.

- Host at least one workgroup meeting with 10 or more topic-specific STLT participants to develop foundation documents and timelines for workgroup activities

- Develop written summaries of the topic specific workgroup meetings and activities.

- Develop and publish a summary of findings from state testings and use of the data to standardize guidance for the proposed external cause matrix and the diagnosis matrix

- Support state participation in a 2018 Workshop to be held in conjunction with the CSTE Annual Conference.

Objective 2. By June 2019, CSTE will continue workgroup activities to develop a report on the proposed ICD-10-CM Injury summary of findings.

Activities:

CSTE will:

- Secure the expert technical input necessary to convene a workgroup of 10 or more members of

the cross-jurisdictional ICD-10-CM Subcommittee as well as representation from NCIPC and

NCHS to review the findings from the cross jurisdictional implementation and testing of the

Proposed ICD-10-CM Injury Case Definition and Analysis Frameworks.

- Hosts workgroup teleconferences as needed and at least one in-person meeting in Atlanta, GA.

- Develop a written technical summary of findings to serve as a basis for NCIPC and NCHS

decision making prior to the development a summary of findings for the ICD-10-CM Injury Case

Definition and Analysis Frameworks

- Coordinate application by local and state epidemiologists of the proposed drug poisoning-related indicators developed by CSTE and the CDC/Prevention for States (PfS) Program, including a comparison summary of cross-jurisdictional results.