ATTACHMENT I to GENERAL CONTRACT AGREEMENT

- Name: Nancy Binkin

- Method of Selection: Competitive Bid

- Period of Performance: May 4, 2018-June 30, 2018

Nancy Binkin will receive a total amount of $15,000.00 for the period of May 4, 2018 through June 30, 2018 for the completion of all deliverables per the payment schedule described in the general contract agreement. The funding award is contingent upon satisfactory compliance with the scope of work and available funds.

- Scope of Work

Nancy Binkin will work with CSTE and stakeholders to build on the current findings of the CSTE Marijuana Surveillance Environmental Scan Analysis Report and write recommendations for developing “best practices” in marijuana surveillance.

Objectives

- Build on the current findings of the environmental scan results, conduct additional analysis and follow-up (via key informant interviews with all 4 early adopter states [WA, CO, AK, OR], and at least 3 recent adopter states).

- Develop a comprehensive report on state-level data collection activities, surveillance capacity and gaps/needs related to marijuana use and impact.

- Describe the content of surveillance or data reports that have been provided by the 7 states (4 early adopter states and 3 of the recent adopter states).

4.   Investigate perceptions of how effectively surveillance has been used to inform

public policy or public health practice.

- Identify examples of how surveillance or other marijuana data collection has been used in the past, or currently, to inform specific policy decisions or program planning.

- Identify examples of how surveillance or data collection is planned to inform future policy decisions (e.g., descriptions of required reports to policymakers, and how that information will be applied to policymaking or program design).

- Summarize strengths, weaknesses, and lessons learned by states regarding marijuana-related surveillance or other data collection.

- Provide recommendations to address marijuana-related data gaps and needs.

Deliverables:

      - Participate in calls with CSTE as needed.

      - Review marijuana environmental scan analysis and collaborate with CSTE to develop further analysis questions/goals and a workplan for implementation.

      - Develop an evaluation assessment to address key objectives.

  - Describe clear project objectives for further assessing surveillance capacity and activities.

  - Describe a protocol for collecting information to meet project objectives (including identification of respondents, outreach, and collection of data)

  - Develop a key informant interview guide or other data collection instrument

  - Create an analytic plan for synthesis of findings.

      - Conduct key informant interviews with 7 of the  legalized states (all 4 early adopter states [WA, CO, AK, OR], and at least 3 recent adopter states).

      - Develop comprehensive report summarizing findings and highlight key trends in state public health surveillance of marijuana; and provide recommendations for future priorities.

      - Present the outcomes to CSTE and identified stakeholders via webinar or conference call.

| Activity | Deliverables | Due Date |
| --- | --- | --- |
| Project Development: - Review CSTE Marijuana Subcommittee Environmental Scan and results - Collaborate with CSTE to develop analysis strategy/goals and finalize workplan - Develop objectives, protocol, interview guide, and analytic plan for synthesis of findings | - Written workplan including interview protocol,question guide, and analysis strategy. | 06/01/18 |
| Implementation: - Conduct and code key informant interviews with the 7 states (4 early adopter states, and 3 recent adopter states) | - Share a written summary of the preliminary analyses from the key informant interviews. | 06/30/18 |
| Analysis: - Complete additional analyses - Develop comprehensive report | Submit the final project report to include a findings summary, highlight the key trends in state public health marijuana surveillance; and recommendations for future marijuana surveillance priorities and practices. | 06/30/18 |
| Dissemination: - Participate in a webinar or conference call for CSTE members to present outcomes. | Partner with CSTE to coordinate a webinar to share the final outcomes of the final report with stakeholders. | 07/18/18 |

Budget

The budget for this study will consist exclusively of personnel time at $100/hour, which is the rate that both Drs. Binkin and Hurst receive for their consulting activities. Dr. Hurst is a project scientist that Nancy had identified to conducting the qualitative data analysis portion of the report. Because they are serving as private contractors, there are no indirect costs. The total budget of $15,000.00, organized by deliverables and staff person-hours, is provided below:

- CSTE Responsibilities:

During the established project period, CSTE will:

- Serve as the Seller’s principle point of contact.

- Facilitate work and provide avenues for communication between Seller and stakeholders

- Monitor the terms of the contract agreement

- Provide payment according to the terms of the contract agreement.

- Seller Responsibilities:

During the established project period, Seller will:

- Accomplish the objectives and deliverables listed in this Statement of Work.

- Provide invoices to CSTE as required in the contract agreement

- Be available through multiple avenues for feedback and discussion (conference calls, email, etc.) on a regular basis or as needed.

- Methods of Accountability:

- During the established project period, Seller will:

- Accomplish the objectives and deliverables listed in this Statement of Work.

- Provide invoices to CSTE as required in the contract agreement

- Be available through multiple avenues for feedback and discussion (conference calls, email, etc.) on a regular basis or as needed.

- A final invoice will be required upon the completion of all project deliverables, within 30 days of the contract end date.