## Slide 1: Syndromic Surveillance Subgroup Kick Off Call
February 20, 2020

## Slide 2: Agenda
Review of Purpose
Proposed Timeline
Expectations and Chair Selection
Next steps

## Slide 3: EOI Steering Committee Steering Committee Chair: Melissa Jordan (FL)
Environmental Health
CSTE Staff: Alesha Thompson
Occupational Health
CSTE Staff: Song Xue
Injury
CSTE Staff: Danielle Boyd, Mia Israel, Cailyn Lingwall
Injury Surveillance Workgroup
(Monthly calls)
Special Emphasis Reports Subgroup
Syndromic Surveillance Subgroup
TBI
Suicide
MVT
ACEs
OD2A Workgroups (TBD)
Suicide/Int Self Harm
Sexual violence/assault
E-scooter injury
EVALI

## Slide 4: Purpose of Syndromic Surveillance Subgroup
To introduce injury epidemiologists to SyS and how it applies to and benefits their work
To provide a space for members to engage in SyS projects of interest with a peer learning component
Brief overview of activities in other CDC SyS workgroups (Pedro)

## Slide 5: Proposed Timeline
2/20/2020 | Kick-off call and identify workgroup member chairs by topic area
2/28/2020 | - Delineate roles within subgroup - Topic area chairs email Mia, Kristen, and Kristina schedule of subgroup calls and any scheduling/call line needs
3/6/2020 | Identify project focus and proposed product
*Topic area specific timelines to be further developed

## Slide 6: Expectations and Chair Selection
Sponsoring/chairing one of the subgroups- involves organizing the subgroup, setting up calls, managing the Basecamp folder, coordinating the decided upon deliverables and any edits, and leading the subgroup in reaching consensus. Time commitment flexible, but more time required than serving as a participant (likely 1 hour per week getting started).
Participating as a member of the subgroups- involves joining calls and communicating regularly via email with the subgroup, participating in drafting and editing the guidance, and working to reach consensus within the subgroup. Time commitment flexible (likely 2-3 hours per month getting started).

## Slide 7: Next Steps
Everyone should have been added to the Basecamp
  Please let us know if you have not received an invitation
Mia/Kristina/Kristen will share group member contact information with chairs
Chairs should communicate to their groups to schedule calls and develop more detailed plans
Notify Mia/Kristina/Kristen of call schedule and any support needs
  We will set up call lines

## Slide 8: Questions?