CSTE Injury Surveillance Workgroup

Syndromic Surveillance Guidance Drafting Timeline

Document Purpose: To provide guidance for injury epidemiologists on framing syndromic surveillance data (limitation of data source, data quality considerations, interpretation/difference from typical rates/counts etc.) for stakeholders and the public. See separate document for working draft.

Timeline: This timeline remains flexible!

| Action Item | Timeline/Deadline | Responsible Party |
| --- | --- | --- |
| Discuss and finalize document purpose; draft TOC | April 27 | All members on call |
| Determine subgroup call frequency and schedule | April 27 | Mia to send recurring calendar invitation, 4th Mondays at 2pm ET; May call will be rescheduled due to Memorial Day |
| Comment on Start Here resources outline | Deadline: 12pm ET May 26 | All subgroup members |
| Check-in on drafting/thoughts/ideas | May 26 | All subgroup members on call |
| Develop rough draft of guidance | Deadline: 12pm ET June 19 | Members to sign up for sections |
| Discuss sections | June 22 | All subgroup members on call |
| Review/comment period | June 22 – July 10 | All subgroup members |
| Revise sections | July 10 – July 24 | Members to sign up for revisions |
| Discuss v2 edits | July 27 | All subgroup members on call |
| Finalize v2 for review | July 27 – August 7 | Members to sign up for revisions |
| Share for review | August 10 – August 24 | WG membership, CDC SMEs, CSTE SyS staff |
| Publish to CSTE toolkit | September 7 | CSTE |