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CSTE Injury Surveillance Workgroup
Syndromic Surveillance Guidance Drafting Timeline

Document Purpose: To provide guidance for injury epidemiologists on framing syndromic surveillance data (limitation of data source, data quality considerations, interpretation/difference from typical rates/counts etc.) for stakeholders and the public. See separate document for working draft. 
Timeline: This timeline remains flexible! 
	Action Item
	Timeline/Deadline
	Responsible Party

	Discuss and finalize document purpose; draft TOC
	April 27
	All members on call

	Determine subgroup call frequency and schedule
	April 27
	Mia to send recurring calendar invitation, 4th Mondays at 2pm ET; May call will be rescheduled due to Memorial Day


	Comment on Start Here resources outline

	Deadline: 12pm ET May 26 
	All subgroup members

	Check-in on drafting/thoughts/ideas
	May 26


	All subgroup members on call

	Develop rough draft of guidance
	Deadline: 12pm ET June 19
	Members to sign up for sections


	Discuss sections
	June 22
	All  subgroup members on call


	Review/comment period
	June 22 – July 10
	All subgroup members


	Revise sections
	July 10 – July 24
	Members to sign up for revisions


	Discuss v2 edits
	July 27 
	All subgroup members on call


	Finalize v2 for review
	July 27 – August 7
	Members to sign up for revisions


	Share for review
	August 10 – August 24
	WG membership, CDC SMEs, CSTE SyS staff


	Publish to CSTE toolkit
	September 7 
	CSTE
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