## ProjectSchedule
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Animal and Zoonotic Influenza Reference Guide | Project Start: | 2021-08-16
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [5 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-08-09 to 2022-08-28
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | START | END | DAYS | time axis 2021-08-09 to 2022-08-28
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Virtual meeting and greet with CSTE and CDC | Dr. Schaeffer, CSTE, CDC | 2021-08-16 | 2021-08-16 | 1
| Review current literature, guidance, templates and tools | Dr. Schaeffer | 2021-08-16 | 2021-10-29
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Schedule and hold key informant interviews | Dr. Schaeffer, Key Informants | 2021-08-16 | 2021-09-17 | 33
| Review and categorize literature, text, and other sources | Dr. Schaeffer | 2021-09-01 | 2021-10-08
| Submit literature review summary, informant interview findings, and reference guide outline | Dr. Schaeffer | 2021-09-24 | 2021-10-11 | 18
| Receive feedback on literature review, interview findings, and reference guide outline | CSTE, CDC, Zoonotic WG | 2021-10-11 | 2021-10-29
| Draft Section 1 | Dr. Schaeffer, CSTE, CDC | 2021-10-11 | 2021-11-08
| Submit Section 1; solicit feedback | Dr. Schaeffer, CSTE, CDC | 2021-11-12 | 2021-11-12
| Receive feedback on Section 1 | CSTE, CDC, Zoonotic WG | 2021-11-12 | 2021-11-24
| Draft Sections 2 & 3 |  | 2021-11-08 | 2021-12-13
| Submit Section 2 & 3; solicit feedback | Dr. Schaeffer, CSTE, CDC | 2021-12-13 | 2021-12-13
| Receive feedback on Sections 2 & 3 | CSTE, CDC, Zoonotic WG | 2021-12-13 | 2021-12-24
| Complete final draft | Dr. Schaeffer | 2021-12-24 | 2022-01-10
| Solicit final draft feedback | CSTE, CDC, Zoonotic WG | 2022-01-10 | 2021-01-28
| Submit final reference guide, webinar materials and deliver webinar | Dr. Schaeffer | 2022-02-14 | 2022-02-14
This is an empty row