## ELR Assessment
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
Planning 1.0
1.1.0 | Obtain executive sponsorship (champion) | [5 empty] | X |  |  | Project champion - this role may differ from jurisdiction to jurisdiction and may be more than one single sponsor / champion.
1.1.1 |  | Define State Law/Regulation/Policy approach for ELR |  |  | one time | IT State Lab NEDSS / ELR Coordinator Epidemiologist Informaticist Outside PH partners | X |  | State and jurisdictional laws and / or regulations | Define, document and obtain necessary approval, sign-off for laws, regulations, and policy for implementation and maintenance of ELR.
1.1.2 |  | Define Business Need |  |  | one time | NEDSS / ELR Coordinator Epidemiologist Informaticist | X |  | Project scope and business justification for ELR | Include high level alternatives analysis and feasibility study, define ROI, describe stakeholders, conduct cost benefits analysis, identify issues and risks and constraints.
1.1.3 |  | Assessing Current Status |  |  | one time | IT State Lab & other labs NEDSS / ELR Coordinator Epidemiologist Informaticist Outside PH partners | X |  | Document of current status and background | Analyze and review the current system to determine if system performance (data flow, reporting, alerting, hardware and software systems) are performing as expected and results are as expected. This step is intended to describe the current state of the "system", either paper or electronic, and address gaps.
1.1.4 |  | Assess Current Business Need |  |  | one time | IT State Lab NEDSS / ELR Coordinator Epidemiologist Informaticist Outside PH partners | X |  | Document of current business need | Based on on programmatic needs determine what is required to address these needs. This includes an understanding of where trading partners are in their capability.
1.1.5 |  | Define Programmatic and IT System Scope |  |  | one time | IT State Lab NEDSS / ELR Coordinator Epidemiologist Informaticist | X |  | Detailed Programmatic and IT business scope | Describe the scope of the entire ELR System including the data flow from trading partners, data routing to surveillance systems. Include planning to manage process and paradigm change. This is a programmatic scope.
1.1.6 |  | Identify and Secure Funding Sources |  |  | on going | State Lab NEDSS / ELR Coordinator State Epidemilogist / Epi Progam Management | X |  | Detailed summary of all available funding sources | Identify and secure financial support to execute scope and objectives. Investigate and include all potential funding sources , grants and programs.
1.1.7 |  | Project Charter |  |  | One time | NEDSS / ELR Coordinator Informaticist | X |  | Project Charter | Includes business need, alternative analysis, change management, and resource requirements.
|  | Assessing Current Status |  |  |  | Epidemiologist Program Management IT ELR Coordinator |  |  | redundant - done as part of of operational analysis | Assess current status and determine optimal architecture to support disease surveillance needs
1.2.0 | Update policy and law
1.2.1 |  | Assess and Update legislation, regulation, or policy |  |  | One time | State/Program Epidemiologist NEDSS / ELR Coordinator State Legal Council | X |  | Summary of existing laws, regulation and policy. | Ensure that ELR is actually allowed within the states based on existing laws, regulations and policies. Possibly initiate process to modify or amend existing laws, regulations and policy if necessary to implement ELR.
1.2.1 |  | Define data elements and reconcile data elements from multiple sources |  | Medium | One time | Program Epidemiologists NEDSS / ELR Coordinator, IT |  |  | Reconcile forms. | Reviewing the content of the report forms including the data elements to serve as a basis for fields to be included in an electronic exchange. Paper forms may be used as a back-up, web based entry may still exist for smaller sites
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
1.2.2 |  | Define what to report, who, when, and how |  |  | One time | Program Epidemiologists NEDSS / ELR Coordinator, State legal counsel, IT, PH Lab | X |  | List of what to report, who receives the reported items, and when and how the data are sent to public health. | For each jurisdiction - based on laboratory tests or results determine if this qualifies as a condition to report to public health. This must also factor in reporting requirements and reporting criteria specific to the jurisdiction. (e.g., Hepatitis A IgM positive). Further specificity by public health may indicate when a test result should be received (or sent) within a given time frame.
1.2.3 |  | Create / update MOU or trading partner agreement |  |  | Periodic | Program Epidemiologists NEDSS / ELR Coordinator, State legal counsel, IT |  | X | MOU and / or trading partner agreement. | Create standard template for use in engaging trading partners and specify data transport method
1.3.0 | Define Scope of IT System Development / Enhancements
1.3.1 |  | Engage trading partners |  |  | One time | Epidemiologist Program Management IT, ELR Coordinator | X |  | List of eligible trading partners | Determine the strategy for engaging data trading partners, surveillance programs and IT programs. Determine appropriate strategies for both internal and external data trading partners.
1.3.2 |  | Determine Scope of IT System |  |  | One time | IT (business analyst) NEDSS Coord. Epidemiologist Informaticist ELR Coordinator | X |  | IT system scope | Describe the vision and scope of the systems work that needs to be done. This should include the business justification for the system, high level business requirements and functional requirements and a baseline alternatives analysis which supports the decision to buy or build the IT system.
1.3.3 |  | Build IT Project Plan |  |  | One time | Project manager IT NEDSS / ELR Coordinator Informaticist Epidemiologist | X |  | IT Project Plant | Develop project management plan and other planning documents; Identify required resources for implementation of IT infrastructure to support ELR.
1.3.4 |  | Develop / Update Technical Implementation Guide for Trading Partners |  |  | One Time with periodic updates | IT NEDSS / ELR Coord. Epidemiologist Informaticist | X |  | Technical implementation guide for Trading Partners | Provide guidelines for secure transport, message format, vocabulary usage and required data elements. Clearly identify reporting requirements.
1.3.5 |  | Define continuity of operations |  |  | One Time with periodic updates | Epidemiologist Program Management IT ELR Coordinator Informaticist Trading partners Incident commanders | X |  | Disastor recovery plan | Ensure that ELR is able to continue in the event of loss of key personnel or loss of infrastructure (business continuity), including disaster recovery. Includes disaster recovery and may be part of the overal disastor recovery plan.
1.3.6 |  | Define Surge Capacity Strategy (On-boarding strategy) |  |  |  | Epidemiologist Program Management IT NEDSS / ELR Coordinator PH Management |  | X | Surge capacity / on-boarding strategy | The strategy for supporting a dramatic increase in requests to support ELR due to recent public events or recent policy (e.g., Meaningful Use) and / or to support the increase in number of data trading partners.
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
1.4.0 | Define Training Needs
1.4.1 |  | Assess PH staff training needs and and plan training |  |  |  | Epidemiologist Program Management IT NEDSS / ELR Coordinator Informaticist | X |  | Public Health Staff training needs assessment / training materials | Identify/Assess training for IT personnel, Disease Intervention Specialist, Epidemiologists. "What are the training needs". Include training on standards, vocabulary, new systems being implemented and new information flows.
1.4.2 |  | Design and Develop Trading Partner / Partner Staff training |  |  |  | Epidemiologist Program Management IT NEDSS / ELR Coordinator Infection Control Lab Informaticist | X |  | Trading Partner Training Plan / Materials | Identify/Assess training for Reporters (e.g., Hospital, Lab, and Physician). "What are the training needs". May consist of communications rather than training. Should include orientation or kick-off process / event for trading partners.
1.5.0 | Communications | [5 empty] | X |  | Communications package | This is internal and external communications with trading partners, with program areas, with users about training needs, with trading partners, with leadership. May also be with end users on what to expect - how to read / use the online screen to read, etc.
1.6.0 | Specify Laboratory Reporting Criteria |  |  |  | On going | State/Program Epidemiologist NEDSS / ELR Coord. Informaticist State Lab | X |  | Laboratory Reporting Criteria Document | What tests should be reported for each organism, reference ranges, business rules. May include choosing which LOINC codes are acceptable, identifying specific diseases.
Engage 2.0
2.1.0 | Manage Trading Partners
2.1.1 |  | Identify, assess capability and Prioritize Trading Partners |  |  | On going | State/Program Epidemiologist NEDSS / ELR Coord. Informaticist IT | X |  | Proritized list of trading partners | Identify who the potential trading partners are, their readiness, coverage provided, and willingness to engage. Determine prioritization of trading partners who are ready for ELR and prioritize implementation based on factors such as: geographic coverage, population coverage, existing infrastructure and technology capability
2.1.2 |  | Establish trading partner agreements |  |  |  | State/Program Epidemiologist NEDSS / ELR Coord. State Legal Counsel Trading Partners IT |  | X | Trading Partner Agreement | Define and document detailed agreements for trading partners regarding sending data to public health including parameters regarding all interactions between the trading partners and public health facilities.
2.1.3 |  | Communicate reporting requirements |  |  | One time and then periodic as needed when changes occur | State/Program Epidemiologist NEDSS / ELR Coord. IT Trading Partners | X |  | Reporting requirements document | Communicate what will be reported and frequency / timeline; Communicate what data elements will be reported; provide IG and other implementation-related references to trading partners.
2.1.4 |  | Assist Trading Partners to Map Data |  |  | One time and then periodic as needed when changes occur | State/Program Epidemiologist NEDSS / ELR Coord. IT Trading Partners Informaticist |  | X | Data mapping guidelines and direction | Public health to work with trading partners if necessary to ensure appropriate mapping of data to message content and format standards. This could be performed by other programs.
2.2.0 | Conduct Training
2.2.1 |  | Conduct PH Staff training |  |  | Periodic | Epidemiologist Program Management IT NEDSS / ELR Coordinator Informaticist | X |  | Implement public health trading plan | Provide training for IT personnel, Disease Intervention Specialist, Epidemiologists. "What are the training needs"
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
2.2.2 |  | Conduct Trading Partner Staff Training |  |  | One time and then periodic as needed when changes occur | Epidemiologist Program Management IT NEDSS / ELR Coordinator Informaticist | X |  | Implement trading partner training plan | Provide training for Reporters (e.g., Hospital, Lab, and Physician). "What are the training needs"
2.3.0 | IT System Development and Enhancement
2.3.1 |  | Finalize system requirements |  |  |  | Project manager IT NEDSS / ELR Coordinator Informaticist Epidemiologist | X |  | IT System requirements document | Gather requirements for software, hardware, security and maintenance for IT system to support ELR.
2.3.2 |  | Develop Design Document |  |  |  | Project manager IT NEDSS / ELR Coordinator Informaticist Epidemiologist | X |  | IT System design document | Creating a detailed systems design document that addresses the requirements defined for the surveillance system.
2.3.3 |  | Develop System |  |  |  | Project manager IT NEDSS / ELR Coordinator Informaticist Epidemiologist | X |  | Develop IT system | Determine all IT requirements for developing IT infrastructure to support ELR system.
2.3.4 |  | Integrate and Test System, including UA testing |  |  |  | Project manager IT NEDSS / ELR Coordinator Informaticist Epidemiologist | X |  | Test IT system (testing, test results, implement fixes, etc.) | Execute test and QA plans to demonstrate that developed system conforms to requirements as specified in the Functional Requirements Documents.
2.3.5 |  | Implement System |  |  |  | Project manager IT NEDSS / ELR Coordinator Informaticist Epidemiologist | X |  | Implement IT system | Transition ELR system into production.
Connect and Test ELR System 3.0
3.1.0 | Initiate ELR implemnetation with trading partners (aka data provider) |  |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist |  |  |  | Check with trading partner to determine if their system is in place and they are able to send a message that complies with the implementation guide. Message should be compliant with structure as well as content requirements for public health.
3.1.1 |  | Trading partner system (e.g.., LIMS) able to produce standards-based structured message with appropriately mapped vocabulary |  |  | Varies by jurisdiiotn and trading partner | Project manager IT NEDSS / ELR Coord. Epidemiologist, Trading Partners | X |  | Summary of trading partner status | Assess if trading partner is able to construct an appropriate standards-based message using the correct terminology and vocabulary
3.1.2 |  | Confirm Connectivity (message transport) PHIN MS / Direct / Secure FTP |  |  |  | Trading Partner IT Health Department IT |  |  | Confirm network connectivity | Confirm that health department can receive message using transport method used by trading partner
3.1.3 |  | Validate the message |  |  |  | Project manager IT, Trading partners NEDSS / ELR Coord. Epidemiologist | X |  | Message testing and validation | Test and confirm message structure is correct, verify that content is correct.
3.1.4 |  | Test Routing and (transformation) of Message to appropriate recipients |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Test message routing | Test and confirm transformation of message is as expected, this may include transformation and / or routing of data to all recipients.
3.1.5 |  | Test consumption of message |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Test consumption of message | Ensure successful data storage and usability of stored data.
3.1.6 |  | Test DR system and process |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Disastor recovery test | Ensure the disastor recovery system is functioning as expected.
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
Validate 4.0
4.1.0 | Validate content and structure of message |  |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist
4.1.1 |  | Compare paper reports and electronic message |  |  | One time per trading partner - with possible random testing - Lesson Learned | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Comparison of paper and electronic (ELR) messages | Verify that reports and content received by paper are also included in electronic form. Ensure that codes and message tables are updated on a regular basis. This steps is intended to check the sensitivity and specificity of ELR with existing reporting processes (e.g., paper-based reporting, manual ELR, or other electronic)
4.1.2 |  | Validate analysis and reporting of data in message |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Message data validation | Verify that analyzed data shows the expected results and that reports include expected information. This step validates the message content and appropriate business rules for each condition received by ELR.
Operate 5.0
5.1.0 | Move data feed to production | Move data feeds to production |  |  |  |  | X |  |  | Partner / provider feeds - move to production
5.2.0 | Alerting
5.2.1 |  | Distribute surveillance guidelines, specific reporting requirements, and criteria to jurisdictions and trading partners |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Surveillance guidelines and reporting requirements | Send ELR guidelines / specific criteria for alerts and alerting to sub-jurisdictions, trading partners.
5.2.2 |  | Receive and manage lab reports of an agent associated with etiology of an immediately reportable condition |  |  |  | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Plan to manage lab results for an agent associated with etiology of an immediately reportable condition | Ensure that the right program and right staff receive an alert from their surveillance system that an agent associated with etiology of an immediately reportable condition is being reported
5.3.0 | Manage IT Systems
5.3.1 |  | Maintain hardware |  |  | Ongoing | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Hardware maintenance plan and schedule | Describe and define the maintenance necessary to support the system.
5.3.2 |  | Maintain software and operating system |  |  | Ongoing | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Software and operating system maintenance plan and schedule | Describe and define the software and operating system maintenance necessary to support the system
5.3.3 |  | Monitor data flows |  |  | Ongoing | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Data flow monitoring plan / process | Monitor data messaging from all trading partners is as expected and ensure timeliness of reports
5.3.4 |  | Analyze data and generate reports |  |  | Ongoing | Project manager IT NEDSS / ELR Coord. Epidemiologist | X |  | Data analysis and reports | Ensure ability to analyze and report on ELR data to support disease surveillance
Process Improvement and Growth 6.0
6.1.0 | Conduct operational analysis |  |  |  |  | Epidemiologist Program Management IT ELR Coordinator |  |  |  | Analyze and review the entire ELR system to determine if system performance (message flow, reporting, alerting, hardware and software systems) are performing as expected and results are as expected.
6.1.1 |  | Improve IT infrastrucure |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator |  | X | IT infrastructure review / improvement plan / process | Based on results from ongoing operational analysis, determine if improvements are necessary for the IT infrastructure (to either enhance or correct issues with the ELR system).
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
6.1.2 |  | Identify additional training needs |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator |  | X | Periodic training needs assessment | Determine if additional training needs exist and how define a strategy on how to meet those needs.
6.1.3 |  | Provide Ongoing Training |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator |  | X | Periodic ongoing training plan | Provide training as needed to continue support of the ELR system and provide trained staff (Including additional and / or back staff). This includes communicating changes in ELR functionality (e.g., viewing, managing, printing) with end-users
6.1.4 |  | Improve communication |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator |  | X | Communications review / analysis and improvement plan | Provide communication updates regarding overall improvement of process and cost / time savings (if applicable) resulting from the implementation of the ELR system.
6.1.5 |  | Streamline processes |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator |  | X | Process improvement analysis and plan | Analyze business and technical process and perform process improvement if necessary
|  | Monitor quality of data | [7 empty] | Monitor quality of received data
6.1.6 |  | Update planning documents |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator |  | X | Planning document review and updating process | Ensure ongoing process improvement plans are maintained and updated as needed to support active ELR system.
6.1.7 |  | Develop methods to manage process and paradigm change |  |  | One time | Epidemiologist Program Management IT ELR Coordinator |  | X | Compilation of change management strategies | Strategies to manage the communication of business process changes - Shared vision, mental models should be developed. Strategy examples: How will resistance to ELR be handled (e.g., locals who are used to paper labs)? How do we obtain buy-in from ELR data users? What can the agency do to ensure entities / persons impacted by process changes are prepared and understand their role in the bigger picture.
6.2.0 | Supporting Ongoing Changes
6.2.1 |  | Assess changes to reportable conditions list |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator | X |  | Reportable conditions list monitoring and updating plan | Continuously monitor and determine impact of changes made to reportable condition list or associated criteria or reporting requirements.
6.2.2 |  | Assess impact of changes to standards |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator | X |  | Change review and assessment plan for standards | Determine impact of changes to standards on operations
6.2.3 |  | Assess impact of change to trading partner's systems |  |  | As needed and as possible | Epidemiologist Program Management IT ELR Coordinator | X |  | Change review and assessment plan for trading partner systems | Determine how changes to the trading partners systems may impact agency operations
6.2.4 |  | Assess impact of change to operating systems / system software |  |  | As needed and as possible |  | X |  | Change review and assessment plan for IT systems | Determine how changes will affect the operating systems and software of the IT system.
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
6.2.5 |  | Assess impact of change to message transport mechanism |  |  | As needed and as possible |  | X |  | Change review and asssessment plan for message transport systems | Determine how changes will affect the message transport system.
6.3.0 | Implement and evaluate metrics (assess ELR coverage) |  |  |  |  | Epidemiologists NEDSS / ELR Coord.
6.3.1 |  | Assess percent of coverage by geography, by population, by conditions reported |  |  | Periodic | Epidemiologists NEDSS / ELR Coord. | X |  | Report on percentage of ELR coverage | * The percent of reportable conditions, including infectious and non-infectious, that are received from reporting laboratories. The percent of conditions reported by ELR is > 50% . Note: metrics are after split of message containing multiple metric items.
6.3.2 |  | Percent of labs (e.g., hospital, private) sending standards-based ELR |  |  | Periodic | Epidemiologists NEDSS / ELR Coord. | X |  | Report on percentage of labs sending standards-based ELR | Assess percentage of public and private labs sending standards based ELR lab.
6.3.3 |  | Assess percent of program area surveillance systems receiving and consuming ELR |  |  | Periodic | Epidemiologists NEDSS / ELR Coord. | X |  | Report on percentage of area surveillance systems receiving an consuming ELR | Assess percentage of program area surveillance systems receiving and consuming ELR data.
6.3.4 |  | Assess timeliness of reporting |  |  | Periodic |  | X |  | Report on timeliness of reporting | Determine timeliness of reporting (using appropriate baseline measurement - which may differ from jursidiction to jursidiction)
6.3.5 |  | Assess completeness of reporting |  |  | Periodic |  | X |  | Report on completeness of reporting | Analyze and determine completeness of reporting (using appropriate baseline measurement).
Note on C1: Function / Task identified as part of ELR.
Note on D1: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E1: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G1: Identify the potential owner(s) for this specific function.
Note on H1: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I1: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J1: Freeform text for comments or when needed to further clarify answers provided in preceding columns.
Note on C15: Function / Task identified as part of ELR.
Note on D15: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E15: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G15: Identify the potential owner(s) for this specific function.
Note on H15: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I15: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J15: Freeform text for comments or when needed to further clarify answers provided in preceding columns.
Note on C25: Function / Task identified as part of ELR.
Note on D25: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E25: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G25: Identify the potential owner(s) for this specific function.
Note on H25: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I25: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J25: Freeform text for comments or when needed to further clarify answers provided in preceding columns.
Note on C39: Function / Task identified as part of ELR.
Note on D39: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E39: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G39: Identify the potential owner(s) for this specific function.
Note on H39: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I39: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J39: Freeform text for comments or when needed to further clarify answers provided in preceding columns.
Note on C55: Function / Task identified as part of ELR.
Note on D55: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E55: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G55: Identify the potential owner(s) for this specific function.
Note on H55: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I55: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J55: Freeform text for comments or when needed to further clarify answers provided in preceding columns.
Note on C73: Function / Task identified as part of ELR.
Note on D73: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E73: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G73: Identify the potential owner(s) for this specific function.
Note on H73: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I73: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J73: Freeform text for comments or when needed to further clarify answers provided in preceding columns.
Note on C86: Function / Task identified as part of ELR.
Note on D86: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E86: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G86: Identify the potential owner(s) for this specific function.
Note on H86: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I86: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J86: Freeform text for comments or when needed to further clarify answers provided in preceding columns.

## Planning
Item # | Function | Step | Progress | Level of Effort (Low, Medium, High) | Frequency | Participants | Recommended | Optional | Deliverables | Description
Planning 1.0
1.1.0 | Obtain executive sponsorship (champion) | [5 empty] | X |  |  | Project champion - this role may differ from jurisdiction to jurisdiction and may be more than one single sponsor / champion.
1.1.1 |  | Define State Law/Regulation/Policy approach for ELR |  |  | one time | IT State Lab NEDSS / ELR Coordinator Epidemiologist Informaticist Outside PH partners | X |  | State and jurisdictional laws and / or regulations | Define, document and obtain necessary approval, sign-off for laws, regulations, and policy for implementation and maintenance of ELR.
1.1.2 |  | Define Business Need |  |  | one time | NEDSS / ELR Coordinator Epidemiologist Informaticist | X |  | Project scope and business justification for ELR | Include high level alternatives analysis and feasibility study, define ROI, describe stakeholders, conduct cost benefits analysis, identify issues and risks and constraints.
1.1.3 |  | Assessing Current Status |  |  | one time | IT State Lab & other labs NEDSS / ELR Coordinator Epidemiologist Informaticist Outside PH partners | X |  | Document of current status and background | Analyze and review the current system to determine if system performance (data flow, reporting, alerting, hardware and software systems) are performing as expected and results are as expected. This step is intended to describe the current state of the "system", either paper or electronic, and address gaps.
1.1.4 |  | Assess Current Business Need |  |  | one time | IT State Lab NEDSS / ELR Coordinator Epidemiologist Informaticist Outside PH partners | X |  | Document of current business need | Based on on programmatic needs determine what is required to address these needs. This includes an understanding of where trading partners are in their capability.
1.1.5 |  | Define Programmatic and IT System Scope |  |  | one time | IT State Lab NEDSS / ELR Coordinator Epidemiologist Informaticist | X |  | Detailed Programmatic and IT business scope | Describe the scope of the entire ELR System including the data flow from trading partners, data routing to surveillance systems. Include planning to manage process and paradigm change. This is a programmatic scope.
1.1.6 |  | Identify and Secure Funding Sources |  |  | on going | State Lab NEDSS / ELR Coordinator State Epidemilogist / Epi Progam Management | X |  | Detailed summary of all available funding sources | Identify and secure financial support to execute scope and objectives. Investigate and include all potential funding sources , grants and programs.
1.1.7 |  | Project Charter |  |  | One time | NEDSS / ELR Coordinator Informaticist | X |  | Project Charter | Includes business need, alternative analysis, change management, and resource requirements.
1.2.0 | Update policy and law
1.2.1 |  | Assess and Update legislation, regulation, or policy |  |  | One time | State/Program Epidemiologist NEDSS / ELR Coordinator State Legal Council | X |  | Summary of existing laws, regulation and policy. | Ensure that ELR is actually allowed within the states based on existing laws, regulations and policies. Possibly initiate process to modify or amend existing laws, regulations and policy if necessary to implement ELR.
|  | Define data elements and reconcile data elements from multiple sources |  | Medium | One time | Program Epidemiologists NEDSS / ELR Coordinator, IT |  |  | Reconcile forms. | Reviewing the content of the report forms including the data elements to serve as a basis for fields to be included in an electronic exchange. Paper forms may be used as a back-up, web based entry may still exist for smaller sites
1.2.2 |  | Define what to report, who, when, and how |  |  | One time | Program Epidemiologists NEDSS / ELR Coordinator, State legal counsel, IT, PH Lab | X |  | List of what to report, who receives the reported items, and when and how the data are sent to public health. | For each jurisdiction - based on laboratory tests or results determine if this qualifies as a condition to report to public health. This must also factor in reporting requirements and reporting criteria specific to the jurisdiction. (e.g., Hepatitis A IgM positive). Further specificity by public health may indicate when a test result should be received (or sent) within a given time frame.
1.2.3 |  | Create / update MOU or trading partner agreement |  |  | Periodic | Program Epidemiologists NEDSS / ELR Coordinator, State legal counsel, IT |  | X | MOU and / or trading partner agreement. | Create standard template for use in engaging trading partners and specify data transport method
1.3.0 | Define Scope of IT System Development / Enhancements
1.3.1 |  | Engage trading partners |  |  | One time | Epidemiologist Program Management IT, ELR Coordinator | X |  | List of eligible trading partners | Determine the strategy for engaging data trading partners, surveillance programs and IT programs. Determine appropriate strategies for both internal and external data trading partners.
1.3.2 |  | Determine Scope of IT System |  |  | One time | IT (business analyst) NEDSS Coord. Epidemiologist Informaticist ELR Coordinator | X |  | IT system scope | Describe the vision and scope of the systems work that needs to be done. This should include the business justification for the system, high level business requirements and functional requirements and a baseline alternatives analysis which supports the decision to buy or build the IT system.
1.3.3 |  | Build IT Project Plan |  |  | One time | Project manager IT NEDSS / ELR Coordinator Informaticist Epidemiologist | X |  | IT Project Plant | Develop project management plan and other planning documents; Identify required resources for implementation of IT infrastructure to support ELR.
1.3.4 |  | Develop / Update Technical Implementation Guide for Trading Partners |  |  | One Time with periodic updates | IT NEDSS / ELR Coord. Epidemiologist Informaticist | X |  | Technical implementation guide for Trading Partners | Provide guidelines for secure transport, message format, vocabulary usage and required data elements. Clearly identify reporting requirements.
1.3.5 |  | Define continuity of operations |  |  | One Time with periodic updates | Epidemiologist Program Management IT ELR Coordinator Informaticist Trading partners Incident commanders | X |  | Disastor recovery plan | Ensure that ELR is able to continue in the event of loss of key personnel or loss of infrastructure (business continuity), including disaster recovery. Includes disaster recovery and may be part of the overal disastor recovery plan.
1.3.6 |  | Define Surge Capacity Strategy (On-boarding strategy) |  |  |  | Epidemiologist Program Management IT NEDSS / ELR Coordinator PH Management |  | X | Surge capacity / on-boarding strategy | The strategy for supporting a dramatic increase in requests to support ELR due to recent public events or recent policy (e.g., Meaningful Use) and / or to support the increase in number of data trading partners.
1.4.0 | Define Training Needs
1.4.1 |  | Assess PH staff training needs and and plan training |  |  |  | Epidemiologist Program Management IT NEDSS / ELR Coordinator Informaticist | X |  | Public Health Staff training needs assessment / training materials | Identify/Assess training for IT personnel, Disease Intervention Specialist, Epidemiologists. "What are the training needs". Include training on standards, vocabulary, new systems being implemented and new information flows.
1.4.2 |  | Design and Develop Trading Partner / Partner Staff training |  |  |  | Epidemiologist Program Management IT NEDSS / ELR Coordinator Infection Control Lab Informaticist | X |  | Trading Partner Training Plan / Materials | Identify/Assess training for Reporters (e.g., Hospital, Lab, and Physician). "What are the training needs". May consist of communications rather than training. Should include orientation or kick-off process / event for trading partners.
1.5.0 | Communications | [5 empty] | X |  | Communications package | This is internal and external communications with trading partners, with program areas, with users about training needs, with trading partners, with leadership. May also be with end users on what to expect - how to read / use the online screen to read, etc.
1.6.0 | Specify Laboratory Reporting Criteria |  |  |  | On going | State/Program Epidemiologist NEDSS / ELR Coord. Informaticist State Lab | X |  | Laboratory Reporting Criteria Document | What tests should be reported for each organism, reference ranges, business rules. May include choosing which LOINC codes are acceptable, identifying specific diseases.
Note on C1: Function / Task identified as part of ELR.
Note on D1: Indicate the level of progress (at this point in time) that your state has made for this specific function.
Note on E1: Please indicate the level of effort your state has utilized to this point regarding the specific function
Note on G1: Identify the potential owner(s) for this specific function.
Note on H1: Indicate whether or not this is a required function (from your ELR experience) - Yes / No
Note on I1: Indicate whether or not this is a optiona lfunction (from your ELR experience) - Yes / No
Note on J1: Freeform text for comments or when needed to further clarify answers provided in preceding columns.